## Target Timeline
ERCOT System Change - Target Implementation Dates
| 2001-12-31 | 2002-01-15 | 2002-01-31 | 2002-02-05 | 2002-02-15 | 2002-02-28 | 2002-03-15 | 2002-03-31 | 2002-04-15 | 2002-04-30 | 2002-05-15 | 2002-05-31 | 2002-06-15 | 2002-06-30 | 2002-07-15 | 2002-07-31 | 2002-08-15 | 2002-08-31
Internal ERCOT Projects
PIP116, 117 & 118 Outage Scheduler | 2001-12-31: Implement. 1/31/02
PIP140, 160, 161 TCRs | 2001-12-31: Implement 2/15/02
Phase 2b Project
PIP110 SCE Ramp Rate | 2001-12-31: Implement 2/05/02
PRR300 DA of Interzonal Cong. | 2001-12-31: Implement 2/15/02
PRR305 Inter-QSE Trades for DA Interzonal Cong. | 2001-12-31: Implement 2/15/02
PIP151 RTs | 2001-12-31: Implement 2/15/02
PIP120, PRR270/271 Local BE Prem. | 2001-12-31: Implement 4/1/02
PRR222 Market Sol. | 2001-12-31: Implement 4/1/02
PIP147 Bid Exp. Time | 2001-12-31: Implement 4/1/02
PIP148 Remove A/S bids | 2001-12-31: Implement 4/1/02
PIP105 Gen Split | 2001-12-31: Implement 4/1/02
PIP132 MMS in RPRS | 2001-12-31: Implement 4/1/02
PIP119 OOME for LaaRs | 2001-12-31: Implement 4/1/02
PIP137/PRR211 BE bids w/RPRS | 2001-12-31: Implement 4/1/02
PIP150 Adj. Sked Not. | 2001-12-31: Implement 4/1/02
PIP198 | 2001-12-31: Implement 4/1/02
PIP112 BUL | 2001-12-31: Target Date being assessed by vendor
PIP210 Part. Block Deploy | 2001-12-31: Target Date being assessed by vendor

## System Change
[6 empty] | Urgency: |  | 1 - highest | LEGEND: Red | - Project underway.
[8 empty] | 2 | Yellow | - Currently being staged.
[8 empty] | 3 | Green | - Currently not staged.
[9 empty] | Blue | - Pending approval.
No. | Item Description | Rec Doc Status* | Priority | Urgency | Related Items | Market | Language Author | Protocol X-REF | Proposed Implementation Date | Comments
STATUS:RED-Project Phase 2; design, build and implementation underway by ERCOT staff and vendor
PIP116 | Outage Scheduler GUI Inadequate | Complete |  |  |  | Wholesale | L. Caylor, R. Poston | 8.1.4 | 2002-01-31 | System Change: Revise and split GUI interface into two. Manual Workaround: Must interpret comments field The comment field in the Outage Scheduler supports a maximum of 1000 characters. All the information boxed will need to be initially submitted in the comment field of the Outage Scheduler, until the GUI panel is built to support a specific field entry of the items boxed
PIP117 | Outage Scheduler automatic receipt acknowledgement | Complete |  |  |  | Wholesale | L. Caylor, R. Poston | 8.4.2 | 2002-01-31 | Outage Scheduler does not automatically acknowledge receipt of outage request/notification. Needs to do auto acknowledgement email. System Change: Alter to provide systematic acknowledgement Workaround: Gather outage requests and reply manually Interim Language proposed to indicate automatic acknowledgement is not occuring. ERCOT may adjust priority.
PIP118 | Outage Scheduler time and date stamp submissions | Complete |  |  |  | Wholesale | L. Caylor, R. Poston | 8.4.3 | 2002-01-31 | Outage Scheduler does not time and date stamp submissions and thus cannot keep track of when submissions are made. ERCOT personnel have no way to comply with the timelines other than to track submission request dates manually. Needs to have submissions time and date stamped and to allow submissions to be sorted by date submitted to facilitate compliance with response timeline. System Change: Support time and date stamp Workaround: Manually support within three days and between 3 and 8 days Struck reference to support of further timeline support until time and date stamp is supported systematically. ERCOT may adjust priority.
PIP140 | No TCRs at market open | Complete |  |  | PIP160 PRR300 | Wholesale | J. Bian | 4.4.1 table | 2002-02-15 | Reference to submitting TCRs with schedules struck from 4.4.1 table. The requirements/process for submitting TCRs to be addressed by future change control group (PCP). Assigned to TCR Task Force
PIP160 | TCR identification number | Complete |  |  | PIP140 PRR300 | Wholesale | J. Bian | 7.5.4.2 | 2002-02-15 | Words referencing creating a unique identification number have been struck until the process can be addressed by future change control group (PCP). Assigned to TCR Task Force
PIP161 | TCR Financial Settlement | Complete |  |  | PRR300 | Wholesale | J. Bian | 7.5.4.3 | 2002-02-15 | To be addressed by future change control group (PCP). Language reflected in the Protocols indicates how to collect funds as a result of the TCR auction, but not how to distribute the funds. Assigned to TCR Task Force
STATUS:RED-Project Phase 2b; design, build and implementation underway by vendor
PIP110 | SCE Ramp Rate | Complete |  |  | PIP 113 | Wholesale | B. Jones | 6.5.2(17) | 2002-02-05 | Ramp should be considered part of instructions, even if outside the Settlement Interval. System cannot currently support this; Language including ramping outside the Settlement Interval has been struck in current protocols and boxed language for the future implementation has been drafted for incorporation once the system can support. Priority based on resolving ramp rate as instructed deviation. Other ramp issues in 110PIP will be address with PRR286. Currently in internal testing at ERCOT. Partial implementation on 1/18/2002.
PRR300 | Direct Assignment of Interzonal Congestion |  |  |  | PIP 140, 160 161 PRR280 PRR296 | Wholesale |  | 2, 6, 7, 9, 16, & 22H | 2002-02-15 | $20 mm threshold hit on 8/14/01. Comm. Order required direct assignment of cost within 6 mos. Implementation on or before 2/15/02
PRR305 | Inter-QSE Trades for Direct Assignment of Inter-zonal Congestion |  |  |  | PRR300 | Wholesale |  | 7.3.4
PIP120 | Local Balancing Energy Premiums | Complete |  |  | PRR222, PRR270, PRR271 | Wholesale | J. Yu; T. Doggett | 6.7.1.2(5) 7.4.3 4.3.2(8) | 2002-04-01 | System supports submitting bid premiums for Resource-specific bids on the Resource Plan. MOS/POS algorithms utilize premium in solving Local Congestion, but this data would need to be passed to Settlement and included in Resource specific charges. A corresponding formula and charge type will need to be created. Drafts of the formula are boxed, and were modified by PRR292.
PRR270 | Unit Specific Dec Premiums |  |  |  | PIP120 | Wholesale |  | 6.7.1(5) | 2002-04-01 | Implementation with PIP120
PRR271 | Local Congestion |  |  |  | PIP120 | Wholesale |  | 6.7.1.2(10) | 2002-04-01 | Implementation with PIP120
PRR222 | New Definition of Market Solution |  |  |  | PIP120 | Wholesale |  | 2.1 | 2002-04-01 | Modify system to use the modified definition of market solution based on 3 resources that are not affiliated with each other submitting bids
PIP147 | Expiration times for bids | Complete |  |  |  | Wholesale | T. Doggett | 4.4.11 4.4.11(6) 4.4.16(8) 4.5.2(5) 4.5.3(5) | Tentative 4/1/2002 | System does not support expiration times for bids Language boxed referencing support of specifying bid expiration time until system is designed to support.
PIP148 | Removing a portion of AS bids | Complete |  |  |  | Wholesale | T. Doggett | 4.5.8 | Tentative 4/1/2002 | System does not allow portion of AS bids to be removed. References to this function have been boxed for when system does support. System Change: support retraction of portion of AS bids. No recognized workaround. Important for QSE to manage schedules.
PIP105 | Generation Meter Splitting | Complete |  |  |  | Wholesale | R. Lozano | 10.3.2.1.6 | 2002-04-01 | Multiple owners of a single unit want to be able to split the generation meter for load (auxiliary power). Currently system does not accommodate split of generation meters. Protocol allows for load splitting only when all channels of a split meter are scheduled through one REP. Reference to multiple CRs struck in current protocols and boxed language supporting splitting load drafted for implementation once the system supports.
PIP132 | Mismatched Schedules in PRPS Underscheduled Charge |  |  |  |  | Wholesale |  | 6.9.2.1.1 | Tentative 4/1/2002 | There is no design to implement the maximum mismatched schedule amount as part of this charge. Underscheduling can be a severe problem; it is important in assessing a cost that mismatched amounts are included. Option discussed of once implemented, making it a separate underschedule fee for reporting and tracking purposes. Formula modified to remove mismatch quantity reference, but boxed for future implementation.
PIP119 | OOME for Loads acting as Resources |  |  |  |  | Wholesale |  | 6.5.2(20) | 2002-04-01 | The calculation for OOME only takes instructions to generators into account. There is no provision for Loads acting as a Resource in the OOME market. Struck reference to Load acting as a Resource as providing OOME, and boxed future language for when service is available in the system.
PIP198 | EPS Load Resource Meters | Complete |  |  | PRR283 | Wholesale |  | 10.2.3 | 2002-04-01 | Option for Load acting as a Resource to EPS Metering was boxed until system can support. System Change: Design and develop system to support EPS metering for Load acting as a Resource Workaround: No support of EPS metering for Load acting as a Resource.
PIP210 | Partial Block Deployment | Complete |  |  | PIP112 | Wholesale | K. Gresham | 6.7.1.1 6.7.4 | Phase 2 | This is new language adopted by RUG (12/6/2000). Need input. Demand Side Task Force. Vendor has design issues, developing timeline.
PIP112 | Balancing Energy Up Load | Partial w/ 107 |  |  | PIP 107 PIP111 PIP210 PRR302 | Wholesale |  | 6.8.1.14.3 | Phase 2 | Not supported in current system design; System change required. Protocol language proposed and boxed until system supports design. Priority unchanged, however, ERCOT & Stakeholders expressed concern with accomplishing this by 01/01/02. Input required. Demand Side Task Force. Vendor has design issues, developing alternatives and timeline.
PIP137/PRR211 | Association of BE Bids with RPRS | Complete |  |  |  | Wholesale | T. Doggett | 6.6.3.2.1(16) 4.1.1. Table 4.4.16(3) | Phase 2 | This concept was not included in the July 27th protocols and the system does not associate Balancing Energy bids with RPRS. When functionality added, add “and associated Balancing Energy bids to last sentence in QSE’s Submission for 1430 and add “and save RPRS energy bids for applicable balancing markets” in ERCOT Responsibility for by1630
STATUS:YELLOW; Project Phase 2b; ON HOLD FOR STAKEHOLDER INPUT
PIP123 | Defaulting AS Supplier |  |  |  | PRR295 | Wholesale |  | 6.3, 6.9 | On hold pending PRR295 | QSE in default of providing A/S; put on hold on 1/1/02 until PRR295 is resolved
PIP115 | Uncontrollable Resources (e.g wind) Deviations | Complete |  |  | PRR293 | Wholesale |  | 6.8.1.15 | On hold pending PRR293 | New wording has been added regarding treatment of deviations from uncontrollable renewable resources under section 6.8.1.15 (Uninstructed Deviations).
PIP150 | Adjusted schedule notification | Complete |  |  |  | Wholesale | T. Doggett | 4.7.2(c ) 4.7.2(e) | On hold | Current design does not provide a notification message to QSE as to the adjustment in its Schedule System Change: provide notification that mismatch was adjusted by ERCOT Workaround: Until fixed, QSE will monitor schedule status on the portal. P1 can send out sked amt. and notice that sked didn't change, but can not change sked. Need input from WMS; scheduled to discuss on 1/31/02.
PIP151 | Responsibility Transfers | Complete |  |  | 287PRR | Wholesale | T. Doggett | 4.9.4 | 2002-02-15 | System does not support Responsibility Transfer Schedules as currently in the Protocols. No box in Protocols. System change on hold until stakeholder input/approval of PRR287.
PIP156 | TTC and CSC forecasts | Complete |  |  |  | Wholesale | J. Bian | 4.4.2(2) 7.3.2.2 | Phase 3 | In Section 7.3.3.2, Tracking Balancing Energy CSC Cost, the definition of TTCcsc is changed from actual Total Transfer Capacity to annual Total Transfer Capability. This is supported by the system. Reference to forecast of Total Transfer Capability in 4.4.2(2) is neither calculated or posted by the system. System Change: Post load area forecasts. Need Input from WMS
PRR247 | Ratcheting of OOME |  | High |  | PRR281 PRR282 | Wholesale |  | 6.8.2.2 | Remanded to WMS by TAC | On hold pending Stakeholder input. Under review by QSEWG.
STATUS YELLOW: NOT RELEASED TO VENDOR; Ordered by PUCT (Docket No. 23220) & Need Stakeholder Input
| Two Settlement System |  |  |  | PRR295 | Wholesale |  |  | 2002-06-01 | Commission Ordered; assigned to PRS. J. Galvin working on requirements
| Simultaneous Procurement of AS |  |  |  |  | Wholesale |  |  | Phase 2 | Commission Ordered; assigned to WMS. WMS working with PUCT. WMS sent a white-paper to PUCT in Nov01 at the 10kft level; need to take to Protocol level.
| Intrazonal Direct Assignment |  |  |  |  | Wholesale |  |  |  | Commission Ordered - issued April 11, 2001.
| New Uninstructed Deviation Calculation |  |  |  |  | Wholesale |  |  | Phase 2 | Commission Ordered. Use second subsequent settlement interval expost MCPE for settlement of uninstructed deviation during the first settlement interval. assigned to WMS. Assigned to Demand WG by WMS.
| Single-round, Simultaneous, Combinatorial Auction for TCRs |  |  | 2003 |  |  |  | 7.5.3.2
STATUS GREEN: NOT RELEASED TO VENDOR; Prioritized by Stakeholders
PRR234 | RMR Margin Option |  | Delete |  |  | Wholesale |  | 6.8.3.7 |  | Give an RMR Unit owner the option of retaining 10% of net positive margin for energy generation in excess of RMR Energy. Manual calculation is a pratical alternative, remove item from list.
PIP106 | Direct Load Control (DLC) | Complete | High | 3 | PIP175 | Wholesale & Retail | W. Reid | 18.7.2 6.3.2 18.2.10 18.2.1.(7) | Phase 3 | Currently there is not a profile for DLC and the system cannot currently support the use of this type of profile. All sections and comments related to DLC have been boxed in protocols and will be released when accomodated by the system. A long lead time has been identified as a factor to implementation.
PIP153 | Posting Congestion and Insufficiency Information | Complete | High | 2 |  | Wholesale | J. Bian | 4.4.9 | Phase 3 | No direct notification occurring as protocols directed, but information is being posted. Congestion notice - resolved; manual work around for capacity insufficiency. Posting requirement related to PIP134, PIP138 & PIP155.
PIP155 | Zonal forecast posting |  | High | 2 |  | Wholesale |  | 4.2.(1) | Phase 3 | ESCA clarification: "Load area forecast" will not be published. System Change: Post load area forecasts Language referencing load area forecast has been boxed until system supports publication. Posting requirement related to PIP134, PIP138 & PIP153.
PRR281 | Change ERCOT Deployment Instructions to Settlement Meter Specific |  | High | 1 | PRR282, PRR247 | Wholesale |  | several |  | Deployment instructions should be provided on a Settlement Meter basis and NOT on a unit or generator specific basis. Currently being discussed at the QSEWG/WMS.
PRR282 | Define OOME as an Instructed Deviation |  | High | 2 | PRR281, PRR247 | Wholesale |  |  |  | QSEWG developing Protocol language.
PRR310 | Estimating Usage Applied to Profiles |  | High | 1 |  | Retail |  | 11.3.2; 11.3.4.1 |  | Revise Protocol formulas to estimate usage when no actual meter read data is available for the day being estimated. Pending TAC & Board approval.
PRR258 | Notification Automation if Permit Required |  | High- extremely need tomorrow | 1 |  | Retail |  | 15.1.1.2, 15.1.1.7, 15.1.1.7 | Version 1.5 [Original target 7/01/02] | Process needed to automate the notification for when a Permit is required. TDSP needs to notify the CR, so the CR can communicate this info to the customer. The TDSP will not energize the premise without a permit/inspection, therefore the customer (moving-in) will not have power until all city inspections are complete and returned to the TDSP. TDSPs have a large volume of permits and need to handle them in an automated fashion. 30k/month need permits.
PRR259 | Process Automation for Unexecutable Move-Ins |  | High, currently manual. Same as 258PRR. | 1 |  | Retail |  | 15.1.4.5 | Version 1.5 [Original target 7/01/02] | A process is needed to automate the notification for when a Move-in is unexecutable. The TDSP needs to notify the CR, so the CR can communicate the information to the customer. The TDSP will not energize the premise in certain “unexecutable” cases; therefore the customer (moving-in) will not have power until all repairs are complete. TDSPs need to handle unexecutables in an automated fashion.
| MIMO Issues - Priority Issue |  | High, immediate implementation | 1 |  | Retail |  |  | Phase 3 | Long-term solutions for stacked move-ins, and move-ins/move-outs with date changes.
| CR Cancel of Switch |  | High, immediate implementation | 2 |  | Retail |  |  | Phase 3 | A solution that will allow the CRs to cancel switches that they submitted.
| TDSP Date Change Response/Change Requested Date |  | High, immediate implementation | 1 |  | Retail |  |  | Phase 3 | The 814_13 will need a new segment to identify that the TDSP is responding to a date change request with a different date than requested.
| Premise Info Rejects |  | High, immediate implementation | 1 |  | Retail |  |  | Phase 3 | ERCOT forward to the CR, the 814_04 premise info reject by the TDSP.
PRR303 | Move-In Rejections |  | High, immediate implementation | 1 |  | Retail |  | 15.1.4.9 |  | The stacked move-in resolution modified the Not First In validation to allow a Move-In when another Move-In is pending, but only when the requested Move-In in later than the pending Move-In. This PRR is pending approval by TAC & the Board.
PRR261 | CR Notification of Move In/Move Out Date Gap |  | High, same as 258PRR. | 1 |  | Retail |  | 15.1.5.7, 15.1.5.9 | Version 1.5 | A process is needed to notify a CR when move-in date changes have caused a gap between a customer who is moving into a premise and another customer who is moving out of the premise. This issue was submitted with multiple options. It has been deferred and remanded to RMS to choose an option. Approved by PRS on 12/20/01 and TAC on 1/3/02. Pending consideration by BOD
PIP101 | POLR Historical Usage | Complete | Low |  |  | Retail | C. Moseley | 15.1.2.7 | Phase 3 | System was designed to send historical usage to POLR when customer sent to POLR. The change to be implemented is that ERCOT will act as the transaction point and will receive the historical data and then send it to POLR upon POLR request. Language boxed regarding usage directly to POLR until system change is implemented. Need RMS to determine whether this is still desired. Low priority RMS may submitt PRR to remove box & not require a system change.
PIP102 | Voltage Support Compensation | Complete | Low |  |  | Wholesale | V. Gates | 6.8.4 6.9.3(1) 6.1.7 6.5.8 | Phase 3 | System not designed to calculate compensation for voltage support.
PIP104 | Black Start | Complete | Low |  |  | Wholesale | B. Jones | 6.8.5 6.9.4.1 6.1.8 | Phase 3 | Current system design uses a simple capacity multiplied by a fee to determine payment. The protocol has a more complex formula which uses a rolling unit availability factor. No Change to Protocols. System Workaround required and supported by ERCOT. ERCOT may adjust the priority if necessary. Manual work around.
PIP134 | Messaging System Language Clarification | Complete | Low |  |  | Wholesale | T. Doggett | 6.4.2 | Phase 3 | Langauge clarification: information is posted by ERCOT, but not using the Messaging System. Language boxed for future system support. Question for WMS: should box be removed? Posting requirement related to PIP138, PIP153 & PIP155.
PIP138 | Posting BE Forecast |  | Low |  |  | Wholesale |  | 6.7.1.1(6) | Phase 3 | Not designed to be posted publically; reference to posting currently struck, but boxed for future implementation. In Sept. 2001, said this was no longer needed. Should the box be removed? Posting requirement related to PIP134, PIP155 & PIP155.
PIP207 | Capacity Insufficiency | Complete | Low |  |  | Wholesale | C. Moseley | 6.6.7.1, 6.8.1.1(2)(b), 6.8.1.3, 6.8.1.5, 6.8.1.9, | Phase 3 | System Change: Automate system to derive prices under capacity insufficency conditions in accordance with protocols Workaround: ERCOT staff creates derived prices manually
PIP208 | Posting Declining OOMC and OOME Dispatch Instructions | Complete | Low |  |  | Wholesale | C. Moseley | 6.5.10 | Phase 3 | System Change: Automate posting of decline of any OOMC or OOME instructions; Workaround: Manual post declines to provide OOMC/OOME How would this be automated? Should always be manual process? If so, delete box. No box in Protocols, remove item.
PRR272 | Add Distribution Zone to Data Query. |  | Low |  | PRR312 | Retail |  | 15.2 |  | Need the Distribution Zone (DZ) field to identify which power pool an ESI ID is located.
| Ad-hoc Usage Request Process Flow |  | Low |  |  | Retail |  |  | Phase 3 | Change the timing of the generation of the 814_27 response.
PRR306 | TCR Ownership Limitation |  | Low |  | PRR313 | Wholesale |  | 7.5.9 |  | Pending PRS, TAC & Board approval. Comments due 2/04/02.
PRR307 | Controllable Resources |  | Low |  |  | Wholesale/ Retail |  | 2.1; 5.6.7; 6.1.2; 6.1.3; 6.1.4; 6.5.1.1; 6.5.2; 6.5.3; 6.5.4; 6.5.6; 6.7.3; 6.8.1.12; 6.10.4.4 |  | This Protocol revision defines Load which can provide Regulation Service. Pending PRS, TAC & Board approval. It is recognized that this issue should be addressed, however, it does not have to be implemented this fiscal year.
PRR311 | DLC to BUL Tansition |  | Low |  |  | Wholesale/ Retail |  | 6.10.5.2; 6.10.2; 6.8.1.14 |  | Pending PRS, TAC & Board approval. The priority may increase in 2003.
PRR312 | Enhance ESI Look-up Function |  | Low |  | PRR272 | Retail |  | 15.2 |  | Pending PRS, TAC & Board approval.
PRR313 | TCR Transfer Deadline |  | Low |  | PRR306 | Wholesale |  | 7.5.7 |  | Pending PRS, TAC & Board approval. Comments due 2/04/02. It is recognized that the software may already be capable of performing this function & there may be minimal delay in implementing this issue.
PIP158 | Contents of Dispatch Instructions | Complete | Medium |  |  | Wholesale | T. Doggett | 5.4.2(1) | Phase 3 | Split language to separate requirements for verbal Dispatch Instruction and systematic Dispatch Instructions. System does not support all of the indicated contents of the systematic dispatch instruction. Language boxed for future implementation. System Change: to include issuing authority in Dispatch Instruction, and time notification and operating level information. Workaround: Provide verbal/faxed instructions; Buy more regulation; Implement voice recorders Interim Language: denote timestamp on Dispatch Instruction Are the boxed items still needed? If so, system impact is on P1 XML.
PIP188 | Forward of Meter Read Information within 4 hours |  | Medium |  |  | Retail |  | 15.1.2.8, 15.1.5.6, 15.1.4.8, 15.1.10 |  | D. Odle to review with RMS whether still needed. ERCOT system capacity review if still needed.
PIP204 | EPS Meter Data Transmittal | Complete | Medium |  | PRR283 | Wholesale/ Retail | J. Cohea | 10.2.3 10.3.2.1.6 | Remanded to RMS by TAC | New section on treatment of EPS Load Data was added, and necessary by June 1st to avoid workaround costs incurred by the TDSP. A new section was drafted with reference to making consumption data available to market participants of EPS meters boxed until system supports it. RUG reviewed and approved the changes as drafted. Boxed changes redistributed and accepted by ERCOT.
PRR260 | Auto Purge Process if Permit Not Received |  | Medium |  |  | Retail |  | 15.1.1.7, 15.1.4.5 | Version 1.5 [Original target 7/01/02] | Facilitates purging of Move-ins that require a permit, but the permit is not received by the TDSP. Purge if the transaction is stale.
| Change Controls |  | Medium |  |  | Retail |  |  | Phase 3 | All change controls approved for the next release, to be included in Version 1.5 release/ERCOT Phase 3 release. 10 have been approved; 3 impact ERCOT.
| Customer Information Segments |  | Medium |  |  | Retail |  |  | Phase 3 | Capture the customer name information from the 814_01 and 814_16 and pass the same on to the TDSPs via the 814_03.
PIP128 | Synchronous Condenser Compensation | Complete |  |  |  | Wholesale | V. Gates | 6.8.3.2(4) 6.8.3.4(2) 6.8.3.6 6.9.4.3 | Phase 3 | No design for support of Sychronous Condenser Service. Language on payment and load uplift boxed until system supports; Reference to no compensation made in protocols. QSEWG re-evaluate need.
|  | Complete |  |  |  |  | Registration