## Target Timeline
ERCOT System Change - Target Implementation Dates for Projects in Progress
| 2002-02-28 | 2002-03-18 | 2002-04-01 | 2002-05-01 | 2002-05-20 | 2002-05-20 | 2002-05-31 | 2002-06-15 | 2002-06-30 | 2002-07-15 | 2002-07-31 | 2002-08-15 | 2002-08-31
Internal ERCOT Projects
PRR306 TCR Ownership Limit | Implement 5/1/02
PRR313 TCR Transfer Deadline | Implement 5/1/02
Phase 2b Project
PIP105 Gen Split | Implement 3/18/02
PIP198 | Implement 3/18/02
PIP119 OOME for LaaRs | Implement 4/1/02
PIP120, PRR270/271 Local BE Prem. | Implement 4/1/02
PRR222 Market Sol. | Implement 4/1/02
PIP147 Bid Exp. Time | Implement 5/20/02
PIP148 Remove A/S bids | Implement 5/20/02
PIP132 MMS in RPRS | Implement 5/20/02
PIP137/PRR211 BE bids w/RPRS | Target date being assessed by vendor/ERCOT (need input from WMS)
PIP151/PRR287 Resp Transfer | Target date being assessed by vendor/ERCOT
PIP150 Adj. Sked Not. | Target date being assessed by vendor/ERCOT
Phase 3 Project
PIP112 BUL | Target Date being assessed by vendor/ERCOT
PIP210 Part. Block Deploy | Target Date being assessed by vendor/ERCOT

## System Change
[6 empty] | Urgency: |  | 1 - highest | LEGEND: Red | - Project underway.
[8 empty] | 2 | Yellow | - Currently being staged.
[8 empty] | 3 | Green | - Currently not staged.
[9 empty] | Blue | - Pending approval.
No. | Item Description | Rec Doc Status* | Priority | Urgency | Related Items | Market | Language Author | Protocol X-REF | Proposed Implement Date | Comments
STATUS:RED-ERCOT Internal project; design, build and implementation will be done by ERCOT staff pending TAC and BOD approval in March
PRR306 | TCR Ownership Limitation |  |  |  | PRR313 | Wholesale |  | 7.5.9 | 2002-05-01 | Approved by TAC, Mar. 07. Pending Board approval in March. If approved, will be implemented.
PRR313 | TCR Transfer Deadline |  |  |  | PRR306 | Wholesale |  | 7.5.7 | 5/1/2002? | Approved by TAC, Mar. 07. Pending Board approval in March. It is recognized that the software may already be capable of performing this function & there may be minimal delay in implementing this issue.
STATUS:RED-Project Phase 2b; design, build and implementation underway by vendor
PIP105 | Generation Meter Splitting | Complete |  |  |  | Wholesale | R. Lozano | 10.3.2.1.6 | 2002-03-18 | Multiple owners of a single unit want to be able to split the generation meter for load (auxiliary power). Currently system does not accommodate split of generation meters. Protocol allows for load splitting only when all channels of a split meter are scheduled through one REP. Reference to multiple CRs struck in current protocols and boxed language supporting splitting load drafted for implementation once the system supports.
PIP198 | EPS Load Resource Meters | Complete |  |  | PRR283 | Wholesale |  | 10.2.3 | 2002-03-18 | Option for Load acting as a Resource to EPS Metering was boxed until system can support. System Change: Design and develop system to support EPS metering for Load acting as a Resource Workaround: No support of EPS metering for Load acting as a Resource.
PIP120 | Local Balancing Energy Premiums | Complete |  |  | PRR222, PRR270, PRR271 | Wholesale | J. Yu; T. Doggett | 6.7.1.2(5) 7.4.3 4.3.2(8) | 2002-04-01 | System supports submitting bid premiums for Resource-specific bids on the Resource Plan. MOS/POS algorithms utilize premium in solving Local Congestion, but this data would need to be passed to Settlement and included in Resource specific charges. A corresponding formula and charge type will need to be created. Drafts of the formula are boxed, and were modified by PRR292.
PRR270 | Unit Specific Dec Premiums |  |  |  | PIP120 | Wholesale |  | 6.7.1(5) | 2002-04-01 | Implementation with PIP120
PRR271 | Local Congestion |  |  |  | PIP120 | Wholesale |  | 6.7.1.2(10) | 2002-04-01 | Implementation with PIP120
PRR222 | New Definition of Market Solution |  |  |  | PIP120 | Wholesale |  | 2.1 | 2002-04-01 | Modify system to use the modified definition of market solution based on 3 resources that are not affiliated with each other submitting bids
PIP119 | OOME for Loads acting as Resources |  |  |  |  | Wholesale |  | 6.5.2(20) | 2002-04-01 | The calculation for OOME only takes instructions to generators into account. There is no provision for Loads acting as a Resource in the OOME market. Struck reference to Load acting as a Resource as providing OOME, and boxed future language for when service is available in the system.
PIP147 | Expiration times for bids | Complete |  |  |  | Wholesale | T. Doggett | 4.4.11 4.4.11(6) 4.4.16(8) 4.5.2(5) 4.5.3(5) | 2002-05-20 | System does not support expiration times for bids Language boxed referencing support of specifying bid expiration time until system is designed to support.
PIP148 | Removing a portion of AS bids | Complete |  |  |  | Wholesale | T. Doggett | 4.5.8 | 2002-05-20 | System does not allow portion of AS bids to be removed. References to this function have been boxed for when system does support. System Change: support retraction of portion of AS bids. No recognized workaround. Important for QSE to manage schedules.
PIP132 | Mismatched Schedules in RPRS Underscheduled Charge |  |  |  |  | Wholesale |  | 6.9.2.1.1 | 2002-05-20 | There is no design to implement the maximum mismatched schedule amount as part of this charge. Underscheduling can be a severe problem; it is important in assessing a cost that mismatched amounts are included. Option discussed of once implemented, making it a separate underschedule fee for reporting and tracking purposes. Formula modified to remove mismatch quantity reference, but boxed for future implementation.
PIP137/PRR211 | Association of BE Bids with RPRS | Complete |  |  |  | Wholesale | T. Doggett | 6.6.3.2.1(16) 4.1.1. Table 4.4.16(3) | Phase 2 | This concept was not included in the July 27, 2001 protocols and the system does not associate Balancing Energy bids with RPRS. When functionality added, add “and associated Balancing Energy bids to last sentence in QSE’s Submission for 1430 and add “and save RPRS energy bids for applicable balancing markets” in ERCOT Responsibility for by1630
PIP151/PRR287 | Responsibility Transfers/Dynamic Resource Transfers |  |  |  |  | Wholesale |  | 4.9.4 | ERCOT/vendor assessing date | Responsibility Transfers (RT) and establishment of Dynamic Resource Transfers (DRT). System does not support RTs as currently in the Protocols. No box in Protocols. DRT - QSE’s may use dynamic power signals to control generation to match a metered load or obligation.
PIP150 | Adjusted schedule notification | Complete |  |  |  | Wholesale | T. Doggett | 4.7.2(c ) 4.7.2(e) | On hold; need input from WMS | Current design does not provide a notification message to QSE as to the adjustment in its Schedule System Change: provide notification that mismatch was adjusted by ERCOT Workaround: Until fixed, QSE will monitor schedule status on the portal. P1 can send out sked amt. and notice that sked didn't change, but can not change sked. Need input from WMS.
STATUS:RED-Project Phase 3
PIP112 | Balancing Energy Up Load | Partial w/ 107 |  |  | PIP 107 PIP111 PIP210 PRR302 | Wholesale |  | 6.8.1.14.3 | Phase 3 | Not supported in current system design; System change required. Protocol language proposed and boxed until system supports design. Priority unchanged, however, ERCOT & Stakeholders expressed concern with accomplishing this by 01/01/02. Input required. Demand Side Task Force. Vendor has design issues, developing alternatives and timeline.
PIP210 | Partial Block Deployment | Complete |  |  | PIP112 | Wholesale | K. Gresham | 6.7.1.1 6.7.4 | Phase 3 | This is new language adopted by RUG (12/6/2000). Vendor assessing design issues, developing timeline.
STATUS:YELLOW; Project Phase 2b; ON HOLD FOR STAKEHOLDER INPUT
PIP156 | TTC and CSC forecasts | Complete |  |  |  | Wholesale | J. Bian | 4.4.2(2) 7.3.2.2 | Phase 3 | In Section 7.3.3.2, Tracking Balancing Energy CSC Cost, the definition of TTCcsc is changed from actual Total Transfer Capacity to annual Total Transfer Capability. This is supported by the system. Reference to forecast of Total Transfer Capability in 4.4.2(2) is neither calculated or posted by the system. System Change: Post load area forecasts. Need Input from WMS
STATUS YELLOW: NOT RELEASED TO VENDOR; Ordered by Legislature
| Competitive Metering |  |  |  |  | Retail |  |  |  | Sec. 39.107. METERING AND BILLING SERVICES. (a) Commercial & industrial customers: January 1, 2004. (b) Residential customers: later of September 1, 2005, or the date on which at least 40 percent of those residential customers are taking service from unaffiliated retail electric providers. Metering and billing services provided to residential customers shall be governed by the customer safeguards adopted by the commission under Section 39.101.
STATUS YELLOW: NOT RELEASED TO VENDOR; Ordered by PUCT (Docket No. 23220) & Need Stakeholder Input
| Two Settlement System |  |  |  | PRR295 | Wholesale |  |  | Ordered to be implemented by 6/1/2002 | Commission Ordered; assigned to PRS. J. Galvin working on requirements
| Simultaneous Procurement of AS |  |  |  |  | Wholesale |  |  | Phase 2 | Commission Ordered; assigned to WMS. WMS working with PUCT. WMS sent a white-paper to PUCT in Nov01 at the 10kft level; need to take to Protocol level.
| Intrazonal Direct Assignment |  |  |  |  | Wholesale |  |  | 2003-01-01 | Commission Ordered - issued April 11, 2001. Amend the Protocols to require direct assignment of intrazonal congestion mgmt. costs, through a usage fee that is based on the flow on the congested intrazonal interface.
| New Uninstructed Deviation Calculation |  |  |  |  | Wholesale |  |  | Phase 2 | Commission Ordered. Use second subsequent settlement interval expost MCPE for settlement of uninstructed deviation during the first settlement interval. assigned to WMS. Assigned to Demand WG by WMS.
| Single-round, Simultaneous, Combinatorial Auction for TCRs |  |  | 2003 |  | Wholesale |  | 7.5.3.2 |  | Commission Ordered in Docket No. 23220, 4/11/01. Amend the Protocols to provide for a simultaneous combinatorial auction (instead of a multiround auction) for selling TCRs. For 2002, a single round auction was put in place.
STATUS GREEN: NOT RELEASED TO VENDOR; Prioritized by Stakeholders
PRR247 | Ratcheting of OOME |  | High | 1 | PRR281 PRR282 | Wholesale |  | 6.8.2.2 | Remanded to WMS by TAC | On hold pending Stakeholder input. Under review by QSEWG.
PRR258 | Notification Automation if Permit Required |  | High- extremely need tomorrow | 1 |  | Retail |  | 15.1.1.2, 15.1.1.7, 15.1.1.7 | Version 1.5 [Original target 7/01/02] | Process needed to automate the notification for when a Permit is required. TDSP needs to notify the CR, so the CR can communicate this info to the customer. The TDSP will not energize the premise without a permit/inspection, therefore the customer (moving-in) will not have power until all city inspections are complete and returned to the TDSP. TDSPs have a large volume of permits and need to handle them in an automated fashion. 30k/month need permits.
PRR259 | Process Automation for Unexecutable Move-Ins |  | High, currently manual. Same as 258PRR. | 1 |  | Retail |  | 15.1.4.5 | Version 1.5 [Original target 7/01/02] | A process is needed to automate the notification for when a Move-in is unexecutable. The TDSP needs to notify the CR, so the CR can communicate the information to the customer. The TDSP will not energize the premise in certain “unexecutable” cases; therefore the customer (moving-in) will not have power until all repairs are complete. TDSPs need to handle unexecutables in an automated fashion.
PRR261 | CR Notification of Move In/Move Out Date Gap |  | High, same as 258PRR. | 1 |  | Retail |  | 15.1.5.7, 15.1.5.9 | Version 1.5 | A process is needed to notify a CR when move-in date changes have caused a gap between a customer who is moving into a premise and another customer who is moving out of the premise.
PRR281 | Change ERCOT Deployment Instructions to Settlement Meter Specific (Injection Point) |  | High | 1 | PRR282, PRR247 | Wholesale |  | numerous |  | Deployment instructions should be provided on a Settlement Meter basis and NOT on a unit or generator specific basis. Currently being discussed at the QSEWG/WMS.
PRR303 | Move-In Rejections |  | High, immediate implementation | 1 |  | Retail |  | 15.1.4.9 |  | The stacked move-in resolution modified the Not First In validation to allow a Move-In when another Move-In is pending, but only when the requested Move-In in later than the pending Move-In.
PRR310 | Estimating Usage Applied to Profiles |  | High | 1 |  | Retail |  | 11.3.2; 11.3.4.1 |  | Revise Protocol formulas to estimate usage when no actual meter read data is available for the day being estimated.
SCR700 | Date Changes on Move-Ins (TDSP Date Change Response/Change Requested Date) |  | High, immediate implementation | 1 |  | Retail |  |  | Phase 3 | The 814_13 will need a new segment to identify that the TDSP is responding to a date change request with a different date than requested. Approved by TAC on Oct. 01.
SCR701 | 814_05 to CR w/ Reject Status (Premise Info Rejects) |  | High, immediate implementation | 1 |  | Retail |  |  | Phase 3 | ERCOT forward to the CR, the 814_04 premise info reject by the TDSP. Approved by TAC in Oct. 01
SCR703 | ERCOT purge of Move-In when permit not received |  | High, immediate implementation | 1 |  | Retail |  |  | Phase 3 | The ERCOT system should purge a Move-in request if a permit is required but not obtained within a specified timeframe. Approved by TAC in Oct. 01
SCR704 | Stacked Move-Ins |  | High, immediate implementation | 1 |  | Retail |  |  | Phase 3 | Long-term solutions for stacked move-ins, and move-ins/move-outs with date changes. Approved by TAC in Oct. 01
SCR706 | Customer Information Segments |  | High | 1 |  | Retail |  |  | Phase 3 | Capture the customer name information from the 814_01 and 814_16 and pass the same on to the TDSPs via the 814_03. Approved by TAC on Mar. 07
PIP153 | Posting Congestion and Insufficiency Information | Complete | High | 2 |  | Wholesale | J. Bian | 4.4.9 | Phase 3 | No direct notification occurring as protocols directed, but information is being posted. Congestion notice - resolved; manual work around for capacity insufficiency. Posting requirement related to PIP134, PIP138 & PIP155.
PIP155 | Zonal forecast posting |  | High | 2 |  | Wholesale |  | 4.2.(1) | Phase 3 | ESCA clarification: "Load area forecast" will not be published. System Change: Post load area forecasts Language referencing load area forecast has been boxed until system supports publication. Posting requirement related to PIP134, PIP138 & PIP153.
PRR282 | Define OOME as an Instructed Deviation |  | High | 2 | PRR281, PRR247 | Wholesale |  |  |  | QSEWG developing Protocol language.
PRR316 | CR Cancel of Switch |  | High, immediate implementation | 2 |  | Retail |  |  | Phase 3 | A solution that will allow the CRs to cancel switches that they submitted.
PIP106 | Direct Load Control (DLC) | Complete | High | 3 | PIP175 | Wholesale & Retail | W. Reid | 18.7.2 6.3.2 18.2.10 18.2.1.(7) | Phase 3 | Currently there is not a profile for DLC and the system cannot currently support the use of this type of profile. All sections and comments related to DLC have been boxed in protocols and will be released when accomodated by the system. A long lead time has been identified as a factor to implementation.
PIP158 | Contents of Dispatch Instructions | Complete | Medium |  |  | Wholesale | T. Doggett | 5.4.2(1) | Phase 3 | System does not support all of the indicated contents of the systematic dispatch instruction. Language boxed for future implementation. Workaround: Provide verbal/faxed instructions; Buy more regulation; Implement voice recorders Interim Language: denote timestamp on Dispatch Instruction Are the boxed items still needed? If so, system impact is on P1 XML.
PIP188 | Forward of Meter Read Information within 4 hours |  | Medium |  |  | Retail |  | 15.1.2.8, 15.1.5.6, 15.1.4.8, 15.1.10 |  | D. Odle to review with RMS whether still needed. ERCOT system capacity review if still needed.
PIP204 | EPS Meter Data Transmittal | Complete | Medium |  | PRR283 | Wholesale/ Retail | J. Cohea | 10.2.3 10.3.2.1.6 | Remanded to RMS by TAC | New section on treatment of EPS Load Data was added, and necessary by June 1st to avoid workaround costs incurred by the TDSP. A new section was drafted with reference to making consumption data available to market participants of EPS meters boxed until system supports it. RUG reviewed and approved the changes as drafted. Boxed changes redistributed and accepted by ERCOT.
PRR260 | Auto Purge Process if Permit Not Received |  | Medium |  |  | Retail |  | 15.1.1.7, 15.1.4.5 | Version 1.5 [Original target 7/01/02] | Facilitates purging of Move-ins that require a permit, but the permit is not received by the TDSP. Purge if the transaction is stale.
PIP101 | POLR Historical Usage | Complete | Low |  |  | Retail | C. Moseley | 15.1.2.7 | Phase 3 | System was designed to send historical usage to POLR when customer sent to POLR. The change to be implemented is that ERCOT will act as the transaction point and will receive the historical data and then send it to POLR upon POLR request. Language boxed regarding usage directly to POLR until system change is implemented. Need RMS to determine whether this is still desired. Low priority RMS may submitt PRR to remove box & not require a system change.
PIP102 | Voltage Support Compensation | Complete | Low |  |  | Wholesale | V. Gates | 6.8.4 6.9.3(1) 6.1.7 6.5.8 | Phase 3 | System not designed to calculate compensation for voltage support.
PIP104 | Black Start | Complete | Low |  |  | Wholesale | B. Jones | 6.8.5 6.9.4.1 6.1.8 | Phase 3 | Current system design uses a simple capacity multiplied by a fee to determine payment. The protocol has a more complex formula which uses a rolling unit availability factor. No Change to Protocols. System Workaround required and supported by ERCOT. ERCOT may adjust the priority if necessary. Manual work around.
PIP134 | Messaging System Language Clarification | Complete | Low |  |  | Wholesale | T. Doggett | 6.4.2 | Phase 3 | Language clarification: information is posted by ERCOT, but not using the Messaging System. Language boxed for future system support. Question for WMS: should box be removed? Posting requirement related to PIP138, PIP153 & PIP155.
PIP138 | Posting BE Forecast |  | Low |  |  | Wholesale |  | 6.7.1.1(6) | Phase 3 | Not designed to be posted publically; reference to posting currently struck, but boxed for future implementation. In Sept. 2001, said this was no longer needed. Should the box be removed? Posting requirement related to PIP134, PIP153 & PIP155.
PIP207 | Capacity Insufficiency | Complete | Low |  |  | Wholesale | C. Moseley | 6.6.7.1, 6.8.1.1(2)(b), 6.8.1.3, 6.8.1.5, 6.8.1.9, | Phase 3 | System Change: Automate system to derive prices under capacity insufficency conditions in accordance with protocols Workaround: ERCOT staff creates derived prices manually
PRR272 | Add Distribution Zone to Data Query. |  | Low |  | PRR312 | Retail |  | 15.2 |  | Need the Distribution Zone (DZ) field to identify which power pool an ESI ID is located.
PRR307 | Controllable Resources |  | Low |  |  | Wholesale/ Retail |  | 2.1; 5.6.7; 6.1.2; 6.1.3; 6.1.4; 6.5.1.1; 6.5.2; 6.5.3; 6.5.4; 6.5.6; 6.7.3; 6.8.1.12; 6.10.4.4 |  | This Protocol revision defines Load which can provide Regulation Service. Pending PRS, TAC & Board approval. It is recognized that this issue should be addressed, however, it does not have to be implemented this fiscal year.
PRR311 | DLC to BUL Transition |  | Low |  |  | Wholesale/ Retail |  | 6.10.5.2; 6.10.2; 6.8.1.14 |  | Pending TAC & Board approval in March. The priority may increase in 2003.
PRR312 | Enhance ESI Look-up Function |  | Low |  | PRR272 | Retail |  | 15.2 |  | Pending TAC & Board approval in March.
SCR702 | Ad-hoc Usage Request Process Flow |  | Low |  |  | Retail |  |  | Phase 3 | Change the timing of the generation of the 814_27 response. Approved by TAC in Oct. 01.
PIP115 | Uncontrollable Resources (e.g wind) Deviations | Complete |  |  | PRR293 | Wholesale |  | 6.8.1.15 | On hold pending PRR293 | New wording has been added regarding treatment of deviations from uncontrollable renewable resources under section 6.8.1.15 (Uninstructed Deviations).
PIP128 | Synchronous Condenser Compensation | Complete |  |  |  | Wholesale | V. Gates | 6.8.3.2(4) 6.8.3.4(2) 6.8.3.6 6.9.4.3 | Phase 3 | No design for support of Sychronous Condenser Service. Language on payment and load uplift boxed until system supports; Reference to no compensation made in protocols. QSEWG re-evaluate need.
SCR705 | Remove Meter Request |  |  |  |  | Retail |  |  |  | Allows a CR to notify the TDSP that the customer is requesting removal of a meter at Move-Out time. [Ref: CC#2001-199] Approved by TAC for Prioritization, Mar 07
SCR707 | ERCOT Acceptance & Pass Thru of New Reject Codes |  |  |  |  | Retail |  |  |  | This change is required to support the Muni-Coop billing model. Approved by TAC for Prioritization, Mar. 07
SCR708 | Forward of Bill Type to POLR |  |  |  |  | Retail |  |  |  | Requires ERCOT to pass thru the REF~BLT billing type code that a customer has chosen to the POLR. Approved by TAC for Prioritization, Mar 07.
SCR709 | Reject for Invalid Bill Type |  |  |  |  | Retail |  |  |  | Allows ERCOT to reject either an 814_16 or 814_10 that does not contain a valid bill type. Approved by TAC for Prioritization, Mar 07.
SCR710 | ERCOT Rejects Move-In or Drop to POLR - Billing Code Not TX SET Compliant |  |  |  |  | Retail |  |  |  | Requires ERCOT to reject an 814_10, Drop to POLR or an 814_16, Move-In Request, if the billing type is not a valid TX SET code. Approved by TAC for Prioritization, Mar. 07.
SCR711 | Forwarding Address for Final Bill |  |  |  |  | Retail |  |  |  | Muni/Coops need a customer's forwarding address on an 814_24, Move-Out Request, in order to send a final bill. Approved by TAC for Prioritization, Mar. 07.
SCR712 | Pass Thru of New Reject Code |  |  |  |  | Retail |  |  |  | Added rejection code BIM for "Billing Information Missing." Allows MC-TDSP to reject the 814_24 if the forwarding billing info is not included. Approved by TAC for Prioritization, Mar. 07.
SCR713 | Customer Information |  |  |  |  | Retail |  |  |  | ERCOT to pass the PER segments from the 814_01, 814_10 & 814_16 to the TDSP in the 814_03. The PER will include the customer name and phone number. [Ref. CC#2002-257] Approved by TAC for Prioritization, Mar. 07.
SCR714 | Special Needs Indicator |  |  |  |  | Retail |  |  |  | The Special Needs Indicator is a pass thru field to Market Participants from ERCOT. [Ref: CC#2002-258] Approved for Prioritization, Mar. 07.