### MARKET TIMELINE SUPPORTING

### MARKET TESTING FLIGHT 0702

| Activity | Calendar Date |
| --- | --- |
| Notice from ERCOT Client Relations Mgr. of Market Testing Pre-orientation meeting to entire ERCOT mail container | May 7th - Tuesday |
| Notice from ERCOT Client Relations Mgr. of Market Testing Orientation meeting to entire ERCOT mail container | May 21st - Tuesday |
| TTPT to Finalize scripts | May 23rd – Thursday, TTPT meeting |
| Pre-Orientation Market Testing activities – informing each Testing CR as needed, of Testing activities and requirements | Not before May, 30th – Thursday |
| Orientation Market Testing activities – informing each Testing CR of Testing requirements as needed | Not later than June, 5th – Wednesday |
| CR must have filed for REP Certification by COB | June, 5th – Wednesday |
| TSW updated on web-site communicating intent to test in July Flight – This is the deadline to sign up for the Flight! | June 6th – Thursday |
| Communication from ERCOT Client Relations manager of Testing Participants to each TDSP | June 7th – Friday |
| Verification and communication from PUCT Staff that Testing Participants intending to test, have applied for REP Certification | June 7th - Friday |
| TCW to be communicated to each Testing Participant | June 10th – Monday |
| TDSPs and ERCOT complete communication of connectivity testing schedule to each Trading Partner | June 11th – Tuesday |
| Connectivity Testing kick-off call | June 12th – Wednesday |
| Connectivity Testing begins | June 13th - Thursday |
| Oncor and Centerpoint communicate Test bed load to TPs and ERCOT | June 24th - Monday |
| Flight Kick off conference call | July 3rd – Wednesday |
| Daily Conference calls begin – Frame 1 Transactions flow | July 8th – Monday |