## Sheet1
Competitive Metering Time Line
2002-07-01 | 2002-08-01 | 2002-09-01 |  | 2003-02-01 | 2003-05-01 |  | 2003-11-01 | 2004-01-01
Today | PUCT Rule | Start Workshops |  | Issue Bid | Sign Contract |  | Go Live | SB7 Date
Version 1.5 Time Line
2002-07-01 | 2002-08-01 |  | 2002-11-01 | 2003-02-01
Today | Complete |  | Implement | Potential
| Design Requirements |  | V1.5 | Fall Back
For V1.5
Proof of Concept Time Line
2002-07-01 |  | 2002-09-01 |  | 2003-02-01 |  | 2002-08-01
Today |  | Potentially |  | Finish Tx SET |  | Others
|  | Request RMS |  | Documentation |  | Implement
|  | Approval |  |  |  | Solution
Feld Group Projects Time Line
2002-07-01 | 2002-08-01 | 2002-09-01 |  | 2003-02-01
Today
Finish 30 | Finish 60 | Finish 90 |  | Finish 180
Day Projects | Day Projects | Day Projects |  | Day Projects