## Transactions
TDSP
Process | Subprocess | TNMP | AEP/third party | ONCOR | Reliant
To Change | 814_20 | 34000 | 19000 | 210493 | 425764
Inactive * |  | 0 | 0 | 0 | 0
Active |  | 34000 | 19000 | 210530 | 425764
Complete | 814_21 (WQ) | 33656 | 18856 | 210498 | 424821
Incomplete | 814_21 (U) | 344 | 144 | 32 | 943
% Complete |  | 98.99% | 99.24% | 99.98% | 99.78%
Validation | ERCOT Analysis Report | in process | in process | in process | in process
Status Details | as of 7/24 | need to resubmit 814_20 to improve accuracy percents | no update on transactions | Complete | 94,000 814_20s over the weekend, 18,000 were rejected
Status Details | as of 7/20 |  | updated numbers as of 7/20 |  | 60520 have been placed in the To_ERCOT/Transitional folder. Other LPID changes are on the server and available for processing by the storm team 1) Another group of approximately 25,000 ESIID lpid changes and 2) Changes for Weather Zone assignment affecting almost 6,000 ESI IDs.
Status Details | as of 7/18 |  |  | Updated the WG number, 6000 814_20s will be sent 7/18
Status Details | as of 7/10 |  | 2715 814_20s of 2911 of AEP is waiting on ERCOT transaction analysis sent by AEP on 7/10. | 7240 814_20s sent to ERCOT, 1700 were rejected, 2700 need good effective dates that need resubmitting. | At 7/9, 85000 (including the 19451) transactions being checked, 19451 are not in Reliant CIS system currently which need a manual 814_20 to ERCOT.
* The 814_20 is unable to be created automatically for an inactive account in some of the TDSP systems (Reliant, AEP).
** An ESI ID having no readings and therefore there is no prior read date to match hence the 814_20 will reject. (estimated less than 17,000)

## CriteriaSummary
Summary of criteria to begin Resettlements: | TDSP
| TNMP | AEP | ONCOR | Reliant
1. Sample 99% Accuracy for Initial Validation for Res. & Bus. Profiles by TDSP. | N | Y | Y | N
2. 99% of the 814_20s transactions from Initial validations correctly loaded into the ERCOT billing system. | Y | Y | Y | Y
3. 99% Zip Codes in the Decision Tree | Y | Y | Y | Y
4. 99% Zip to Weather Zone mapping | Y | Y | Y | Y
Legend: Y = meets criteria, N = does not meet criteria