## Consolidated Project Priorities
Reference Number= PMO PR#
Source= Legislative, PUCT, Market, or ERCOT project initiation
Priority= Priority recommendations set by PRS for Market initiatives and Steering Committee for Internal ERCOT Initiatives
Rank= Rank recommendation set by PRS for Market Initiatives and Steering Committee for Internal ERCOT Initiatives
Project Title= Short Description of Project
Outcomes= Business Objectives
Estimated Cost= Estimated ERCOT portion of project cost (1 - H=>$5M, 2 - MH= $3-5M, 3 - M= $1-3M, 4 - HL= $500K - $1M, 5 - L= <$500K)
Comments= Any additional supporting comments
Ref. No. | Source | Priority | Rank | Project Title | Outcomes | Est. Cost | Comments
PR-20129 | Market | 1.1 | 1 | Move In/Move Out Solution (Analysis) Includes: Removal of NFI errors and allows stacks External Reports and Extracts Cancellation of pending switches | The Move-in/Move-out process, as originally defined by the Texas Market, is not working as initially thought. This project is to try and identify the issues that are causing this process to fail and determine what is needed in order to fix problem. This effort must be done in stages; the first stage being an in-depth analysis of the Market scenarios that are failing and the development of detailed requirements in order to prepare an RFP. | 5 - L | Projects 20129 & 30002 should be ranked together.
PR-30002 | Market | 1.1 | 2 | Move In Move Out Enhancement | To provide a system and process changes necessary to support the final Move In Move Out Process as designed by the market. These changes may require architecture changes to support a 4 hour turn around requirement. | 4 - HL | Projects 20129 & 30002 should be ranked together.
PR-30003 | Market | 1.1 | 3 | Texas Set 1.5 2003 Additional Work | To complete 2002 Capital Project for Texas Set V1.5 | 5 - L
| PUCT | 1.1 | 4 | Amend POLR Process Part II | System Change to add a code for the services being requested segmented (LIN).
| Market | 1.1 | 5 | Lodestar Data Loading Improvements | Improve loading of usage data into the Lodestar system for Settlement.
PR-30004 | Market | 1.1 | 6 | Texas Set 1.6+ | To support system changes and market design changes for future Texas Set V1.6 and 1.7 expected in 2003 | 2 - MH
PR-30005 | PUCT | 1.2 | 7 | LAAR Implementation | To completely and successfully implement the Load Acting As Resource program in the ERCOT market. Currently, the Responsive Reserve Market for LaaR has been successfully launched in ERCOT. However, the LaaR participation in the following markets, Non-Spin Reserve Market, Replacement Reserve Market, Balancing Energy Market, and even Regulation Market, will need to be developed. With the successful implementation of this project the ERCOT power market will have a more developed load response program. | 5 - L
PR-20126 | Market | 1.2 | 8 | ERCOT Data Transparency_SCR720 | The ERCOT market design is zonal, both in terms of market and grid operations and are designed to operate and financially settle on a 15-minute interval basis, with QSEs having the opportunity to self-manage their zonal positions on a bilateral basis. The Net Zonal Energy and Actual Zonal Generation quantities (“QSE Data Requirements”) are key components of the 15-minute interval, bilateral, zonal market design that are necessary, and valuable, in maximizing the actual availability and efficient use of the ERCOT grid. | 5 - L
PR-30015 | Market | 1.2 | 9 | Improvement on BES Timing | To improve the Balancing Energy Market timing so that the market can be cleared with more accurate system information. By improving the Balancing Energy Market Clearing Timing, the balancing energy market performance will be improved and this can potentially minimize the ERCOT ancillary service requirements in achieving better social welfare. With the completion of this project, any potential price chasing activity can be minimized and the ERCOT balancing energy market performance is expected to be enhanced correspondingly. | 3 - M
PR-30012 | Market | 1.2 | 10 | Enhance BES & RPRS Market (Step I) | Enhance BES & RPRS Market. Cap Shadow Price. Avoid to deploy inefficient bids with high price for resolving congestion. In this step, the software is changed to have different Penalty Cost Factor for different CSCs. | 5 - L
PR-30011 | Market | 1.2 | 11 | Enhance BES & RPRS Market (Step II) | Enhance BES & RPRS Market. Cap Shadow Price. Avoid to deploy inefficient bids with high price for resolving congestion. In this step, the software is changed to use original shift factors for schedules and adjusted shift factors for bids. | 5 - L
PR-20124 | PUCT | 1.3 | 12 | Performance Measures Relating to Competitive Retail Electric Market_PUCT 24462 | Provide measurements on the Competitive Retail Market (e.g. # customers by class, category, CR, TDSP); Market Mechanics ( e.g. key transactions processed with/without error, measurements within/out of protocols); Customer Enrollments; Customer Billing Success Rates; and Customer Service. | 4 - HL
PR-30014 | PUCT | 1.3 | 13 | Load Research Sampling | Design load research samples and deploy sample meters in support of Load Profiling (per Protocols Section 18). According to Protocols Section 18, the cost of performing any load research for load profiling purposes is the responsibility of ERCOT. Additionally, business resources are required to perform the actual analysis and the reporting requirements defined in Protocols 18. | 3 - M | Load Research Sampling is subject to PUCT 25516 rulemaking
PR-30001 | ERCOT | 1.1 | 1 | Competitive Metering in 2004 | Modify ERCOT processes and Lodestar to support competitive metering before Jan 1, 2004 | 2 - MH | Would like more information regarding estimated cost inputs for TAC.
Subproject to PR-20111 PR-30047 | ERCOT | 1.1 | 2 | Hardening EDI Transaction Pipeline | Undertake a number of improvements in the EDI Process including implementing top items identified by SWAT team to improve application hardening, simplify EDI map maintainability/logic by dividing single 814 input map into multiple 814 maps per transaction type e.g. 814_01, 03 and others. | 3 - M
Subproject to PR-20111 PR-30048 | ERCOT | 1.1 | 2 | EDI Pipeline Performance | Identify/communicate current transaction volume, throughput, and bottlenecks. Assess current monitoring points, identify gaps, and address gaps. Identify and address single threading as recommended by Feld Group | 4 - HL
PR-30049 | ERCOT | 1.1 | 3 | Pkg 2 Disaster Recovery | Provide the ability to recover essential Package 2 databases and functionality to support billing and settlements within 48 hours of a disaster | 1 - H
PR-20125 | ERCOT | 1.1 | 4 | PR-20125 Dashboard | Provide Market visibility into the volumes, success rates, error rates, performance metrics, and GAPS on the transactions processed by ERCOT. | 5 - L
| ERCOT | 1.1 | 1 - HIGH High High | CSA Warranty Team Transition
PR-30044 | ERCOT | 1.1 | 5 | Stop Oscillation of Constraint Management | Eliminate oscillation of constraint management; eliminating NERC penalties which will accumulate when penalties implemented, preventing possible cascading outages and collapse of ERCOT if contingencies take place when overlimit | 5 - L
PR-30045 | ERCOT | 1.1 | 6 | Fix Alarm System | Make transmission alarm system work | 5 - L
PR-30050 | ERCOT | 1.1 | 7 | EMS Front End Replacement | Replace the RTU frond end equipment (TFEs and CFEs) with Windows based servers (aka SMPs) CFE parts are no longer manufactured, and spare parts supply will be exhausted by the end of 2003. This will keep us current with ESCA's product roadmap. | 5 - L
PR-20134 | ERCOT | 1.1 | 8 | CSA Re-architect Development Environment |  | 5 - L
PR-20117 | ERCOT | 1.1 | 9 | Internal Testing and Verification | Build a regression testing library of mock transactions and test scripts to ensure that any fix, SIR or other manipulation of the PaperFree maps produce the desired results. | 5 - L
PR-30051 | ERCOT | 1.1 | 10 | Database Reorganization Tool | Provide ERCOT DBAs the ability to perform database reorganization online with minimum down-time to application and business operations | 4 - HL
PR-30006 | ERCOT | 1.1 | 11 | Acquire/Integrate OSISoft PI Software | Provide timely analyses and reports to ERCOT Operations, Compliance and Market Participant Stakeholder Groups and be in compliance with NERC Planning Standards and Operating Policies, as required by the ERCOT Agreement with NERC. Also, provide a test bed for new measurements of ERCOT and market participant performance. Provide reports required by the ERCOT Protocols and Operating Guides | 5 - L
PR-30041 | ERCOT | 1.1 | 12 | DC Tie Modeling | Develop a new DC injection model so that DC ties are modeled correctly for every EMP function, including AGC, SCADA, RTNET and STNET. | 5 - L
PR-30053 | ERCOT | 1.2 | 13 | BE Mismatch Schedules Automation | Automate and fill in the gaps to the process that performs the mismatch adjustments according to protocol that is currently a settlement manual workaround | 5 - L
PR-30043 | ERCOT | 1.2 | 14 | MOI Printing Functions | Develop the functionality to allow print from MOI displays | 5 - L
PR-30056 | ERCOT | 1.2 | 15 | Outage Sensitive Factor (OSF) | The Outage Coordinators study many cases with lots of contingencies and need a faster tool to assess the impact of the outages on the contingencies. This was originally submitted as a OTDF change but it was determined that modifying the OTDF would not satisfy our requirements. By maintaining a reliable system, the Market Participants are provided a stable marketplace. This will reduce the risk and uncertainty of the market. | 5 - L
PR-30093 | ERCOT | 1.2 | 16 | RPRS Market Re-design | Enhance the effectiveness of RPRS market. Current RPRS market can not always provide most economic solution because it consider every hour independently. A new method called constrained unit commitment method can be used to enhance the effectiveness of RPRS market. | 3 - M
PR-30059 | ERCOT | 1.3 | 17 | Alarm Change Resource Plan | Stop repeated shortage of units to control line overloading due to QSE's changing resource plans without ERCOT's noticing. | 5 - L
PR-30054 | ERCOT | 1.3 | 18 | ETS Phase 2 | Expand ESIID Tracking System capability to allow web interface for market participants. Improve visibility and problem resolution for CRs and TDSPs. This is a continuation of the original ETS project. | 3 - M
PR-30008 | Market | 1.3 | 19 | Load Profiling Software | Enhance load profiling software to improve user capabilities and enhance reporting abilities | 5 - L
PR-30060 | ERCOT | 1.3 | 20 | Security Constraint PF | Method to develop Generator Requirements for outages-and develop generator solutions for contingencies. Outage Coordinators do not have a way to determine Generator solutions for contingencies. This will greatly enhance the reliability of the system | 5 - L
PR-30069 | ERCOT | 1.3 | 21 | OVPI Evaluation | Evaluate OVPI as a reporting tool, paying special attention to this product's ability to provide insight into the performance and capacity of network components. | 5 - L
PR-30070 | ERCOT | 1.3 | 22 | OVPI Implementation | Implement OpenView Performance Insight (OVPI) as a reporting tool for network statistics, later extending the tool to cover other aspects of the network and services. | 5 - L
PR-30065 | ERCOT | 1.3 | 23 | EMS Network Upgrade | This project will upgrade the network for MOS and POS to gigabit performance. Network performance is having an impact on both the MOS market solutions and the POS data collection. By increasing the network speed, both of these functions will speed up and will not be subjected to performance issues during high activity periods. | 5 - L
PR-30057 | ERCOT | 1.3 | 24 | Deployment of Remote Production Support Systems | To provide a PC and associated peripherals to ERCOT employees who support production systems from home. ERCOT employees are currently using PC's they purchased or that ERCOT has purchased to access critical EMS, Commercial Operations or Data Warehouse servers from home. These systems are not protected by a centralized anti-virus, firewall or intrusion detection system. Auditors and security consultants have identified this as a high risk to having an extended interruption to ERCOT operations and a negative impact to the energy market. | 4 - HL
PR-30061 | ERCOT | 1.3 | 25 | Enterprise Security Management | Increase the detection capabilities of our networks. This solution will allow us to collect information and correlate events. | 4 - HL
PR-20121 | ERCOT | 1.3 |  | Unapproved Enhancement SIRs (19 identified by SWAT Tm) | Project to address SIRs identified by the Retail SWAT teams that deal with revised system requirements and market gaps. | 4 - HL
PR-30062 | ERCOT | 1.3 |  | Security Plan Implementation | Document security state of systems | 5 - L
PR-30010 | PUCT | 2.1 | 14 | Relaxed Balanced Schedule | Implement the relaxed balanced energy schedule in the ERCOT market. Since the current balancing energy market is designed to be an ancillary service market and it is used to maintain the system reliability, the relaxed balanced schedule may introduce a spot energy market in ERCOT. If the current balancing energy market can not satisfy this requirement from the operational perspective, a brand new spot energy market may need to be designed. The successful completion of this project will provide a solid recommendation, from the market design perspective, of the relaxed balanced schedule implementation in the ERCOT market. | 5 - L
PR-30032 | Market | 2.1 | 15 | Voltage Support Compensation_PIP102 | System not designed to calculate compensation for voltage support.
PR-20123 | Market | 2.1 | 16 | Direct Load Control_PIP106 | Protocols Section 18.7, Supplemental Load Profiling addresses the need for Load Profiles that accommodate pricing schemes that encourage a demand response to price in the retail market. Currently there is not a profile for DLC and the system cannot currently support the use of this type of profile. | 3 - M | Estimated that a year is required to implement. The Load Profiling Working Group is working on defining the requirements for this.
PR-30022 | Market | 2.1 | 17 | UFE Analysis Metering | To attain compliance with Protocol Section 11.5 - Unaccounted For Energy Analysis. According to Protocols Section 11.5.2.1 The cost of installing any metering solely for UFE analysis purposes will be recovered through the ERCOT System Administration Fee. Additionally, business resources are required to support the working group oversight the actual analysis, and the reporting requirements defined in Protocols 11.5. | 3 - M
| Market | 2.1 | 18 | Proxy Day Determination Extension [PRR352] | Changes the Non-Weather Sensitive (NWSIDR) Proxy Day determination method to use the most recent historical ESI-ID interval data from the last 12 months. | 5 - L
PR-30016 | Market | 2.1 | 19 | Dynamic Ratings | Several of ERCOT's TO's have implemented, or are about to implement, dynamic line rating as a function of ambient temperature or other factors. ERCOT must implement this same methodology to avoid unnecessary costs. | 5 - L
PR-30009 | Market | 2.1 | 20 | Define VDI as Instructed Deviation | Define VDI as Instructed Deviation so that ERCOT frequency performance can better meet the NERC Operational Criteria. Currently, the ERCOT verbal dispatch instruction are not considered as instructed deviation. With implementation of this project, VDIs will be defined as instructed deviation. | 3 - M
PR-20072 | PUCT | 2.1 | 21 | New Uninstructed Deviation Calculation (funded '02) | Required by the Comm. Order in Docket No. 23220. Interim fix currently in place. | 5 - L
PR-20130 | Market | 2.1 | 22 | Association of BE Bids with RPRS_PIP137/PRR211 | The system does not associate Balancing Energy bids with RPRS. When functionality added, add “and associated Balancing Energy bids to last sentence in QSE’s Submission for 1430 and add “and save RPRS energy bids for applicable balancing markets” in ERCOT Responsibility for by1800. Need more input from stakeholders. | 5 - L
PR-30018 | Market | 2.1 | 23 | RT Market Ramp Rate [PRR349] | To improve the ERCOT real time market ramp rate formulation so that the balancing energy deployment can consider the QSEs' actual ramp capability. This project will improve the ERCOT frequency control performance and help ERCOT in achieving the NERC CPS1 criteria. | 4 - HL
PR-30013 | Market | 2.1 | 24 | AS Mismatched Schedules | Ensure that ERCOT operation system follows Protocols. Relieve manual workload. Currently, ERCOT system does not consider the factor of mismatched AS schedules when calculating AS self-arrangement value. Settlement staff need to manually correct QSE's AS self-arrangement when there are mismatched schedules between QSEs. | 5 - L
PR-30023 | Market | 2.2 | 25 | Enhance ESI ID Lookup_PRR312 | Adds Station ID, Power Region, Premise Type and Status (active/de-energized/inactive) field to ESI ID Look-up function. | 5 - L
PR-20128 | Market | 2.2 | 26 | Publish Zonal Deployments_SCR722 | Real-Time Portal Posting and XML query capability of Aggregate zonal unit-specific incremental and decremental deployments, separately stated, each by category, including aggregate OOM deployments. | 5 - L
PR-20127 | Market | 2.2 | 27 | XML Data for QSEs_SCR721 | QSEs desire increased transparency of ERCOT operations and, accordingly, the timely availability of real-time operating data without having to browse or scrape the ERCOT system. ERCOT computer system performance is suffering from this current lack of XML enabled data interface. | 5 - L
PR-30025 | Market | 2.2 | 28 | Modify A/S Performance and Freq Cntrl Algorithms | Assuming Protocol changes will direct the change, the new measure will improve performance monitoring, and lead to more accountability for QSE’s in deployment of A/S. It may also provide a means to migrate towards direct assignment of A/S costs, should ERCOT stakeholders chose to move the market in that direction. | 5 - L
PR-30007 | Market | 2.3 | 29 | Implement GISB 1.6 Transport - SCR717 | Implement the transport protocol defined by GISB 1.6 to allow large market participants a single, secure transport method | 5 - L
PR-30083 | ERCOT | 2.1 | 26 | Lodestar Upgrade | Complete an architectural review of Lodestar and upgrade to new version. | 3 - M
PR-30058 | ERCOT | 2.1 | 27 | Siebel 7.0 Upgrade | Upgrade to a more current and fully supported version of ERCOT's Siebel registration system. Siebel 7.0 has new web browser capabilities and improved functionality that ERCOT can use to meet market expectations for visibility into our systems. | 3 - M
PR-30063 | ERCOT | 2.1 | 28 | Lawson Software Upgrade | Lawson will no longer support current version. Must upgrade to retain support. Upgrade Lawson Environment to 8.0.1_ESP2 Upgrade Lawson Application to 8.0.3 | 5 - L
PR-30064 | ERCOT | 2.1 | 29 | Pkg 2 Development Systems | Required for ERCOT to own development environment that allows clean code fixes and migrations into production. Current development environments do not allow reliable coding or testing results. | 3 - M
PR-20107 | ERCOT | 2.1 |  | Citrix Analysis (O&M) | Analyze current CITRIX environments to identify required configuration and migration path. | 5 - L $76K
PR-20105 | ERCOT | 2.1 |  | Network Placement Editor | A tool (once referred to as the French tool now referred to as NPE, Network Placement Editor) that would link the network and scada one line displays to the network model database. This tool was to be included in the original one line conversion from Siemens Power Visuals one-line displays to ESCA Rapport Full Graphics one-line displays, but it was not complete at the time. | 5 - L $18,590
PR-20113 | ERCOT | 2.1 |  | Help Desk Call Recording System (50K Funded) | Purchase and install a recording system to record Help Desk calls. | 5 - L $50K
PR-20116 | ERCOT | 2.1 |  | Outage Coordinator Metrics Eval Rpt | Monitor daily Approved, Rejected, Forced & Withdrawn outages entered in the 4 time ranges in the outage scheduler. Calculate average number of outages Approved, Rejected, Forced & Withdrawn daily. Calculate percentage approved in the correct time range. Create Monthly report. See attachment. Print monthly report to intranet site.
PR-20119 | ERCOT | 2.1 |  | 814_04 Report Enhancement | The current reports help with transaction gaps, they currently report 814_04 rejects back to the TDSP. We want to also give this information to the CR and show the reason and add the ERCOT rejections as well. This will allow the CR to reconcile any missing responses to Switch, Move-in or Move-outs. | 5 - L $16,087.50
PR-20120 | ERCOT | 2.1 |  | TA1 Modification | Best practices for EDI transactions: send and receive one transaction type per ISA. A few market participants are sending both 814s and 867s in the same ISA. This is allowed in ANSI standard but based on our architecture and transaction volume we would prefer them separated. The market has agreed to make the changes, but we still get these intermittently. | 5 - L $28,600
PR-2007301 | ERCOT | 2.1 |  | Incorporate TCR Billing and Credits into Settlements Invoices | Integrate TCR Credit payments and auction invoicing into the Settlements invoicing process, making it all one process | No Est
PR-30066 | ERCOT | 2.1 | 30 | DA/DW Redundancy | This project is to allow for timely disaster recovery of the Data Archive and Data Warehouse in the event of a disaster at the Taylor computing facility. It is primarily a hardware purchase. | 5 - L
PR-30046 | ERCOT | 2.1 |  | Hardening Systems | Bring all our systems to a secure state and allow ERCOT to apply hardening standards required by SAS70 Audit. | 3 - M
PR-30052 | ERCOT | 2.1 |  | Portal Redesign | Redesign/Rearchitect the Portal and its interfaces to ERCOT systems. The current commercial and retail portal is not meeting market needs or expectations for reliability. | 3 - M
PR-30067 | ERCOT | 2.1 |  | BES Deployment Dependency on Resource Pln | To relax the ERCOT balancing energy deployment dependency on Resource Plan and the current SCADA information will be used in balancing energy deployment. Since the Resource Plan is operational non-binding and SCADA is more up-to-date, this project will improve the ERCOT market operational reliability considering that some participants may experience difficulty in updating their Resource Plans to reflect the actual operational status under certain conditions. The successful implementation of this project will improve the ERCOT system reliability. | 4 - HL
PR-30068 | ERCOT | 2.1 |  | Display Print Resource Plan | Provide methodology for Day Ahead operator to see the generation pattern of the QSE's proposed resource plan and identify needed units. Provide method of providing resource plan to TO's. Allow Operator in Adjustment period to see what is planned. | 5 - L
PR-30071 | ERCOT | 2.1 |  | Database Monitoring Tool | Provide ERCOT DBAs the ability to monitor databases operation supporting FTP Message Broker, Price to Beat, Texas 1.5 and ETS systems. | 5 - L
PR-30072 | ERCOT | 2.2 |  | Balancing Schedule Dependency on Resource Pln | Currently balancing energy schedule is being modified by the actual capability reflected in the Resource Plan submitted by the participants. Since Resource Plan is operational non-binding and schedule is operational binding, the market and the system reliability will be improved by using the actual energy schedule from those participants who has physical resources to support their schedule activity. | 4 - HL
PR-30073 | ERCOT | 2.2 |  | Automate AS Qualification Testing | Add automation to the existing process of providing Ancillary Service Qualification testing. | 5 - L
PR-30074 | ERCOT | 2.2 |  | Enhance STNET to run multiple selected Time Ranges | STNET needs to link with Outage Scheduler and run selected multi-hour/day studies in a batch mode status. | 5 - L
PR-30075 | ERCOT | 2.2 |  | Outage Scheduler Enhancements | Supply Better information on outages to the Market ,ERCOT Operations and PUC. 1 . Add version Tracking for Resource and Transmission Outages 2. Add "actual Start" and "actual end" to outages. 3. Develop a Electronic version of the Forced/Level1 outage form. 4. Add new request types : "Forced Extension", "Equipment Status Change" | 5 - L
PR-30076 | ERCOT | 2.2 |  | Perimeter Antivirus | This project will prevent viruses from reaching our network by catching them at the perimeter of our networks. | 5 - L
PR-30077 | ERCOT | 2.2 |  | Honeypot System | This system will allow us to route potential network attacks to a dummy system. | 5 - L
PR-30078 | ERCOT | 2.2 |  | OVOw Evaluation | Evaluate HP OpenView Operations for Windows 7 as a service level management tool, paying close attention to the service navigator and distributed performance smart plug-in's (SPIs). | 5 - L
PR-30079 | ERCOT | 2.2 |  | OVOw Implementation | Implement OpenView Operations for Windows 7 as the "single pane of glass" that provides a window into managing our network as a collection of services. | 5 - L
PR-30080 | ERCOT | 2.2 |  | DNS for Participant Site Failovers | ERCOT has a means by which to fail over to a different site if systems become inoperable at one site or another. This project will give market participants this ability to perform site failovers without manual intervention on ERCOT's part to facilitate this move. | 5 - L
PR-30081 | ERCOT | 2.2 |  | Tape Backup | Tape backup is needed for obvious reasons. We need to be able to recover from a server failure in a minimum amount of time. If the RSA and RADIUS/TACACS servers were to fail, all VPN authentications would fail. If the Syslog and CiscoWorks servers were to fail, the Network group will be incapable of monitoring events that occur with regard to equipment failure, Network attacks, etc... The tape backup would minimize the downtime needed to rebuild the key servers that drive our Network. | 5 - L
PR-30082 | ERCOT | 2.2 |  | SeeBeyond Upgrade | Complete an architectural review of TCH / Seebeyond and upgrade to new version if we do not replace. | 3 - M
PR-30084 | ERCOT | 2.3 |  | CSC Limit Calculations/Posting | To automatically calculate daily CSC limits and post them on the web | 5 - L
PR-30085 | ERCOT | 2.3 |  | Allow SPS Modeling in Contingency Analysis | Allow operations to separate contingency overloads which require attention from contingency overloads which will be controlled by special protection schemes | 5 - L
PR-30086 | ERCOT | 2.3 |  | Frequency Performance Metric Report | To measure the performance of the Operations department and employees on their control of regulation and balancing energy deployment. To act as a yardstick to measure improvements | 5 - L
PR-30087 | ERCOT | 2.3 |  | RMC Redundancy | To provide the market participants with a fully redundant report server, and minimize overall unavailability of report explorer and the package 2 API | 5 - L
PR-30088 | ERCOT | 2.3 |  | Change Pearl Scripts to all 2 Finals/2 Trueups | The completion of this project will allow the batch to process 2 finals and 2 trueups with each batch. Experience indicates that quite often settlements has a need to run more than one final and one trueup with each batch. The current configuration does not allow that to occur. | 5 - L
PR-30089 | ERCOT | 2.3 |  | EMS e-Terra Archive IU | This project will move the e-Terra Archive (a.k.a. ETA or HIS) user interface to dedicated servers. Currently, the ETA and DSA functionalities are sharing the same servers. The potential exists that a non-critical function (DSA) could impair a critical function (ETA). | 5 - L
PR-30090 | ERCOT | 2.3 |  | DBA Reporting Tool | Provide ERCOT DBAs the ability to generate database trending Reports | 5 - L
PR-30091 | ERCOT | 2.3 |  | ercot.com and TCR Redundancy | To provide the market participants and general public a redundant environment with a near 24 hour uptime for ercot.com and TCR. | 5 - L
PR-30027 | Market | 3.1 | 30 | Data Extract Shadow System | Create a system within ERCOT where we can emulate the process used by market participants to load data extracts and use the information to verify the accuracy of ERCOT settlement statements and other reporting. Estimate includes 1 person for 1 year to support the system and act as an interface with the Client Service Representatives. | 5 - L
PR-30103 | Market | 3.2 |  | TCR Settlement Synchronization | TCR Credit payments from daily congestion costs need to be integrated into the Settlements invoicing process | 5 - L
PR-30028 | Market | 3.2 |  | Overload Reports | Be able to report to the ROS and PUCT the overload's that have taken place over a given period. Be able to track our performance in this respect and identify corrective actions to remedy these conditions. | 5 - L
PR-30029 | Market | 3.2 |  | Overlimit Reports (O&M) | Be able to report to the ROS and PUCT the overlimit conditions that have taken place over a given period. Be able to track our performance in this respect and identify corrective actions to remedy these conditions. Meet NERC requirements
PR-30026 | Market | 3.3 |  | EPS Meter Data Transmittal via extract_PIP204/PRR283 | New section on treatment of EPS Load Data was added. A new section was drafted with reference to making consumption data available to market participants of EPS meters. Boxed until system supports it. | 5 - L
No PR | Market | 3.3 |  | Fix Retail XML Transaction Format to MPs | Make outward facing XML more consistent with standards across the country. (Only 2 participants currently using XML.)
PR-20122 | Market | 3.3 |  | Unit Resource Testing_PRR332 | PRR 332 requires that ERCOT allow units under test to take priority over other units in constraint management. (i.e. be omitted from constraint management). When SFT is functional this will not be possible, because SFT automatically includes ALL resources in its analysis. Make changes to Market Database, Market User Interface, and SPD to ensure that units under test are not moved through balancing instructions. | 5 - L
PR-30030 | Market | 3.3 |  | PDC Report | ERCOT is required by protocols to analyze and report on resource response to events to the performance, Disturbance Compliance Taskforce. Provide functionality to meet this requirement. | 5 - L
PR-30031 | Market | 3.3 |  | POLR Historical Usage_PIP101 | System was designed to send historical usage to POLR when customer sent to POLR. The change to be implemented is that ERCOT will act as the transaction point and will receive the historical data and then send it to POLR upon POLR request. Language boxed regarding usage directly to POLR until system change is implemented. Need RMS to determine whether this is still desired. Low priority RMS may submit PRR to remove box & not require a system change. |  | SCR to be submitted.
PR-30034 | Market | 3.3 |  | Synchronous Condenser Compensation_PIP128 | No design for support of Sychronous Condenser Service. Language on payment and load uplift boxed until system supports; Reference to no compensation made in protocols. QSEWG needs to re-evaluate need.
PR-30035 | Market | 3.3 |  | Messaging System Language Clarification_PIP134 | Language clarification: information is posted by ERCOT, but not using the Messaging System. Language boxed for future system support. Question for WMS: should box be removed? Posting requirement related to PIP138, PIP153 & PIP155.
PR-30036 | Market | 3.3 |  | Posting BE Forecast_PIP138 | Not designed to be posted publicly; reference to posting currently struck, but boxed for future implementation. In Sept. 2001, said this was no longer needed. Should the box be removed? Posting requirement related to PIP134, PIP153 & PIP155.
PR-30037 | Market | 3.3 |  | Contents of Dispatch Instructions_PIP158 | System does not support all of the indicated contents of the systematic dispatch instruction. Language boxed for future implementation. Workaround: Provide verbal/faxed instructions; Buy more regulation; Implement voice recorders Interim Language: denote timestamp on Dispatch Instruction Discussed need for this w/QSEWG in Aug. '02. Consensus was Low Priority. System impact is on P1 XML.
PR-30038 | Market | 3.3 |  | Forward of Meter Read Information within 4 hrs_PIP188 | Boxed language that requires meter read data received by ERCOT prior to midnight to be forwarded to CRs by 0400 the next day, and meter read data received by ERCOT between midnight and 0600 be forwarded to CR by noon the same day..
PR-30039 | Market | 3.3 |  | Controllable Resources_PRR307 | This Protocol revision defines Load which can provide Regulation Service.
PR-30040 | Market | 3.3 |  | DLC to BUL Transition (requires BUL/DLC completed)_PRR311 | Direct Load Control for BULs.
| Market | 3.3 |  | BLT OOME [PRR355] | Modify Protocols to provide for payment when Block Load Transfers provide OOME
PR-30021 | ERCOT | 3.1 |  | Replace DSM6 and VGR Freq Recorders | Provide data for timely analyses and reports following disturbances to ERCOT Operations, Compliance and Market Participant Stakeholder Groups and be in compliance with NERC Operating Policies. | 5 - L
PR-30092 | ERCOT | 3.1 |  | ERCOT Market Structure Study | To have a complete evaluation of the current ERCOT market structure and generate one consolidated ERCOT market status report which can be used as the guidance for ERCOT, PUCT and stakeholders in future market Re-design process. This study will include: a.) ERCOT frequency control performance evaluation and suggestions. b.) ERCOT congestion management performance evaluation and suggestions. c.) The inter-relationship between the ERCOT centralized ancillary service markets and the bilateral markets between the participants. d.) Evaluation the merits and shortcomings between the ERCOT zonal, portfolio model and any proposed nodal model. e.) Evaluation of the proposals to minimize the ERCOT socialized market cost. Other related market topics can also be included in the study scope and one consolidated recommendations will be provided to support any further ERCOT market evolution activity. | 4 - HL
PR-30094 | ERCOT | 3.1 |  | VSAT/TSAT Interface Upgrade | To upgrade VSAT/TSAT's DCP interface in EMP so that operators would have a better view of results. | 5 - L
PR-30095 | ERCOT | 3.1 |  | System Map | Provide a way for the system operators to see the prevailing power flows across the state. | 5 - L
PR-30096 | ERCOT | 3.1 |  | ESCA to PTI Download | Base case data is dumped from the ESCA system in PSSE/PTI format. It is necessary to translate from a breaker model to a bus model when making this download. Stakeholders use this data to review study cases and to compare the ERCOT data to their own database. ERCOT uses the PSSE/PTI case to transfer data from the ESCA model to other application software packages such as the Voltage Stability package. | 5 - L
PR-30097 | ERCOT | 3.1 |  | Display Coming Schedule Changes | Currently there is no quick way for operators to observe large schedule changes approaching between QSE's and Zones. Such a vision of what is coming is needed to take pro-active measures to prevent loading problems. Example - Dallas area auto loading | 5 - L
PR-30098 | ERCOT | 3.1 |  | Provide Display for Gen Output/Limits/Monitored Pts | Replace the operator designed spreadsheet now being used by operations with a display or functionality which is supported by the IT department. | 5 - L
PR-30099 | ERCOT | 3.1 |  | Taylor Office Complex | Construct 40,000 sq/ft facility in order to provide necessary work space for ERCOT's existing workforce and future expansion. | 1 - H
PR-30100 | ERCOT | 3.1 |  | OVPD/NDAOM Evaluation | Evaluate OpenView Performance Diagnosis and Network Diagnostic Add-on Module for their effectiveness at understanding the network connections between any two network components. | 5 - L
PR-30101 | ERCOT | 3.1 |  | OVPD/NDAOM Implementation | Implement OpenView Performance Diagnosis and Network Diagnosis with the goal of understanding performance of the network connections between any two network components. | 5 - L
PR-30102 | ERCOT | 3.1 |  | NICE Playback System | Provide Operations, Help Desk and Client Representatives the ability to playback audio recordings without stopping the audio recording/archiving process. | 5 - L
PR-30008 | ERCOT | 3.1 |  | Load Profiling Software | Enhance load profiling software to improve user capabilities and enhance reporting abilities | 5 - L
PR-30104 | ERCOT | 3.2 |  | STLF and BES Offset Reports | Track STLF and BES Offset calculations for Operations Performance Measurement. Currently there is no mechanism to measure how accurate STLF and Offset values are. | 5 - L
PR-30105 | ERCOT | 3.2 |  | Congestion Management Reports | To verify validity of BES deployment for zonal congestion management. Currently there is no data/report to measure how well congestions are managed for operations performance metrics. | 5 - L
PR-30106 | ERCOT | 3.2 |  | Display PF and SCADA on Single One Line | To allow debugging of network tools. Currently identifying the differences between a power flow case and SCADA requires a laborious switching back an forth between displays | 5 - L
PR-30107 | ERCOT | 3.2 |  | IDS Load Balancer | Increasing the performance of our Network Intrusion Detection Systems. | 5 - L
PR-30108 | ERCOT | 3.2 |  | OVIS/OVWTO Evaluation | OpenView Internet Services and Web Transaction Observer can provide objective, repeatable measurements of web-based transaction performance, yielding insight into the user's experience. | 5 - L
PR-30109 | ERCOT | 3.2 |  | OVIS/OVWTO Implementation | Implement OpenView Internet Services and Web Transaction Observer with the goal of understanding user level experience for web-based requests. | 5 - L
PR-30110 | ERCOT | 3.2 |  | Replace TCH | TCH Architecture and Seebeyond product implementation have been an ongoing stability and reliability problem for ERCOT. Project is to consider re architecting or replacing the current software. | 1 - H
PR-30111 | ERCOT | 3.3 |  | Balancing Energy AS Provider Performance Rpt | To provide the AS performance report required by protocol | 5 - L
PR-30112 | ERCOT | 3.3 |  | SunRay | This is a proof of concept project where we will show a more secure desktop solution that will require less support. | 5 - L
PR-30113 | ERCOT | 3.3 |  | Telewall | This system is essentially a firewall for our PBX system. | 5 - L
PR-30114 | ERCOT | 3.3 |  | Tripwire | This application will allow us to analyze the integrity of our systems. | 5 - L
PR-30115 | ERCOT | 3.3 |  | Network Sensor Install | Increase the security detection capabilities of networks. | 5 - L
PR-30116 | ERCOT | 3.3 |  | Austin Computer Room Expansion | Expand existing Austin Computer Room in order to provide additional 500sq/ft for installation of required systems. | 5 - L
PR-30117 | ERCOT | 3.3 |  | OVWTA Evaluation | Evaluate OpenView Web Transaction Analyzer as a facility that can track the specific components of a transaction as that transaction is processed by servers. | 5 - L
PR-30118 | ERCOT | 3.3 |  | OVWTA Implementation | Implement OpenView Web Transaction Analyzer as a facility that can track the specific components of a transaction as that transaction is processed by servers. | 5 - L
PR-30119 | ERCOT | 3.3 |  | High Availability Comm Apps | To upgrade and provide failover / resource sharing capability for Commercial Applications. This proposal is based on a study done by ERCOT and HP looking at replacing all current UNIX servers with latest model with load balancing in Taylor and upgraded failover in Austin. | 1 - H
PR-30120 | ERCOT | 3.3 |  | MOStoBE Data Recovery | Recover data for MOStoBE from Package 3.
PR-30121 | ERCOT | 3.3 |  | SIR on HEAT (Consolidated tracking tool) | This project will cover automating and creating synergy for several disparate IT processes at ERCOT. Examples of these process: SIR, SPR, CCM, Help Desk Tickets, Fast Track, PMO work flows and SCR. | 5 - L
PR-30122 | ERCOT | 3.3 |  | ESCA Web Internet Only Servers | This project will establish a division between the WAN and Internet for all Whole Sale Operations. Two Servers will remain on the WAN, Two new servers will be on the internet only. This is for each ERCOT location. | 5 - L
PR-30123 | ERCOT | 3.3 |  | Training Registration Application Upgrade | While the development of the original Training Registration application resulted in a good, basic application, use by ERCOT and Market Participant personnel has revealed the need for new functions and for improving some existing functions. | 5 - L
PR-30017 | Market |  |  | Market Solution in Zonal BES Market | Define Market Solution concept in ERCOT Zonal BES Market. Whenever there is no Market Solution, the BES bid price shall be capped by a standard price. | 5 - L | PRS recommended deleting this project.
PR-30019 | Market |  |  | Market Solution in AS Market | Define Market Solution concept in AS Market. Whenever there is no Market Solution, the AS bid price shall be capped by a standard price. | 5 - L | PRS recommended deleting this project.
PR-30020 | Market |  |  | Modify OOM tool to allow fleet deployments | Allow fleet deployment of QSE resources to control congestion in a timely manner without issuing VDI. | 5 - L | PRS recommended deleting this project.