## Pending LPwork
Subject | Status | Word doc/cross ref | Pending Items | Priority | Responsible party
LPG |  | 1 | LPG Section 8.7 Criteria for Requiring a Change (gray box). This section shall be revisited and completed after the first annual evaluation of Load Profile Models by ERCOT- | 2 | PWG
LPG |  | 2 | LPG Section 8.7.1 Criteria for Making a Change Based on Information Other than Current Load Research Data (gray box). | 2 | PWG
LPG |  | 4 | LPG Section 9.2.3.1 Load Profile ID Change Related to a TDSP Tariff Change (gray box) | 3 | TX SET
LPG |  | 5 | LPG Section 9.2.3.3.1 Non-IDR to IDR (NIDR to IDR) (gray box) | 3 | TX SET
LPG |  | 6 | LPG Section 11.2 Initial Assignment Validation for Opt-In NOIE’s (gray box) | 2 | PWG/Rbrown
LPG |  | 7 | LPG Section 11.3 Validation when Load Profile Segment definitions change (gray box). | 3 | ERCOT
LPG |  | 8 | LPG Section 11.4 Annual Validation (gray box). | 1
LPG |  | 9 | LPG Section 12.7 Costs for Profile Segment Changes (gray box). | 2 | ERCOT
LPG |  | 10 | LPG Section 15 Load Research Samples (gray box). LPG Section 15 Load Research Samples (gray box). | 2 | PUCT
LPG |  | 11 | LPG Section 15.2.2 Availability of Data (gray box). | 2 | PUCT
LPG |  | 12 | LPG Section 15.2.4 Creation of New Samples (gray box). | 2 | PUCT
LPG |  | 13 | LPG Section 16.1.2 Establishing New TOU Schedules (gray box). | 2 | PWG/Rbrown
LPG |  | 14 | LPG Section 16.2.3 TSDP Programs (gray box) | 2 | PUCT
LPG |  | 15 | LPG Section 16.5 Access to Data (gray box). | 2 | PUCT
LPG |  | 16 | LPG Section 16.5.1 Access to the Sponsored Load Profiles (gray box). | 2 | PUCT
LPG |  | 17 | LPG Section 16.5.2 Access to Data for Individual ESI IDs in the DLC Sample (gray box). | 2 | PUCT
LPG |  | 18 | LPG Section 17.2 IDR Requirement (gray box). | 1 | PWG
PRR |  | 19 | Protocol revision to remove IDR meters. | 1 | PWG
PRR |  | 20 | Follow up with PRR309 virtual meter change effective October 1, 2002. | 1 | PWG
MREAD |  | 21 | Expand on the estimation process for gaps in over and under reads. | 3
GEN |  | 23 | Potential Load Profile Segment change requests soon after July 31, 2002. | 1
GEN |  | 24 | PWG add more information on the ERCOT website and links. | 3
PRR |  | 25 | Protocols Revision Request for Section 18.4.4.2 | 1 | PWG
PRR |  | 26 | Susan Neel asked the question at RMS on Initial Validation of LP ID assignments. "Why can't ERCOT update their systems directly instead of having TDSPs submit 814_20s?" | 3 | PWG
PRR |  | 27 | The PWG has long questioned the reasoning behind the PUCT's action to add the phrase "if approved by the PUCT" in Protocols Section 18.7.1.4(2) "Availability of TOU Schedules." | 3
PRR |  | 28 | RMS Workshop on IDR default profile | 1
RMS |  | 32 | RMS issue submittal on notification of CRs of prior record. | 2
PUCT |  | 35 | Status report of PUCT project 25516 update. | 1 | Ernie
DLC |  | 37 | Review DLC implementation status. | 2 | PWG
MOUT |  | 39 | Issue when no CR of Record and meter stays energized. | 3
GEN |  | 41 | Review past meeting minutes for old business issues. | 2
MREAD |  | 42 | Estimation process for TDSP to submit 867s when data is missing readings | 3
VAL |  | 43 | ERCOT validation process for IDR vs. BusNoDem or BusLF profile ID assignments. | 1
IDR |  | 46 | UFE performance with new usage factor estimator. | 1
DATA |  | 47 | Settlement data in Lodestar vs. 867 transactions. | 3
GEN |  | 49 | Develop a contact list with phone numbers and emails of PWG members. | 3
VAL |  | 50 | The RMS discussed at the July 8, 2002, RMS meeting, the difficulty in distinguishing initial validation transactions from normal business transactions. Tracking the status is therefore difficult. The LPWG was asked to develop a proposed resolution and send to Texas SET for review. | 1
VAL |  | 51 | At the RMS meeting July 8, 2002, Bender asked that the resolution of the interpretation of assignment of profile ID on customer level versus premise level should be included in the RMS Operating Guides | 1
GEN |  | 52 | Role of facilitator? | 2
LR |  | 53 | ERCOT Load Research 2003 Budget | 2 | ERCOT/Bday
GEN |  | 55 | Meeting schedule coordination with PUCT and other ERCOT subcommittees. | 1
PUCT |  | 56 | PUCT Docket 26359 Competitive Metering | 2
LPG |  | 57 | Draft a section to add to the LPG addressing how profiles will be maintained and the types of changes that may be made | 2 | ERCOT/Bday
DT |  | 58 | Research documentation on PWGs responsibility for Decision Tree | 2
GEN |  | 59 | Question on Res units changes back to Landld /do you change profile back to bus from RES? | 2 | PWG
GEN |  | 60 | Ercots 2003 budget Items | 2
GEN |  | 61 | Idr Loading in Lodestar – James Cohea Chair | 1
IV |  | 62 | 814_20 transaction changes. | 1
GEN |  | 63 | Pioneer Natural Resources to pursue flat profile | 3
GEN |  | 64 | Photovoltaic generation
ME |  | 65 | Annual Profile Model Evaluation
VAL |  | 66 | Lessons learned from Initial and Annual Validation
PRR |  | 67 | PRR 368 Section 18 References (PRS review 11/26)
LPG |  | 68 | Load Profiling Guides Revision Request (LPGRR) numbering and mananging system needed
PRR |  | 69 | PRR 367 IDR Installation & Use (PRS review 11/26)
PRR |  | 70 | PRR 362 Load Profiling Guide

## Closed Items
Subject | Status | Word doc/cross ref | Pending Items | Priority | Responsible party
LPG | closed | 3 | LPG Section 9.2 Processes to Change Load Profile ID Assignments (gray box). | 3 | TX SET
DT | closed | 22 | Valid ID profile list in decision tree. | 1 | PWG/ERCOT
LPG | closed | 29 | Status of LPG. | 1
VAL | closed | 30 | Review the status of Initial Validation of Profile ID sub team by Terry Bates. | 1
RMS | closed | 31 | Report on RMS meeting on 7/8/02. | 1
VAL | closed | 33 | Review the usage month sub team status by John Taylor. | 1
RMS | closed | 34 | Update the Annual Validation for 2002 Resolution for submittal to RMS. | 1
PRR | closed | 36 | Status report of PRR330 and true-up resettlement. | 1 | Ernie
MREAD | closed | 38 | Meter read date vs. meter change date issue. | 3 | TX SET
PRR | closed | 40 | Routine PRR review for PWG issues. | 3 |  | same as #21???
TDSP | closed | 44 | TDSP Performance incentives and penalties. | 3
TAC | closed | 45 | TAC Task Force on ERCOT Governance. | 3 |  | TX choice is leaving
GEN | closed | 48 | Develop a Calendar of events that affect PWG. | 3
TAC | closed | 54 | TAC task force on Governance. | 3