## Notes
Determine Business Processes
Develop process flows and document business processes
Determine Business Best Practices
Develop Best Practices and/or Operating Guide, Identify protocol changes, Submit PRR for revisions
Develop TX SET recommended GLs
Review current TX SET guidelines, recommend changes, identify new transactions required for changing out a meter, I.e. Service Orders, Meter test Results. Assumptions: minimum transaction modifications. i.e. 814_20, 810-02. Add SAC04 charge code for discretionary charge for meter owner customer credit.
MPs Identify System Impact
All Market Participants will review Best Practices, TX SET guidelines for feasibility and system impact, document how Customer Owned Credit will be invoiced, address proration issue
System Impact SCR and Protocol PRR
Market will develop any System Change Request (SCR) and Protocol Revisions Requests (PRR) to implement Competitive Metering in a timely manner to issuer quality assurance
ERCOT and MPs Program based on SCRs
Start minimal coding changes to support a non-set process. Full System Coding will not begin until the evaluation is complete. Developers will begin coding based on the SCRs. ERCOT I/T must have notification of scope 60 days prior to start of coding changes.
Develop Market Testing Requirements
Assumptions are for a paper flow process where ever possible. Develop test scripts and schedule, work with TTPT to develop plan for Flight 1003.
Market Testing Flight - TTPT
Assumptions are for a paper process where ever possible . If the MP misses the November test flight the next available time is February 2004. The market will require a manual process until automated function can be implemented. Request testing begin in November for COMETWG changes in TTPT Flight 1003.
Implementation Management
Market will open Jan 02,2004 with a paper/e-mail process where ever possible. The only transaction changes required are the 810_02 and the 814_20.
Competitive Owner GLs Implemented
Changes to the 814_20 for meter ownership should only be in the N1 name segment. The 810_02 invoice will have a new code for the TDSP meter ownership credit, or other meter ownership TDSP charges.
Milestones
1. Rule final Mid-May
2. Team 2 deliver Draft business requirements to RMS and TX SET - Apr.15
3. RMS approve COMET business requirements for TX SET - Apr.23
4. Submit PRR that have system impacts to RMS - Apr 23
5. TDSP file Tariff - Aug
6. TX SET release GLs to MP - June 1
7. Submit PRR for non-system impact to RMS - Aug 30
8. MPs complete development and testing - Oct 10
9. MPs complete TTPT - Dec 5

## Timeline
Competitive Metering Ownership Timeline (Draft)
| 2003 | [11 empty] | 2004
Event | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Market Draft Rule 25.311 Jan.16 | bar: 2003 Jan
Market Review of Rule | bar: 2003 Jan to 2003 Feb
Market Participants Comments | bar: 2003 Feb
PUCT Workshop / Review Comments | bar: 2003 Mar
Final Rule Making Project # 26359, April EOM | bar: 2003 Apr to 2003 May
TDSP File Tariff | bar: 2003 Jun to 2003 Aug
RMS COMET Workshops
Timeline Due to PUCT Staff Mar.28 | bar: 2003 Mar
Market Wide List/Standards Apr.25 | bar: 2003 Apr
Market Structure and Timeline May 30 | bar: 2003 May
Determine Business Processes | bar: 2003 Feb to 2003 May
Document Business Requirements and Best Practices (Operating Guide) | bar: 2003 Apr to 2003 Jun
Develop TX SET recommended GLs | bar: 2003 May
MPs Identify System Impact and write SCR | bar: 2003 Apr to 2003 Jun
Recommend Protocol PRR to RMS | bar: 2003 Apr to 2003 Aug
ERCOT and MPs Program based on SCRs involving TTPT Flight 1003 | bar: 2003 Jun to 2003 Oct
Develop Market Testing Requirements | bar: 2003 Aug to 2003 Sep
Market Testing Flight - TTPT | bar: 2003 Oct to 2003 Nov
Develop communication Formats (Non-SET) | bar: 2003 Jun to 2003 Oct
Implementation Management
Competitive Ownership Implemented | bar: 2004 Jan
Evaluate Results | bar: 2004 Jun
Adjust Processes for lessons learned | bar: 2004 Jul to 2004 Aug
: Joint COMET development activities
: Rule Making activities
: All MPs activities
: Implementation Management
: Deliverables