Key Points for the Combined Cycle Plant Modeling Project

- Dynamic simulations are crucial to the planning and operation of the ERCOT power system

- It is projected that by the summer of 2005 about 22% of the ERCOT total generation capacity maybe composed of combined cycle plants. It is possible that during an off-peak season, a much higher percentage of generation will be supplied by these plants.

- Last August, since the number of combined cycle plants is on the rise, ERCOT  initiated an effort to pursue hiring of consultants to develop models, and incorporate them into the PSS/E. ERCOT staff prepared a rough draft of an RFP for discussion, modification and revision.

- This project has recently been moved to a lower order of priority and is on the back burner or off the stove. We recommend that this project resume a higher priority, such that adequate PSS/E dynamics models are developed, validated, coded, and are ready for use by December 2004. To meet this timeline, the DWG recommends that the RFP be awarded to a vendor by December 2003; hence, the refinement of the RFP should begin within the next few months.

- The DWG suggests the following steps to be included within an RFP, starting with the block diagrams of the model developed by CIGRE:

- Using the CIGRE published models, develop “PSS/E ready” Fortran code. This can be accomplished within a few months. Estimated cost for this item is $20,000.

- Develop detail model verification testing procedures. The objective is to obtain the parameters for the models. Test one single-shaft plant and one multi-shaft plant.

- If necessary, install measurement devices and take measurements for the plants that were tested and for which model parameters were derived.

- Conduct simulations

- review and approve the validity of the models. Estimated cost for Items 2-5 is $60,000.

- Based on the experience gained from the items 1-5, incorporate language in the Generation Interconnection Request to address future combined cycle plants model requirements and the associated procedures.

- The total cost of Phase I( Items 1-6) is estimated at $80,000, to be completed by December 2004.

- The DWG also discussed the need for obtaining CIGRE model parameters for existing combined cycle plants. This may need to be implemented as a second phase of this project, and may be costly. The DWG will evaluate the results of phase I, and recommend to what extent existing plants should be tested to obtain model parameters.