## 2004 Market
Reference Number= ERCOT Project No.
Project Title= Short Description of Project
Outcomes= Business Objectives
Estimated Cost to ERCOT= 1 - H=>$5M, 2 - MH= $3-5M, 3 - M= $1-3M, 4 - HL= $500K - $1M, 5 - L= $100K-$500K, 6 - LL= <$100K
Comments= Any additional supporting comments
Ref. No. | Source | Priority | Rank | Target Release | Project Title | Outcomes | Est. Cost | Comments
PR-30161 | Market | 1.1 | 1 |  | PRR413 - Optimization for the Whole Operating Day in RPRS Procurement Process | Modify RPRS procurment process so that RPRS procurement process is an optimum solution for the whole Operating Day. | 3 - M
PR-40038 | Market | 1.2 | 2 | Q1 | Mass Customer Transition | To be able to transition large volumes of customers to other Reps in the event of a major market situation | 4 - HL
PR-30162 | Market | 1.2 | 3 |  | PRR423 - Dispatch of Generation Resources Below Minimum Operating Level | Requires ERCOT to use other Resource Dispatch options to maintain system reliability prior to Dispatching a Generation Resource below its Low Operating Limit. | 6 - LL
PR-30135 | Market | 1.3 | 4 |  | SCR 725 - ERCOT Settlement Estimation | To provide all recipients of Settlement Statements information regarding the estimation required because of missing metered values. With each Settlement Statement, ERCOT must provide information regarding the Load estimation required because of missing metered volumes. Information for ERCOT-wide estimation, represented REPs estimation, and their specific QSEs estimation. | 6 - LL
PR-20128 | Market | 1.3 | 5 |  | SCR722 Publish Zonal Deployments | Real-Time Portal Posting and XML query capability of Aggregate zonal unit-specific incremental and decremental deployments, separately stated, each by category, including aggregate OOM deployments. | 6 - LL
PR-20127 | Market | 1.3 | 6 |  | SCR721 XML Data for QSEs | QSEs desire increased transparency of ERCOT operations and, accordingly, the timely availability of real-time operating data without having to browse or scrape the ERCOT system. ERCOT computer system performance is suffering from this current lack of XML enabled data interface. | 5 - L
PR-30166 | Market | 1.3 | 7 |  | PRR446 -Disclosure of OOMC Dispatches | Provides for disclosure of each unit receiving an OOMC Dispatch Instruction, intervals for which the instruction was received, intervals for which and quantity of energy deployed by ERCOT from units receiving an OOMC Dispatch Instructions
PR-40001 | Market | 1.3 | 8 | TO 4.X | PRR428 - RMR Scheduling process | Modifies scheduling of RMR units under a separate QSE | 5 - L
PR-40001 | Market | 1.3 | 9 | TO 4.X | LAAR /BUL Enhancements | Includes Resource Types information on RRS awards to market, Block bids for LAAR AS bids, Multiple BUL Bid Curves per QSE per CM Zmzone | 5 - L
PR-30032 | Market | 2.1 | 10 |  | PIP102 Voltage Support Compensation | System not designed to calculate compensation for voltage support. | 5 - L
PR-20130 | Market | 2.1 | 11 | TO 4.X | PIP137/PRR211 Association of BE Bids with RPRS (Needs to be done in conjunction with PRR413 - PR) | The system does not associate Balancing Energy bids with RPRS. When functionality added, add “and associated Balancing Energy bids to last sentence in QSE’s Submission for 1430 and add “and save RPRS energy bids for applicable balancing markets” in ERCOT Responsibility for by1800. Need more input from stakeholders. | 5 - L | Will be included in PR-40001 - Technical Operations Release 4.X
PR-30013 | Market | 2.1 | 12 |  | AS Mismatched Schedules | Ensure that ERCOT operation system follows Protocols. Relieve manual workload. Currently, ERCOT system does not consider the factor of mismatched AS schedules when calculating AS self-arrangement value. Settlement staff need to manually correct QSE's AS self-arrangement when there are mismatched schedules between QSEs. | 6 - LL
PR-30163 | Market | 2.2 | 13 |  | PRR422 - OOM Zonal Dispatch Instructions | Provides details on deployment and settlement of Zonal OOME Dispatch Instructions in command and control conditions. | 4 - HL
PR-30016 | Market | 2.3 | 14 | TO 4.X | Dynamic Ratings | Several of ERCOT's TO's have implemented, or are about to implement, dynamic line rating as a function of ambient temperature or other factors. ERCOT must implement this same methodology to avoid unnecessary costs. | 5 - L | Will be included in PR-40001 - Technical Operations Release 4.X
PR-40034 | Market | 2.3 | 15 | Q3 | TX SET V2.1 | This version is still undefined. The MPs have already begun to develop change controls. | 3 - M
PR-30103 | Market | 3.2 | 16 | Q3 - Q4 | TCR Settlement Synchronization of Credit Payment with Settlement Invoices | TCR Credit payments rom daily congestion costs need to be intrgrated into the Settlements invoicing process to have one settlement statement that includes all TCRcredits at the same time and on the same form as the rest of the Market Participant's settlements. | 5 - L
PR-30026 | Market | 3.3 | 17 | 2Q | PIP204/PRR283 EPS Meter Data Transmittal via extract | New section on treatment of EPS Load Data was added. A new section was drafted with reference to making consumption data available to market participants of EPS meters. Boxed until system supports it. | 5 - L
PR-30133 | Market | 3.3 | 18 |  | Fix Retail XML Transaction Format to MPs | Make outward facing XML more consistent with standards across the country. (Only 2 participants currently using XML.) | 5 - L
PR-30034 | Market | 3.3 | 19 | 3Q | PIP128 Synchronous Condenser Compensation | No design for support of Sychronous Condenser Service. Language on payment and load uplift boxed until system supports; Reference to no compensation made in protocols. QSEWG needs to re-evaluate need. | 5 - L
PR-30035 | Market | 3.3 | 20 |  | PIP134 Messaging System Language Clarification | Language clarification: information is posted by ERCOT, but not using the Messaging System. Language boxed for future system support. Question for WMS: should box be removed? Posting requirement related to PIP138, PIP153 & PIP155. | 4 - HL
PR-30037 | Market | 3.3 | 21 | TO 4.X | PIP158 Contents of Dispatch Instructions | System does not support all of the indicated contents of the systematic dispatch instruction. Language boxed for future implementation. Workaround: Provide verbal/faxed instructions; Buy more regulation; Implement voice recorders Interim Language: denote timestamp on Dispatch Instruction Discussed need for this w/QSEWG in Aug. '02. Consensus was Low Priority. System impact is on P1 XML. | 4 - HL | Will be included in PR-40001, Technical Operations Release 4.X
PR-30038 | Market | 3.3 | 22 | 2Q | PIP188 Forward of Meter Read Information within 4 hrs | Boxed language that requires meter read data received by ERCOT prior to midnight to be forwarded to CRs by 0400 the next day, and meter read data received by ERCOT between midnight and 0600 be forwarded to CR by noon the same day.. | 5 - L | This was boxed due to uncertainty around system performance. If systems can meet the timing, the language will be let out of the box.
PR-30039 | Market | 3.3 | 23 | TO 4.0 | PRR307 Controllable Resources | This Protocol revision defines Load which can provide Regulation Service. | 4 - HL | Will be included in PR-40001, Technical Operations Release 4.X
PR-30132 | Market | 3.3 | 24 | 3Q | PRR355 - BLT OOME | Provide for payment when Block Load Transfers provide OOME. Supported by ERCOT thru manual process. This project would be to automate the calculations. | 5 - L
PR-40037 | Market | 3.3 | 25 | Q3 | MSP Competitive Metering | To be able to handle meter service providers within the Texas market once their role has been defined and approved by the PUC | 2 - MH
PR-40039 | Market | 3.3 | 26 | Q1 | Day Ahead / Forward Markets | To set up Day Ahead and Forward Markets for Energy. | 3 - M
PR-30022 | Market | 3.3 | 27 |  | UFE Analysis Metering | To attain compliance with Protocol Section 11.5 - Unaccounted For Energy Analysis. According to Protocols Section 11.5.2.1 The cost of installing any metering solely for UFE analysis purposes will be recovered through the ERCOT System Administration Fee. Additionally, business resources are required to support the working group oversight the actual analysis, and the reporting requirements defined in Protocols 11.5. | 3 - M
Note on G25: ERCOT: See if there are only 2 participants still using this.