## Active Projects
Reference Number= ERCOT Project No.
Project Title= Short Description of Project
Outcomes= Business Objectives
Estimated Cost to ERCOT= 1 - H=>$5M, 2 - MH= $3-5M, 3 - M= $1-3M, 4 - HL= $500K - $1M, 5 - L= $100K-$500K, 6 - LL= <$100K
Comments= Any additional supporting comments
Projects on this list are currently in flight. There is an approved budget and project team assigned to the project.
Ref. No. | Source | Priority | Rank | Target Release | Project Title | Outcomes | Est. 2003 Expend. | Target Implement | Comments
PR-20069 | Market | 2002 |  |  | PIP112 - BULs & PIP210 Blocked Deployment | Implement functionality for Balancing Up Loads and block deployment of LaaRs | 3 - M | 2003-11-17
PR-20104 | Market | 2002 |  |  | PRR327 - Confidentiality & 348- Confidentiality Revision | Evaluation of database software to determine if it can provide an environment to make information available to the public via queries. | 6 - LL | 2003-12-31
PR-20123 | Market | 2.1 |  |  | PIP106 Direct Load Control | Protocols Section 18.7, Supplemental Load Profiling addresses the need for Load Profiles that accommodate pricing schemes that encourage a demand response to price in the retail market. Currently there is not a profile for DLC and the system cannot currently support the use of this type of profile. |  |  | Estimated that a year is required to implement. The Load Profiling Working Group has submitted a PRR for this. Original PRI 2.1 Rank 22; PR-30040 has been rolled into this project
PR-20126 | Market | 1.2 | 9 |  | SCR 720 ERCOT Data Transparency | The ERCOT market design is zonal, both in terms of market and grid operations and are designed to operate and financially settle on a 15-minute interval basis, with QSEs having the opportunity to self-manage their zonal positions on a bilateral basis. The Net Zonal Energy and Actual Zonal Generation quantities (“QSE Data Requirements”) are key components of the 15-minute interval, bilateral, zonal market design that are necessary, and valuable, in maximizing the actual availability and efficient use of the ERCOT grid. | 6 - LL
PR-20139 | ERCOT | 2002 |  |  | 810 Performance Enhancement | Complete re-write of 810_02 settlement process from Lodestar to the Report Server | 6 - LL | 2003-09-10
PR-20147 | Market | 1.3 |  |  | Analyze System Capacity for QSEs | This project will perform analysis on the current systems to determine the capacity for allowing the QSEs to increase the number of sub-QSEs they have. This requires analysis and stress tests of the systems. | 6 - LL | 2003-08-31
PR-30002-02 | Market | 1.1 |  |  | Move-In/Move-Out Market Solution to Stacking (TX SET v2.0) | To provide a system and process changes necessary to support the final Move In Move Out Process as designed by the market. These changes may require architecture changes to support a 4 hour turn around requirement. | 4 - HL | Planning Phase; Implementation 8/01/04 l/t | Long-Term Intiative underway; incl TX Set 2.0
PR-30004 | Market | 0 |  |  | Texas Set 1.6+ | To support system changes and market design changes for future Texas Set V1.6 and 1.7 expected in 2003 | 5 - L
PR-30007 | Market | 2.3 |  |  | SCR717 Implement GISB 1.6 (NAESB 1.6) Transport | Implement the transport protocol defined by GISB 1.6 to allow large market participants a single, secure transport method | 5 - L | Planning Phase
PR-30008 | ERCOT | 1.3 |  |  | Load Profiling Software | Enhance load profiling software to improve user capabilities and enhance reporting abilities | 5 - L | Planning Phase
PR-30014 | Market/ ERCOT | 1.3 |  |  | Load Research Sampling | Design load research samples and deploy sample meters in support of Load Profiling (per Protocols Section 18). According to Protocols Section 18, the cost of performing any load research for load profiling purposes is the responsibility of ERCOT. Additionally, business resources are required to perform the actual analysis and the reporting requirements defined in Protocols 18. Protocols Section 18.7, Supplemental Load Profiling addresses the need for Load Profiles that accommodate pricing schemes that encourage a demand response to price in the retail market. Currently there is not a profile for DLC and the system cannot currently support the use of this type of profile. Includes developing functionality for DLC for BULs. |  | Planning Phase | Consolidated 20123, PIP106 Direct Load Control; 30014, Load Research Sampling; and 30040 DLC for BUL. Load Research Sampling is subject to PUCT 25516 rulemaking
PR-30023 | Market |  |  |  | PRR312 Enhance ESI ID Lookup | Adds Station ID, Power Region, Premise Type and Status (active/de-energized/inactive) field to ESI ID Look-up function. | 6 - LL
PR-30047 | ERCOT | 1.1 | 3 | CO | EDI Pipeline and Transaction Systems | Undertake a number of improvements in the EDI Process including implementing top items identified by SWAT team to improve application hardening, simplify EDI map maintainability/logic by dividing single 814 input map into multiple 814 maps per transaction type e.g. 814_01, 03 and others. | 4 - HL | Planning Phase
PR-30051 | ERCOT | 1.1 |  |  | Database Management |  | 3 - M | Exec Phase
PR-30051-01 | ERCOT |  |  |  | DB Management Subproject 01 |  | 4 - HL
PR-30052 | ERCOT | 2.1 |  |  | Portal Redevelopment Analysis | The current Portal will not be supported after March 2003. Redesign/Rearchitect the Portal and its interfaces to ERCOT systems. The current commercial and retail portal is not meeting market needs or expectations for reliability. | 3 - M | Exec Phase 10/5/03
PR-30054 | ERCOT | 1.3 |  |  | ETS Phase 2 Data Transparency | Generate new reports and provide additional enhancements and functionality within the existing ETS system. An internal Dashboard would also be developed to present summary graphs and transactional flows by MPs, display information on system health, show exception alerts, volumes of transactions processed and backlogged, and batch status updates. | 3 - M | Exec Phase
PR-30056 | ERCOT | 2.1 |  |  | Outage Sensitive Factor (OSF) | The Outage Coordinators study many cases with lots of contingencies and need a faster tool to assess the impact of the outages on the contingencies. This was originally submitted as a OTDF change but it was determined that modifying the OTDF would not satisfy our requirements. By maintaining a reliable system, the Market Participants are provided a stable marketplace. This will reduce the risk and uncertainty of the market. | 6 - LL | Planning Phase
PR-30058 | ERCOT | 2.1 |  |  | Siebel 7.0 Upgrade/Replacement | Upgrade to a more current and fully supported version of ERCOT's Siebel registration system. Siebel 7.0 has new web browser capabilities and improved functionality that ERCOT can use to meet market expectations for visibility into our systems. | 3 - M | Planning Phase
PR-30061 | ERCOT | 1.3 |  |  | Enterprise Cyber and Physical Security |  | 2 - MH | 2003-11-30
PR-30061-B | ERCOT | 0 |  |  | ERCOT Cyber/Physical Systems and Plant Upgrades; ERCOT Risk Management Program and Systems | Implement new and required cyber and physical security systems and facilties tied to ERCOT Security and Risk Management Program
PR-30063 | ERCOT | 2.1 |  |  | Lawson Software Upgrade/Replacement | Lawson will no longer support current version. Must upgrade to retain support. Upgrade Lawson Environment to 8.0.1_ESP2 Upgrade Lawson Application to 8.0.3 | 5 - L | Exec Phase 11/3/03
PR-30064 | ERCOT | 2.1 |  |  | Pkg 2 Commmercial Development Systems | Required for ERCOT to own development environment that allows clean code fixes and migrations into production. Current development environments do not allow reliable coding or testing results. | 3 - M | Exec Phase
PR-30075 | Market | 0 |  |  | Outage Scheduler | Protocol 8 (9) requires ERCOT to establish record keeping for the outage schedules. The record that is kept at this date is incomplete without an historical audit trail of the modifications that are made. This project will provide (1) a complete record of modifications that take place during the lifetime of an outage in order to evaluate our processes at ERCOT and provide the PUCT with informartion needed to monitor the processes; and (2) enhanced operational flexibility and outage records to more accuratly reflect actual system conditions during the full duration of each outage.
PR-30082 | ERCOT | 2.2 |  |  | Commercial Applications System Upgrade | Complete an architectural review of TCH / Seebeyond and upgrade to new version if we do not replace. | 3 - M
PR-30083 | ERCOT | 0 |  |  | Lodestar Upgrade/Replacement | Complete an architectural review of Lodestar and upgrade to new version. |  | In review
PR-30102 | ERCOT | 3.1 |  |  | NICE Playback System | Provide Operations, Help Desk and Client Representatives the ability to playback audio recordings without stopping the audio recording/archiving process. | 6 - LL
PR-30116 | ERCOT | 1.1 |  |  | Disaster Recovery Ph II | installation of required systems for Ph II of Disaster Recovery and expansion of existing Austin Computer Room in order to provide additional 500sq/ft to accommodate | 4 -HL | 2003-08-31
PR-30125 | Market | 1.1 |  |  | Lodestar Data Loading Improvements | Improve loading of usage data into the Lodestar system for Settlement. | 6 - LL | Planning Phase
PR-30129 | Market | 0 |  |  | SCR723 Remote Access | Add hardware, software, and required license to enable Transmission Operators to access the ERCOT network analysis software remotely through the ERCOT WAN. Implement secure access to the network applications that will insure that only authorized Transmission Operators will have access.
PR-30130 | Market | 0 |  |  | PRR352 Proxy Day Determination Extension | Changes the Non-Weather Sensitive (NWSIDR) Proxy Day determination method to use the most recent historical ESI-ID interval data from the last 12 months. | 5 - L | 2003-09-30 | 2.1, 24
PR-30139 | Market | 1.1 |  |  | SCR 727 - ESI ID Service history | Provides REPs and TDSPs information regarding the relationship of ESI-IDs to all components of the settlement recorder (REP, TDSP, Profile, Congestion Zone, Loss Code, UFE Zone, sub-UFE Zone and QSE) and relative usage information for a given trade date, as of a given settlement date. | 6 - LL
PR-30141 | ERCOT | 2.1 |  |  | EMS/MMS Hardware system upgrades/replacement | Upgrade CPU and RAM for EMMS Department | 5 - L | Exec Phase 10/24/03 | Subproject 01
PR-30143 | ERCOT | 1.1 |  |  | Portfolio/Project Management System | Implement a system to track and monitor the progress of projects throughout their lifecycle. | 6 - LL | Planning Phase
PR-30147 | ERCOT | 1.3 |  |  | Document Managing/Imaging System | Analysis Phase | 5 - L | Planning Phase | Planning Phase
PR-30148 | Market/ ERCOT | 1.1 |  | TO 3.0 | EMMS System, Release 3.0 | PR-20122, PRR332 Unit Testing; PIP137/PRR211 Assoc of BE bids wRPRS; Load Rollover during line outage; Enhance BES & RPRS; Dynamic Ratings; RT Market Ramp Rate; Stop Osc. Of Constraint Mgmt; EMS Front End Replacement; Security Constraint PF; Enhance STNET; CSC Limit Calc/Post; SPS Modeling in Contingency Analysis; RPRS Redesign; VSAT/TSAT Interface Upgrade; ESCA to PTI Download; PRR349 UBES-DBES Ramp Rates; PRR359 Improve Resource Plan; PRR342-Sim. Procure of AS | 2 - MH | Planning Phase | Consolidation of: 20122, PRR332 Unit Testing; 20159, Load Rollover during line outage; 30044, Stop Osc. Of Constraint Mgmt; 30050, EMS Front End Replacement; 30059 Alarm Change Resource Plan; 30060, Security Constraint PF; 30074, Enhance STNET; 30085, SPS Modeling in Contingency Analysis; 30094, VSAT/TSAT Interface Upgrade; 30095 System Map (Alstom); 30096, ESCA to PTI Download; 30128, PRR349 UBES-DBES Ramp Rates; 30131, PRR359 Improve Resource Plan; 30134 PRR 373 OOM as Instructed Deviation; 30140, PRR342-Sim. Procure of AS; 30144 EMP 2.2 Upgrade; 30167, Archival of Shift Factors; 30168, PRR424 - Elimination of Resource Specific Deployment used for Energy Purposes; 30169, Handling Equipment name Changes; 30170, Implement a selected contingency into power flow; 30171, Automatic generation of one-line diagrams
PR-30149 | PUCT/ERCOT/Market |  |  |  | Data Warehouse | Long-term data infrastructure improvement project. |  | Planning Phase
PR-30150 | ERCOT |  |  |  | Tracking of Digital Certificates | Modify system to track certain attributes of digital certificates |  | Initiation Phase
PR-30151 | ERCOT |  |  |  | HR/Payroll System | Implement an integrated system for HR/Payroll |  | Initiation Phase
PR-30152 | ERCOT |  |  |  | REC Trading Program Enhancements | Provides enhancements to the REC program including public message board; modifies query and report functionality, and messages | 6 - LL | Planning Phase
PR-30153 | ERCOT |  |  |  | TCR Trading Program Enhancements | Add functionality to maximize bid-based revenues by applying credit limit to clearing prices; also enhances reports | 6 - LL | Planning Phase
PR-30155 | ERCOT |  |  |  | WAN Renewal | WAN connectivity renewal | 5 - L | Exec Phase
PR-30156 | ERCOT |  |  |  | SCR730 MOS Test Environment for MP Testing | Market Test environment which enables interface and business testing for the market | 5 - L | 2004-01-09 | Market Participants need an environment to test XML/Portal submissions, responses, and notifications.
PR-30158 | Market | 1.3 |  | TO 4.X | PRR397 - McCamey Area Congestion Management | This is designed to minimize uplifted congestion costs while attempting to reliably maximize the use of the transmission system in the McCamey area where numerous wind turbine generators are currently located and additional wind generators may be constructed. Establishes Tradeable Generation Rights. | 6 - LL
PR-30159 | Market | 1.1 |  |  | PRR371 - OOM Compensation | Increases the number of Resource Categories for OOM Capacity, Energy and Startup Payments. Provides for payment for Minimum Energy | 6 - LL | Initiation Phase
PR-30160 | PUCT | 1.1 |  |  | Nodal Market Redesign | Redesign wholesale market per PUCT order. | 1 - H
PR-30164 | ERCOT | 2.3 |  |  | Projector replacement for Met Center back up control center | Improve clarity and dependability | 5 - L
PR-30165 | ERCOT |  |  |  | PRR440 - Interim Removal of Market Solution
PR-30172 | ERCOT |  |  |  | TCC Computer Room/Annex HVAC additions | Modify cooling units in TCC and Annex Bldg.
PR-30173 | ERCOT |  |  |  | Taylor Blue Bldg. workspace modifications | Modify workspaces to accommodate employees and cotractors
PR-30174 | ERCOT |  |  |  | MOStoLodestar interface modification
PR-30175 | ERCOT |  |  | 2004-10-04 | SAS70 Type II | Activities to ensure readiness for SAS70 Type II | 3 - M
PR-30176 | ERCOT |  |  | 2004-04-01 | HIPPA Compliance | Activities to ensure compliance with HIPPA | 4 - HL
PR-30177 | ERCOT |  |  |  | Austin Met First Floor Buildout
PR-30178 | ERCOT |  |  |  | Taylor Plaza buildout
PR-40002 | ERCOT | 0 |  |  | PUCT Rule - 23100 - Market Oversight and Market Oversight Systems in the ERCOT market | Implement the recommendations and associated systems, software and applications from the PUCT Market Oversight Design effort slated to complete in October 2003 |  | Wallace
PR-40003 | ERCOT | 0 |  |  | Tier 1 SAN: I-Test |  |  | Technology Services
PR-40004 | ERCOT | 0 |  |  | Account Management CRM | Provide customer account information for all MPs, to all ERCOT personnel, regarding contacts, issues, disputes, resolution, and correspondence
PR-40041 | ERCOT | 0 |  |  | New Building |  |  | Technology Services
PR-40042 | ERCOT | 0 |  |  | Enterprise Data Warehouse | To construct the hardware and software to support the arcitected data archive and warehouse to support the PUCT project and internal ERCOT users |  | Development
PR-40050 | ERCOT |  |  |  | New building in Taylor

## Project Priority List
Reference Number= ERCOT Project No.
Project Title= Short Description of Project
Outcomes= Business Objectives
Estimated Cost to ERCOT= 1 - H=>$5M, 2 - MH= $3-5M, 3 - M= $1-3M, 4 - HL= $500K - $1M, 5 - L= $100K-$500K, 6 - LL= <$100K
Comments= Any additional supporting comments
Projects on this list are pending.
Ref. No. | Source | Priority | Rank | Target Release | Project Title | Outcomes | Comments | Est. Cost
PR-40044 | PUCT | 1.1 | 1 | With TX Nodal | ERCOT Run Day Ahead Market Rule 27678 | Placeholder for proposed rule for ERCOT Run day Ahead Market Project |  | 3 - M
PR-40045 | PUCT | 1.1 | 2 |  | CRR Rule 28226 | Placeholder for proposed rule for CRR's Project |  | 4 - HL
PR-30161 | Market | 1.1 | 3 |  | PRR413 - Optimization for the Whole Operating Day in RPRS Procurement Process | Modify RPRS procurment process so that RPRS procurement process is an optimum solution for the whole Operating Day. | Market Rank - 1 | 4 - HL
PR-30001 | ERCOT | 1.1 | 4 |  | Competitive Metering in 2004 for Large Nonresidential Customers | Modify ERCOT processes and Lodestar to support competitive metering before Jan 1, 2004 |  | 5 - L
PR-30064 | ERCOT | 1.1 | 5 |  | IT Infrastructure Build-Out | In order to provide an adequate test environment for current and future projects as well as market advancements this project will include data storage and IT test environments for P-Test, I-Test, Dev and Participant Testing. |  | 3 - M
PR-30093 | ERCOT | 1.1 | 6 | TO 4.X | RPRS Market Redesign | Include dependency between hours and include temporal and network constraints | Will be included in PR40001, Technical Operations Release 4.X | 3 - M
PR-40001 | ERCOT | 1.1 | 7 | TO 4.X | Enhancement to OOM tools for congestion management | The OOM tools would be enhanced for managing congestion more effectively: a) Fleet deployment of OOM b) Dispatch management tool for electronic recording c) Building OOM into SCE equation |  | 4 - HL
PR-40001 | ERCOT | 1.1 | 8 | TO 4.X | Improve Real Time Local Congestion Management | Fix problems with (1) Disaggregation of portfolio schedule and award (2) Logging of active constraints from EMS |  | 5 - L
PR-40046 | ERCOT | 1.1 | 9 |  | ERCOT Network Reliability | Mitigate risks of single Network points of failure for SAN's, ITest and System Backups between data centers. Reduce negative impact to the Market and ERCOT Operations | Costs reflect purchase of electronics, installation and first year maintanence | 5 - L
PR-40005 | ERCOT | 1.1 | 10 |  | IDR Estimation logic changes | Changes in the IDR estimation routine to better estimate IDR ESI IDs when no actual data is available. Better estimation of IDR ESI IDs that will result in more accurate settlements. |  | 5 - L
PR-40006 | ERCOT | 1.1 | 11 |  | End of Life MMS (ES40) Servers | Replace existing MMS Compaq ES40 servers with up-to-date hardware with greater computational capacity. The ES40 servers will reach end-of-life in 2004. While they are still supported by HP, parts and maintenance will be increasingly costly. Switching to ES80 servers will also provide additional computational capacity to support enhancements to the MMS package. |  | 4 - HL
PR-40007 | ERCOT | 1.1 | 12 |  | SCR 727 Phase 2 | Enhancements/changes to SCR 727 to address known issues with the extract. Provide TDSPs and CRs with full/accurate view of data in ERCOT systems. |  | 5 - L
PR-40008 | ERCOT | 1.1 | 13 |  | Tier 1 SAN: Production |  |  | 2 - MH
PR-40009 | ERCOT | 1.1 | 14 |  | DW and Archive Systems and Storage Upgrades to support 2003 and 2004 additional capacity (dev/test, prod and DASD) | Adequate systems and storage performance to support previously implemented projects, planned projects and historical data/compute capacity growth |  | 4 - HL
PR-40010 | ERCOT | 1.1 | 15 |  | Server Consolidation | To identify and implement solutions that maximize computational capacity and minimize administrative overhead. ERCOT currently employs individual servers for most individual applications. From a cost and capacity planning standpoint, it would be beneficial to identify ways to run multiple applications on a smaller number of servers. |  | 2 - MH
PR-40011 | ERCOT | 1.1 | 16 |  | Portal Replacement Phase II | Provide data transparency to MPs related to transactions and business processes |  | 3 - M
PR-40012 | ERCOT | 1.1 | 17 |  | EMMS Systems and Storage Upgrades to support 2003 and 2004 additional capacity (dev, test, prod and DASD) | Adequate systems and storage performance to support previously implemented projects, planned projects and historical data/compute capacity growth |  | 3 - M
PR-40038 | Market | 1.2 | 18 |  | Mass Customer Transition | To be able to transition large volumes of customers to other Reps in the event of a major market situation | Market Rank - 2 | 4 - HL
PR-30162 | Market | 1.2 | 19 |  | PRR423 - Dispatch of Generation Resources Below Minimum Operating Level | Requires ERCOT to use other Resource Dispatch options to maintain system reliability prior to Dispatching a Generation Resource below its Low Operating Limit. | Market Rank - 3 | 6 - LL
PR-30084 | ERCOT | 1.2 | 20 | TO 4.X | CSC Thermal and Volt Limits Calcualtions/Posting |  | Will be included in PR40001, Technical Operations Release 4.X | 5 - L
PR-40001 | ERCOT | 1.2 | 21 | TO 4.X | Automate DC TIE Schedule tracking process | Automate (1) Inadvertent exchange flow calculation (2) QSE DCTie Schedule verification (3) Offset Calculation |  | 6 - LL
PR-40001 | ERCOT | 1.2 | 22 | TO 4.X | Load Forecast Performance | Graphical tool to analyze the variation of load forecast error over the time of forecast |  | 6 - LL
PR-40001 | ERCOT | 1.2 | 23 | TO 4.X | Performance monitoring of SCADA /State Estimator | Monitor SCADA/SE input data performance - failure due to ICCP link failure, RTU failure etc and identify responsbile TDSPs for coordination |  | 6 - LL
PR-40001 | ERCOT | 1.2 | 24 | TO 4.X | Performance Monitoring for ERCOT, TDSP and QSEs | Define and track reliability and operational metrics for ERCOT, TDSP and QSE to identify system failure and improve overall performance |  | 5 - L
PR-40001 | ERCOT | 1.2 | 25 | TO 4.X | Graphs for monitoring frequency performance | Graphical data analysis for monitoring impact on frequency , reasons for CPS1/CPS2 deviation etc |  | 5 - L
PR-40013 | ERCOT | 1.2 | 26 |  | OOME and OOMC Payments | Develop a program to calculate and verify Wind generator claims for OOME operation. Also possible develop programs to administer the OOMC cost calulations. This would reduce administrator involvement. Currently using highly manually intensive macros for comparing calculations from the Protocol to calculations provide by the generqtion entities. |  | 6 - LL
PR-40014 | ERCOT | 1.2 | 27 |  | Switcher Extract | Provide Competitive Retailers with 12 months of historical usage for ESI IDs that they gain as a customer. Provide CRs with full knowledge of usage data in ERCOT systems that will be used to settle their new customers. |  | 6 - LL
PR-40015 | ERCOT | 1.2 | 28 |  | TCR Report Enhancement | Add automated reports to reduce manual interfaces, provide ability to query documents and reports, reduce dependency on macros that must frequently be changed. This would provide administrator flexibility, more timely and easier to use customer information. |  | 6 - LL
PR-30135 | Market | 1.3 | 29 |  | SCR 725 - ERCOT Settlement Estimation | To provide all recipients of Settlement Statements information regarding the estimation required because of missing metered values. With each Settlement Statement, ERCOT must provide information regarding the Load estimation required because of missing metered volumes. Information for ERCOT-wide estimation, represented REPs estimation, and their specific QSEs estimation. | Market Rank - 4 | 5 - L
PR-20128 | Market | 1.3 | 30 |  | SCR722 Publish Zonal Deployments | Real-Time Portal Posting and XML query capability of Aggregate zonal unit-specific incremental and decremental deployments, separately stated, each by category, including aggregate OOM deployments. | Market Rank - 5 | 5 - L
PR-20127 | Market | 1.3 | 31 |  | SCR721 XML Data for QSEs | QSEs desire increased transparency of ERCOT operations and, accordingly, the timely availability of real-time operating data without having to browse or scrape the ERCOT system. ERCOT computer system performance is suffering from this current lack of XML enabled data interface. | Market Rank - 6 | 5 - L
PR-30166 | Market | 1.3 | 32 |  | PRR446 -Disclosure of OOMC Dispatches | Provides for disclosure of each unit receiving an OOMC Dispatch Instruction, intervals for which the instruction was received, intervals for which and quantity of energy deployed by ERCOT from units receiving an OOMC Dispatch Instructions | Market Rank - 7 | 5 - L
PR-40001 | Market | 1.3 | 33 | TO 4.X | PRR 428 - RMR Scheduling process | Implement scheduling of RMR units under a seprate QSE as per PRR428 | Market Rank - 8 | 5 - L
PR-40001 | Market | 1.3 | 34 | TO 4.X | LAAR /BUL Enhancements | Includes Resource Types information on RRS awards to market, BLOCK bids for LAAR AS bids, Multiple BUL BID Curves per QSE/ per cmzone | Market Rank - 9 | 5 - L
PR-30065 | ERCOT | 1.3 | 35 |  | EMS Network Upgrade | This project will upgrade the network for MOS and POS to gigabit performance. Network performance is having an impact on both the MOS market solutions and the POS data collection. By increasing the network speed, both of these functions will speed up and will not be subjected to performance issues during high activity periods. |  | 5 - L
PR-30069 | ERCOT | 1.3 | 36 |  | OVPI Evaluation/Implementation | Evaluate/Implement OVPI as a reporting tool, paying special attention to this product's ability to provide insight into the performance and capacity of network components. |  | 5 - L
PR-40001 | ERCOT | 1.3 | 37 | TO 4.X | Market Solution detection outside of SPD | Remove Dependency on SPD wrapper and implement the logic in separate program |  | 5 - L
PR-40001 | ERCOT | 1.3 | 38 | TO 4.X | Enhancement to Market Analyst Interface | Display AS awards that are not scheduled |  | 6 - LL
PR-40001 | ERCOT | 1.3 | 39 | TO 4.X | Training of Load Forecast Models | Annual training of Short term and Mid term load forecast models |  | 6 - LL
PR-40001 | ERCOT | 1.3 | 40 | TO 4.X | STNET server | Move the STNET functionality and read-only users off the production EMS onto new servers |  | 5 - L
PR-40001 | ERCOT | 1.3 | 41 | TO 4.X | HP Openview integration | Centralize and expand EMMS system health management |  | 5 - L
PR-40001 | ERCOT | 1.3 | 42 | TO 4.X | Enhancement to Development Test system | Sytem for IT development process |  | 6 - LL
PR-40001 | ERCOT | 1.3 | 43 | TO 4.X | Testing Simulation Environment | Simulation envrionemnt IT testing for SAT and Regression testing |  | 4 - HL
PR-40016 | ERCOT | 1.3 | 44 |  | 170 Systems Enhancements | Provide full implementation of workflow, expand to other ERCOT depts outside of Legal, HR, and Finance, and assess expansion to external user access. |  | 5 - L
PR-40017 | ERCOT | 1.3 | 45 |  | Lawson/170 Systems Integration | Provide tight integration between the two systems so that 170 Systems information is accessed from Lawson and vice versa. Will provide increased timeliness and accuracy of information. |  | 5 - L
PR-30032 | Market | 2.1 | 46 | 2Q | PIP102 Voltage Support Compensation | System not designed to calculate compensation for voltage support. | Market Rank - 10 | 5 - L
PR-20130 | Market | 2.1 | 47 | TO 4.X | PIP137/PRR211 Association of BE Bids with RPRS |  | Will be included in PR40001, Technical Operations Release 4.X; Market Rank - 11 | 5 - L
PR-30013 | Market | 2.1 | 48 |  | AS Mismatched Schedules | Ensure that ERCOT operation system follows Protocols. Relieve manual workload. Currently, ERCOT system does not consider the factor of mismatched AS schedules when calculating AS self-arrangement value. Settlement staff need to manually correct QSE's AS self-arrangement when there are mismatched schedules between QSEs. | Market Rank - 12 | 4 - HL
PR-30066 | ERCOT | 2.1 | 49 |  | DA/DW Redundancy | This project is to allow for timely disaster recovery of the Data Archive and Data Warehouse in the event of a disaster at the Taylor computing facility. It is primarily a hardware purchase. |  | 5 - L
PR-30073 | ERCOT | 2.1 | 50 | TO 4.X | Automate AS Qualification Testing | Add automation to the existing process of providing Ancillary Service Qualification testing. | Will be included in PR40001, Technical Operations Release 4.X | 6 - LL
PR-30141 | ERCOT | 2.1 | 51 |  | EMS/MMS Hardware system upgrades/replacement |  |  | 3 - M
PR-40001 | ERCOT | 2.1 | 52 | TO 4.X | Mapping voltages and flows in PI | Map voltages and line flows into PI for post mortem analysis |  | 6 - LL
PR-40001 | ERCOT | 2.1 | 53 | TO 4.X | User Interface - Human Factors Project | Improve the usability of MOI and MAI as per the recommendations of the Human Factors project |  | 5 - L
PR-40001 | ERCOT | 2.1 | 54 | TO 4.X | Enhancement to Outage Scheduler/ STNET | Add a feature to import outages on an equipment type basis from outage scheduler into STNET |  | 6 - LL
PR-40001 | ERCOT | 2.1 | 55 | TO 4.X | RMR Process Automation | Includes automation of Delivery Plan, Availability Plan, Deployment, Settlements |  | 5 - L
PR-40019 | ERCOT | 2.1 | 56 |  | Testing Website Enhancements | Transition Retail Testing Website (ETOD) support from Business to IT |  | 6 - LL
PR-40020 | ERCOT | 2.1 | 57 |  | HTTP/HTTPS for Market Certification | Provide additional data transport for the Market Certification environment |  | 6 - LL
PR-40021 | ERCOT | 2.1 | 58 |  | Settlements Data Storage | To create a stable environment to save ERCOT Settlements validation and dispute data. Reduces business exposure of inability to access data or even loss of validation and dispute data. |  | 6 - LL
PR-30163 | Market | 2.2 | 59 |  | PRR422 - OOM Zonal Dispatch Instructions | Provides details on deployment and settlement of Zonal OOME Dispatch Instructions in command and control conditions. | Market Rank - 13 | 4 - HL
PR-20157 | ERCOT | 2.2 | 60 |  | PCOOM Adjustment Requirements | A controlling function needs to be added to PCOOM calculation module. Settlements group can manually adjust the controlling function (interval data cut used as a flag) to adjust OCOOM calculations on a per interval basis. |  | 5 - L
PR-30029 | ERCOT | 2.2 | 61 |  | Overlimit Reports (O&M) | Be able to report to the ROS and PUCT the overlimit conditions that have taken place over a given period. Be able to track our performance in this respect and identify corrective actions to remedy these conditions. Meet NERC requirements |  | 5 - L
PR-30030 | ERCOT | 2.2 | 62 |  | PDC Report | ERCOT is required by protocols to analyze and report on resource response to events to the performance, Disturbance Compliance Taskforce. Provide functionality to meet this requirement. |  | 5 - L
PR-30067 | ERCOT | 2.2 | 63 | TO 4.X | BES Deployment Dependency on Resource Pln | To relax the ERCOT balancing energy deployment dependency on Resource Plan and the current SCADA information will be used in balancing energy deployment. Since the Resource Plan is operational non-binding and SCADA is more up-to-date, this project will improve the ERCOT market operational reliability considering that some participants may experience difficulty in updating their Resource Plans to reflect the actual operational status under certain conditions. The successful implementation of this project will improve the ERCOT system reliability. | Will be included in PR40001, Technical Operations Release 4.X | 4 - HL
PR-30072 | ERCOT | 2.2 | 64 | TO 4.0 | Balancing Schedule Dependency on Resource Pln | Currently balancing energy schedule is being modified by the actual capability reflected in the Resource Plan submitted by the participants. Since Resource Plan is operational non-binding and schedule is operational binding, the market and the system reliability will be improved by using the actual energy schedule from those participants who has physical resources to support their schedule activity. |  | 4 - HL
PR-30078 | ERCOT | 2.2 | 65 |  | OVOw Evaluation/Implementation | Evaluate/Implement HP OpenView Operations for Windows 7 as a service level management tool, paying close attention to the service navigator and distributed performance smart plug-in's (SPIs). |  | 5 - L
PR-30080 | ERCOT | 2.2 | 66 |  | DNS for Participant Site Failovers | ERCOT has a means by which to fail over to a different site if systems become inoperable at one site or another. This project will give market participants this ability to perform site failovers without manual intervention on ERCOT's part to facilitate this move. |  | 5 - L
PR-30081 | ERCOT | 2.2 | 67 |  | Tape Backup | Tape backup is needed for obvious reasons. We need to be able to recover from a server failure in a minimum amount of time. If the RSA and RADIUS/TACACS servers were to fail, all VPN authentications would fail. If the Syslog and CiscoWorks servers were to fail, the Network group will be incapable of monitoring events that occur with regard to equipment failure, Network attacks, etc... The tape backup would minimize the downtime needed to rebuild the key servers that drive our Network. |  | 5 - L
PR-30111 | ERCOT | 2.2 | 68 |  | Balancing Energy AS Provider Performance Report | To provide the AS performance report required by protocol |  | 5 - L
PR-40001 | ERCOT | 2.2 | 69 | TO 4.X | Improvements to VSA/DSA | Improve and automate the EMS-DCP-VSA/DSA process |  | 6 - LL
PR-40001 | ERCOT | 2.2 | 70 | TO 4.X | Line naming convention | Establish standard convention for naming transmission lines throughout ERCOT (ERCOT and TDSP) |  | 5 - L
PR-40001 | ERCOT | 2.2 | 71 | TO 4.X | System protocol violation notification application - ownership transfer | Transferring of ownership from Technical operations to IT |  | 6 - LL
PR-40022 | ERCOT | 2.2 | 72 |  | Automate sending "RMREQ`s" to Lodestar | Automate the process of creating RMR unit schedules and importing into Lodestar. This will reduce errors caused by manual intervention. |  | 5 - L
PR-40023 | ERCOT | 2.2 | 73 |  | IT Dashboard | Provide near-real time operational statistics to internal ERCOT personnel - started under ETS Phase II (Internal) |  | 5 - L
PR-40024 | ERCOT | 2.2 | 74 |  | Automate Receipt of QSE Payments in Lodestar | Automate the importation of QSE Invoice payments into Lodestar. Currently, a manual effort the requires significant coordination with IT Production to import file manually created in Settlements & Billing department. |  | 6 - LL
PR-30016 | Market | 2.3 | 75 | TO 4.X | Dynamic Ratings |  | Will be included in PR40001, Technical Operations Release 4.X; Market Rank - 14 | 5 - L
PR-40034 | Market | 2.3 | 76 |  | TX SET V2.1 | This version is still undefined. The MPs have already begun to develop change controls. | Market Rank - 15 | 3 - M
PR-40036 | Market | 2.3 | 77 |  | PRR 408 - DC Tie Transaction Accounting | Provides information to the TDSP and Market Participants for transmission billing purposes. | Per PRS:Talk to J. Galvin about moving up on priority list. Linked to PR-40001, Automate DC Tie Schedule Tracking, Priority 1.2 - Rank 21 | 6 - LL
PR-30110 | ERCOT | 2.3 | 78 |  | Replace TCH | TCH Architecture and Seebeyond product implementation have been an ongoing stability and reliability problem for ERCOT. Project is to consider re architecting or replacing the current software. |  | 3- M
PR-30028 | ERCOT | 2.3 | 79 |  | Overload Reports | Be able to report to the ROS and PUCT the overload's that have taken place over a given period. Be able to track our performance in this respect and identify corrective actions to remedy these conditions. |  | 5 - L
PR-30086 | ERCOT | 2.3 | 80 |  | Frequency Performance Metric Report | To measure the performance of the Operations department and employees on their control of regulation and balancing energy deployment. To act as a yardstick to measure improvements |  | 5 - L
PR-30087 | ERCOT | 2.3 | 81 |  | RMC Redundancy | To provide the market participants with a fully redundant report server, and minimize overall unavailability of report explorer and the package 2 API |  | 5 - L
PR-30088 | ERCOT | 2.3 | 82 |  | Change Perl Scripts to all 2 Finals/2 Trueups | The completion of this project will allow the batch to process 2 finals and 2 trueups with each batch. Experience indicates that quite often settlements has a need to run more than one final and one trueup with each batch. The current configuration does not allow that to occur. |  | 5 - L
PR-30091 | ERCOT | 2.3 | 83 |  | ercot.com and TCR Redundancy | To provide the market participants and general public a redundant environment with a near 24 hour uptime for ercot.com and TCR. |  | 5 - L
PR-30143 | ERCOT | 2.3 | 84 |  | Portfolio Management System | Extend function and capability of MS Project Server to include Portfolio Management and Reporting |  | 5 - L
PR-40001 | ERCOT | 2.3 | 85 | TO 4.X | EMMS communication overhaul | Revise and secure all real time communications |  | 5 - L
PR-40001 | ERCOT | 2.3 | 86 | TO 4.X | SPD/SFT application resilency | Create additional fault tolerance in SPD/SFT applications |  | 6 - LL
PR-40001 | ERCOT | 2.3 | 86 | TO 4.X | Eliminate EMS site dependency | Eliminate EMS.MMS and other application server dependencies during fail overs |  | 6 - LL
PR-40040 | ERCOT | 2.3 | 87 | TO 5.X | EMMS Release 5.X | Pre-nodal no-regret improvements to ERCOT Market |  | 3 - M
PR-40026 | ERCOT | 3.1 | 89 |  | ETS Data Warehouse Project | Rewrite ETS ETL processes to derive data from new archive architecture. |  | 5 - L
PR-30011 | ERCOT | 3.1 | 90 | TO 4.X | Enhance BES & RPRS Market (Step II) |  | Will be included in PR40001, Technical Operations Release 4.X | 5 - L
PR-30021 | ERCOT | 3.1 | 91 |  | Replace DSM6 and VGR Freq Recorders | Provide data for timely analyses and reports following disturbances to ERCOT Operations, Compliance and Market Participant Stakeholder Groups and be in compliance with NERC Operating Policies. |  | 5 - L
PR-30100 | ERCOT | 3.1 | 92 |  | OVPD/NDAOM Evaluation/Implementation | Evaluate/Implement OpenView Performance Diagnosis and Network Diagnostic Add-on Module for their effectiveness at understanding the network connections between any two network components. |  | 5 - L
PR-40001 | ERCOT | 3.1 | 93 | TO 4.X | Voltage Scheduler | Compute proper voltage profile for generation set point voltages to improve voltage profile for both base case as well as contingency cases |  | 6 - LL
PR-40027 | ERCOT | 3.1 | 94 |  | ETS Addition to Retail Cert Environment |  |  | 5 - L
PR-40028 | ERCOT | 3.1 | 95 |  | Batch Performance Impacted by Zonal Designations | If the Market chooses to increase the number of congestion management zones this project will investigate each Lodestar Rate Schedule/Rider/List that estimates or calculates based on zonal designation and implement code or database schema changes to minimize run time. |  | 5 - L
PR-30103 | Market | 3.2 | 96 |  | TCR Synchronization of Credit Payment with Settlement Invoices | To have one settlement statement that includes all TCRcredits at the same time and on the same form as the rest of the market participant's settlements. | Market Rank - 16 | 5 - L
PR-30012 | ERCOT | 3.2 | 97 | TO 4.X | Enhance BES & RPRS Market (Step I) |  | Will be included in PR40001, Technical Operations Release 4.X | 5 - L
PR-30104 | ERCOT | 3.2 | 98 |  | STLF and BES Offset Reports | Track STLF and BES Offset calculations for Operations Performance Measurement. Currently there is no mechanism to measure how accurate STLF and Offset values are. |  | 5 - L
PR-30105 | ERCOT | 3.2 | 99 |  | Congestion Management Reports | To verify validity of BES deployment for zonal congestion management. Currently there is no data/report to measure how well congestions are managed for operations performance metrics. |  | 5 - L
PR-30108 | ERCOT | 3.2 | 100 |  | OVIS/OVWTO Evaluation/Implementation | Evaluate/Implement OpenView Internet Services and Web Transaction Observer can provide objective, repeatable measurements of web-based transaction performance, yielding insight into the user's experience. |  | 5 - L
PR-40001 | ERCOT | 3.2 | 101 | TO 4.X | Emission Tracking Tool | Collect and track generation emission credit data from QSE that would be used in planning for dispatch by ERCOT | Review with WMS and ERCOT Planning | 6 - LL
PR-40001 | ERCOT | 3.2 | 102 | TO 4.X | Fuel Supply Tracking Tool | Collect and track fuel supply data from QSE that would be used in planning for dispatch by ERCOT | Review with WMS and ERCOT Planning | 6 - LL
PR-40029 | ERCOT | 3.2 | 103 | 3/04 | Budgeting Tool | Provide a more flexible and accurate budgeting tool that allows "what if" scenerios and that pushes budget preparation effort out to desired resources. |  | 5 - L
PR-40030 | ERCOT | 3.2 | 104 | 3Q | Real Time Credit Risk Information | Provide timely and accurate information from Lodestar to ERCOT Finance department via an automated reporting function. Reduces Market exposure to accounts that are reaching critical account receivable limits. |  | 6 - LL
PR-40031 | ERCOT | 3.2 | 105 | Q4 | Replacement of IT Sub-Systems | Potential Retail Projects impact based on architecture chosen. Existing interfaces may need to be rewritten |  | 2 - MH
PR-30018 | ERCOT | 3.3 | 106 | TO 4.X | RT Market Ramp Rate |  | Will be included in PR40001, Technical Operations Release 4.X
PR-30026 | Market | 3.3 | 107 | 2Q | PIP204/PRR283 EPS Meter Data Transmittal via extract | New section on treatment of EPS Load Data was added. A new section was drafted with reference to making consumption data available to market participants of EPS meters. Boxed until system supports it. | Market Rank - 17 | 5 - L
PR-30034 | Market | 3.3 | 108 |  | PIP128 Synchronous Condenser Compensation | No design for support of Sychronous Condenser Service. Language on payment and load uplift boxed until system supports; Reference to no compensation made in protocols. QSEWG needs to re-evaluate need. | Market Rank - 19 | 5 - L
PR-30035 | Market | 3.3 | 109 |  | PIP134 Messaging System Language Clarification | Language clarification: information is posted by ERCOT, but not using the Messaging System. Language boxed for future system support. Question for WMS: should box be removed? Posting requirement related to PIP138, PIP153 & PIP155. | Market Rank - 20 | 5 - L
PR-30022 | Market | 3.3 | 110 | 3Q | UFE Analysis Metering | To attain compliance with Protocol Section 11.5 - Unaccounted For Energy Analysis. According to Protocols Section 11.5.2.1 The cost of installing any metering solely for UFE analysis purposes will be recovered through the ERCOT System Administration Fee. Additionally, business resources are required to support the working group oversight the actual analysis, and the reporting requirements defined in Protocols 11.5. | Market Rank - 27 | 3 - M
PR-30025 | ERCOT | 3.3 | 111 | TO 4.X | Monitor A/S Performance and Freq Cntrl Algorithms | Assuming Protocol changes will direct the change, the new measure will improve performance monitoring, and lead to more accountability for QSE’s in deployment of A/S. It may also provide a means to migrate towards direct assignment of A/S costs, should ERCOT stakeholders chose to move the market in that direction. | Per PRS - At risk, 11/26/02; Will be included in PR40001, Technical Operations Release 4.X | 5 - L
PR-30037 | Market | 3.3 | 112 | TO 4.X | PIP158 Contents of Dispatch Instructions | System does not support all of the indicated contents of the systematic dispatch instruction. Language boxed for future implementation. Workaround: Provide verbal/faxed instructions; Buy more regulation; Implement voice recorders Interim Language: denote timestamp on Dispatch Instruction Discussed need for this w/QSEWG in Aug. '02. Consensus was Low Priority. System impact is on P1 XML. | Will be included in PR40001, Technical Operations Release 4.X; Market Rank - 21 | 4 - HL
PR-30038 | Market | 3.3 | 113 |  | PIP188 Forward of Meter Read Information within 4 hrs | Boxed language that requires meter read data received by ERCOT prior to midnight to be forwarded to CRs by 0400 the next day, and meter read data received by ERCOT between midnight and 0600 be forwarded to CR by noon the same day.. | This was boxed due to uncertainty around system performance. If systems can meet the timing, the language will be let out of the box. NOTE: 8/03 A PRR should be done to take this language out of the box. CFM; Market Rank - 22 | 5 - L
PR-30039 | Market | 3.3 | 114 | TO 4.X | PRR307 Controllable Resources | This Protocol revision defines Load which can provide Regulation Service. | Will be included in PR40001, Technical Operations Release 4.X; Market Rank - 23 | 4 - HL
PR-30117 | ERCOT | 3.3 | 115 |  | OVWTA Evaluation/Implement | Evaluate/Implement OpenView Web Transaction Analyzer as a facility that can track the specific components of a transaction as that transaction is processed by servers. |  | 5 - L
PR-30119 | ERCOT | 3.3 | 116 |  | High Availability Comm Apps | To upgrade and provide failover / resource sharing capability for Commercial Applications. This proposal is based on a study done by ERCOT and HP looking at replacing all current UNIX servers with latest model with load balancing in Taylor and upgraded failover in Austin. |  | 1 - H
PR-30120 | ERCOT | 3.3 | 117 |  | MOStoBE Data Recovery | Recover data for MOStoBE from Package 3. |  | 5 - L
PR-30121 | ERCOT | 3.3 | 118 |  | SIR on HEAT (Consolidated tracking tool) | This project will cover automating and creating synergy for several disparate IT processes at ERCOT. Examples of these process: SIR, SPR, CCM, Help Desk Tickets, Fast Track, PMO work flows and SCR. |  | 5 - L
PR-30123 | ERCOT | 3.3 | 119 |  | Training Registration Application Upgrade | While the development of the original Training Registration application resulted in a good, basic application, use by ERCOT and Market Participant personnel has revealed the need for new functions and for improving some existing functions. |  | 6 - LL
PR-30132 | Market | 3.3 | 120 |  | BLT OOME | PRR355 modified Protocols to provide for payment when Block Load Transfers provide OOME. Supported by ERCOT thru manual process. This project would be to automate the calculations. | Market Rank - 24 | 5 - L
PR-30133 | Market | 3.3 | 121 |  | Fix Retail XML Transaction Format to MPs | Make outward facing XML more consistent with standards across the country. (Only 2 participants currently using XML.) | Market Rank - 18 | 5 - L
PR-40032 | ERCOT | 3.3 | 122 |  | Lawson Crystal Reporting | Provide access to other organizational data, i.e., operational data. |  | 5 - L
PR-40033 | ERCOT | 3.3 | 123 |  | Blue Building Redesign & Rebuild | Blue Building Redesign & Rebuild |  | 3 - M
PR-40037 | Market | 3.3 | 124 |  | MSP Competitive Metering | To be able to handle meter service providers within the Texas market once their role has been defined and approved by the PUC | Low priority due to dependency on timing of PUCT action; Market Rank - 25 | 3 - M
PR-40039 | Market | 3.3 | 125 | With TX Nodal | Day Ahead / Forward Markets | Placeholder for potential Retail Projects impact after requirements have been further defined | Market Rank - 26 | 3 - M
PR-40018 | ERCOT | 3.3 | 126 |  | TCR - On Peak/Off Peak | Enhance the TCR program to allow it to distinguish between on and off peak TCRs. This functionality will be required when ERCOT goes to nodal. |  | 6 - LL

## Closed
Reference Number= ERCOT Project No.
Project Title= Short Description of Project
Outcomes= Business Objectives
Comments= Any additional supporting comments
Projects on this list are closed because they have been completed or cancelled (usually because they are no longer needed).
Ref. No. | Source | Priority | Rank | Target Release | Project Title | Outcomes | 2003 Expend. | Implement Date | Release | Comments | Inhouse ERCOT Comments | 2003 Expend. | Original Budget | Budget Amend | Total Budget | 2002 Expend. | Sponsor | PM | IT Del. | Business Line | Product | Date Completed | Count
501 | ERCOT |  |  |  | Package 2 Redundancy/Disaster Recovery | Provide the ability to recover essential Package 2 databases and functionality to support billing and settlements within 48 hours of a disaster | 2 - MH | 2003-05-30 | EO |  | Inflight; PR-20040/30049; 2/14/03 merged with PR-30116, add. $191K | 4054374 | 12000000 | 191000 | 12191000 | 8136626 | Grendel | Gitre | Wyatt | EO | Transactional |  | 1
20057 | ERCOT |  |  |  | Weather Redundancy Path | A new redundant weather data path needs to be built for real-time system operations. Currently, weather data is passed from P2 database. When P2 goes down, weather data will not be updated in P1. | 6 - LL | 2003-03-15 | TO 2.0 |  | Closed 3/15/03 | 39960 | 39960 |  | 39960 |  | Saathoff | Mundo | Dondetti | TO | EMS |  | 1
20078 |  |  |  |  | Market Synchronization | Address market issues resulting in an out of sync “Rep of Record” between ERCOT, TDSP, and CR systems for all ESI IDs. Make necessary corrections to ensure that >1 MW customers were switched on the correct date in January 2002. Modify current IDR validation logic to remove gap validation. |  |  |  |  | This project was approved in 2 parts: 1) $750K; 2) $26K. | 323123 | 750000 | 26000 | 776000 | 452877 | Gruber | Cohea | Tarr/ Connell | CO | Market Relationship Management |  | 1
20094 | Market |  |  |  | QSE MOS Web Enhancements | SCR 718 | 6 - LL | 2003-03-15 | TO 2.0 | Complete 4/1/03 | EMS has balance of work.1/30/03 | 50000 | 50000 |  | 50000 |  | Judice | Rector | Tamby | TO | MMS |  | 1
20111 | ERCOT |  |  |  | Transaction Pipeline Hardening Initiative | PR-20111 Hardening Initiative Includes: TCH EAI Performance/Architecture Analysis Review/Enhance TCH/Siebel Interface Scope/Implement EDI Pipeline Perform./Capacity Mgmt EDI Pipeline Infrastructure Hardening Define Transaction Hardening Model Production Support and SeeBeyond Issues Add TCH data to Archive for Queries Outbound Transaction Extract 814_20 Add Prioritization XML Verification Analyze and Fix Perl Scripts Add SNMP Traps/HP Alerts in TCH Add SNMP Traps/Alerts in Paperfree | 6 - LL | 2003-05-11 | CO |  | This project has had 3 approved portions: Initial $179K; Second $250K; Third $239K. Need a summary of the scope of this project. There are additional portions of this project that have not been approved 1/30/03 There are two additional line items on the priority list for subprojects 4 & 5 | 55098 | 668000 |  | 668000 | 612902 | Gruber | Farley | Judice | CO | Transaction Processing |  | 1
20117 | ERCOT |  |  |  | Internal Map Testing and Verification | Create a set of test scenarios and test data that ERCOT can use not only to ensure that TX V1.5 are implemented appropriately, but also to ensure that other changes to the systems are easily tested prior to implementation | 6 - LL | Completed 7/23/03 | CO |  | A scope change request has been submitted to increase the approved amount to $170K. IT is evaluating. 1/30/03 Update 072203: J. Prince will verify status and provide update | 45000 | 45000 |  | 45000 | 0 | Gruber | Prince | Farley | CO | Transaction Processing |  | 1
PR-20121 | ERCOT | 1.3 | 35 |  | Unapproved Enhancement SIRs (19 identified by SWAT Tm) | Project to address SIRs identified by the Retail SWAT teams that deal with revised system requirements and market gaps. | 4 - HL | [5 empty] | #VALUE! |  | #VALUE! |  |  | Farley |  | CO | Transaction Processing | 2002 | 3
20124 | Market |  |  |  | PUCT 24462 Performance Measures Relating to Competitive Retail Electric Market | Provide measurements on the Competitive Retail Market (e.g. # customers by class, category, CR, TDSP); Market Mechanics ( e.g. key transactions processed with/without error, measurements within/out of protocols); Customer Enrollments; Customer Billing Success Rates; and Customer Service. | 4 - HL | 2003-05-06 |  |  |  | 670000 | 670000 |  | 670000 |  |  | Diaz |  |  |  |  | 1
20125 | ERCOT |  |  | EO | Dashboard | Provide Market visibility into the volumes, success rates, error rates, performance metrics, and GAPS on the transactions processed by ERCOT. | 5 - L | Canceled | Partial scope included in ETS Phase 2; remaining scope will be reviewed and re-submitted | Portion rolled into ETS Phase II; Change Cntrl being routed with $ amount req'd for ETS added scope of Dshbd. Project Cancellation will be submitted for closing this project. 2004 IT Dashboard project will be issued 04 PR #. | 182000 | 182000 |  | 182000 | 0 |  | Diaz |  | EO 3.1 | Portal | 0 | May OC | 0
20143 | Market |  |  |  | Redevelopment of Disputes and Service Requests. | This change is a development effort to replace the Disputes and Service Request Processes on the portal. The current architecture uses the EAI-Siebel Architecture. The new development would restrict this functionality to the portal only (Cold Fusion and SQL Server 2000). | 6 - LL | Complete 4/11/03 | CO |  | Complete as of 3/5/03. Need signoff. | 19900 | 19900 |  | 19900 | 0 | Connell | Martinez/Middleton | Middleton | CO | Market Relationship Management |  | 1
20145 | ERCOT |  |  |  | Develop Plan for Build Out of Austin Facility | Work with architecture firm to provide plans and estimates for optimal build out of remaining space at Austin facilities | 6 - LL | 2003-03-31 | EO |  | Included in DR Phase I Delivery |  | 25000 |  |  | 0 | Grendel | Holt |  | EO | Facility |  | 1
PR-20156 | Market |  |  | CO 2.0 | GISB EDM 1.4 and HTTPS Market Participant Testing and Migration | The project will migrate existing Market Participants from their use of FTP to GISB EDM 1.4 or HTTPS (FTP Replacement). This will involve exchanging Technical Connectivity Worksheets, testing, and Production migration from FTP. | 5 - L | Closing Phase 6/30/2003 |  | Migration of MPs that are currently ready. Not all MPs are in this migration. |  |  | 120000 | 0 | 120000 |  | Tarr | Martinez | Tarr | CO 2.0 | Transaction Processing | 2002 | 1
PR-30002-01 | Market | 1.1 |  | CO 2.0/3.0 | Move In Move Out Enhancement Short Term/Mid-Term Solution | To provide a system and process changes necessary to support the final Move In Move Out Process as designed by the market. These changes may require architecture changes to support a 4 hour turn around requirement. | 4 - HL | Closed 6/28/03 s/t and m/t | Short Term Initiative underway - completed 6/28/03 |  | $201,807 expended | 201807 | 0 | 201807 | 0 | 201807 | 0 |  | Prince/Wingerd | CO 2.0/3.0 | Transaction Processing | Feb OC | 1
30005 |  |  |  |  | LAAR Implementation | To completely and successfully implement the Load Acting As Resource program in the ERCOT market. Currently, the Responsive Reserve Market for LaaR has been successfully launched in ERCOT. However, the LaaR participation in the following markets, Non-Spin Reserve Market, Replacement Reserve Market, Balancing Energy Market, and even Regulation Market, will need to be developed. With the successful implementation of this project the ERCOT power market will have a more developed load response program. |  | Complete as of 12/31/02 | [14 empty] | 1
30006 | ERCOT |  |  |  | Acquire/Integrate OSISoft PI Software | Provide timely analyses and reports to ERCOT Operations, Compliance and Market Participant Stakeholder Groups and be in compliance with NERC Planning Standards and Operating Policies, as required by the ERCOT Agreement with NERC. Also, provide a test bed for new measurements of ERCOT and market participant performance. Provide reports required by the ERCOT Protocols and Operating Guides | 5 - L | 2003-03-31 | TO 2.0 | Closed |  | 422000 | 422000 |  | 422000 | 0 | Grimm | Mundo/Robinson/Howard | Howard | TO | EMS |  | 1
30009 |  |  |  |  | Define VDI as Instructed Deviation | Define VDI as Instructed Deviation so that ERCOT frequency performance can better meet the NERC Operational Criteria. Currently, the ERCOT verbal dispatch instruction are not considered as instructed deviation. With implementation of this project, VDIs will be defined as instructed deviation. |  |  |  |  | 2/10/03; Functionality already in place, | [11 empty] | 1
30010 |  |  |  |  | Relaxed Balanced Schedules | Implement the relaxed balanced energy schedule in the ERCOT market. Since the current balancing energy market is designed to be an ancillary service market and it is used to maintain the system reliability, the relaxed balanced schedule may introduce a spot energy market in ERCOT. If the current balancing energy market can not satisfy this requirement from the operational perspective, a brand new spot energy market may need to be designed. The successful completion of this project will provide a solid recommendation, from the market design perspective, of the relaxed balanced schedule implementation in the ERCOT market. |  | Complete, no longer needed, 2/14/03 | [14 empty] | 1
30015 | Market | 1.2 |  |  | Improvement on BES Timing | To improve the Balancing Energy Market timing so that the market can be cleared with more accurate system information. By improving the Balancing Energy Market Clearing Timing, the balancing energy market performance will be improved and this can potentially minimize the ERCOT ancillary service requirements in achieving better social welfare. With the completion of this project, any potential price chasing activity can be minimized and the ERCOT balancing energy market performance is expected to be enhanced correspondingly. | 3 - M | Completed 6/25/03 | TO 2.1 |  |  |  | 1150000 |  |  | 0 |  |  |  | TO 2.1 | MMS |  | 1
30017 |  |  |  |  | Market Solution in Zonal BES Market | Define Market Solution concept in ERCOT Zonal BES Market. Whenever there is no Market Solution, the BES bid price shall be capped by a standard price. |  |  |  |  | PRS recommended deleting this from original list. No longer required. | [11 empty] | 1
30019 |  |  |  |  | Market Solution in AS Market | Define Market Solution concept in AS Market. Whenever there is no Market Solution, the AS bid price shall be capped by a standard price. |  |  |  |  | PRS recommended deleting this project. | [11 empty] | 1
30020 |  |  |  |  | Modify OOM tool to allow fleet deployments | Allow fleet deployment of QSE resources to control congestion in a timely manner without issuing VDI. |  |  |  |  | PRS recommended deleting this project. | [11 empty] | 1
30041 | ERCOT |  |  |  | DC Tie Modeling | Develop a new DC injection model so that DC ties are modeled correctly for every EMP function, including AGC, SCADA, RTNET and STNET. | 6 - LL |  |  |  | NOT REQUIRED; original PRI 1.1 Rank 10 |  | 25000 | [5 empty] | Jessica Bian |  |  |  | 1
30045 | ERCOT |  |  |  | Fix SCADA Transmission Alarm System | Complete the configuration of the transmission alarm system | 6 - LL | Completed 7/1/2003 | TO 2.1 |  |  |  | 89000 |  |  | 0 |  | Mundo | Boecker | TO 2.1 |  |  | 1
PR-30053 | ERCOT | 1.2 |  | TO | PRR 387 - BE Mismatch Schedules Automation | Automate and fill in the gaps to the process that performs the mismatch adjustments according to protocol that is currently a settlement manual workaround | 5 - L | 2003-09-05 |  | Original PRI 1.2 Rank 12 |  |  | 160000 | 0 | 160000 | 0 | Galvin | Troxtell | Opheim | CO 2.0 | Settlement/Billing | Jan OC | 1
PR-30057 | ERCOT | 1.3 | 36 |  | Deployment of Remote Production Support Systems | Provision of PCs and associated peripherals to ERCOT employees who support production systems from home. | 5 - L |  |  |  | Minor Capital |  | 500000 |  |  |  | Lowe |  |  | EO | Corporate | 2002 | 3
30068 |  |  |  |  | Display Print Resource Plan | Provide methodology for Day Ahead operator to see the generation pattern of the QSE's proposed resource plan and identify needed units. Provide method of providing resource plan to TO's. Allow Operator in Adjustment period to see what is planned. |  |  |  |  | 2/10/03; Will be done as internal development/maintenance. | [11 empty] | 1
20059 | ERCOT | 2002 |  | TO 2.1 | Outage Scheduler Phase 2 |  | 6 - LL | 2003-08-18 |  | Inflight. Change request submitted for $9,320. IT is evaluating whether change can be absorbed by approved budget. 1/30/03 |  | 27149 | 65000 |  | 27149 | 0 | Saathoff | Martinez/Rector | Rector | TO 2.1 | MMS | 2003-08-18 | 1
PR-30072 | ERCOT | 3.3 | 10 | TO 4.X | Balancing Schedule Dependency on Resource Pln | Currently balancing energy schedule is being modified by the actual capability reflected in the Resource Plan submitted by the participants. Since Resource Plan is operational non-binding and schedule is operational binding, the market and the system reliability will be improved by using the actual energy schedule from those participants who has physical resources to support their schedule activity. | Will be included in PR40001, Technical Operations Release 4.X |  |  |  | Move to closed sheet per team 7/10/03 |  | 1000000 |  |  |  | Joel Mickey |  |  | TO | MMS |  | 3
30089 |  |  |  |  | EMS e-Terra Archive IU | This project will move the e-Terra Archive (a.k.a. ETA or HIS) user interface to dedicated servers. Currently, the ETA and DSA functionalities are sharing the same servers. The potential exists that a non-critical function (DSA) could impair a critical function (ETA). |  |  |  |  | No longer needed. | [11 empty] | 1
30095 |  |  |  |  | System Map | Provide a way for the system operators to see the prevailing power flows across the state. |  |  |  |  | 2/10/03; Will be done as internal development/maintenance. | [11 empty] | 1
30097 |  |  |  |  | Display Coming Schedule Changes | Currently there is no quick way for operators to observe large schedule changes approaching between QSE's and Zones. Such a vision of what is coming is needed to take pro-active measures to prevent loading problems. Example - Dallas area auto loading |  |  |  |  | 2/10/03; Will be done as internal development/maintenance. | [11 empty] | 1
30098 |  |  |  |  | Provide Display for Gen Output/Limits/Monitored Pts | Replace the operator designed spreadsheet now being used by operations with a display or functionality which is supported by the IT department. |  |  |  |  | 2/10/03; Will be done as internal development/maintenance. | [11 empty] | 1
30099 | ERCOT |  |  |  | Taylor Office Complex | Analysis phase - Construct 40,000 sq/ft facility in order to provide necessary work space for ERCOT's existing workforce and future expansion. | 6 - LL | 2002-12-12 |  |  |  | 95000 | 95000 |  | 95000 | 0 | Connell | Thomas |  | EO 2.0 | Transaction |  | 1
30106 |  |  |  |  | Display PF and SCADA on Single One Line | To allow debugging of network tools. Currently identifying the differences between a power flow case and SCADA requires a laborious switching back an forth between displays |  |  |  |  | 2/10/03; Will be done as internal development/maintenance. Completed In Service Date 07/08/03 | [11 empty] | 1
30126 | Market |  |  |  | PRR369 Combined Cycle Units Settlement Aggregation | This changes the way instruction to combined cycle plants are settled to more accurately reflect the operational interdependencies of the plant technology. Prior to implementation of this, when unit specific instructions are issued to a combined cycle plant, owners move their units in tandem to achieve the resulting bus output ERCOT needs to maintain reliability. However, at settlement, the plant owner only receives payment for the portion of the instruction that was followed by the instructed unit. This is often 1/3 or ¼ the payment the generator should receive for the benefit provided to the system. Implementation of PRR369 will result in the payment to the generator based on the "bus output". | 6 - LL | Completed 8/6/03 | CO 2.0 |  |  | 100000 | 100000 |  | 100000 | 0 | Galvin | Troxtell |  | CO 2.0 | Transaction Processing |  | 1
30127 | Market |  |  |  | PRR350 Smoothing Algorithm | Changes the current smoothing algorithm. Provides improved control performance by the ERCOT control area and by a QSEs’ increased ability to follow the power schedule expected by ERCOT. | 6 - LL | 2003-04-30 | TO 2.0 | Completed |  | 80000 | 80000 |  | 80000 |  |  | Boecker, JM | Boecker, JM | TO | EMS |  | 1
30136 | ERCOT |  |  |  | GISB Changes to ETS | Provide necessary changes to ETS to identify all Market transactions submitted to ERCOT through GISB. These transactions will be available on B1, identified as GISB transactions. | 5 - L | 2003-02-26 | CO | Complete 3/12/03 |  | 193000 | 193000 |  | 193000 | 0 | Gruber | Diaz | Tarr | CO | Transaction Processing |  | 1
30145 | ERCOT |  |  |  | Oracle 9i Upgrade |  | 5 - L | 2003-05-05 | TO 2.0 | Complete 6/6/03 |  | 400000 | 400000 |  | 400000 |  | Tamby | Mundo | Howard | TO 2.0 |  |  | 1
30157 | ERCOT |  |  |  | Legal Area Expansion Project | Adds one office and three additional workspaces to the Legal Area. | 6 - LL | Completed 6/30/2003 |  | Original design provided for offices and workspce for 5 attorneys and 3 support staff. The Legal Dept has outgrown the current area. | 16000 | 16000 |  | 16000 | 0 |  |  |  | EO |  | 0 | Apr OC | 1
20060/ 30003 | Market |  |  |  | TX SET Version 1.5 | The functionality objectives of 1.5 can be categorized into three main areas: enablement of Muni/Coop participation in the market, replacement of manual work-around activities at ERCOT, and increased information sharing between all participants. | 3 - M | 2003-04-11 | CO | Complete 4/25/03 | A-Cancellations(25); B-Rejects(26); C-Move In/Out(27); D-Billing(28); E-Reports(29) G-Retail System Enhancements(31) H-Facilities & Testing(32) Texas SET 1.5(01) 2/24/03 Market Flight Test; 4/11/03 Production; Scope includes PR-30124, Amend POLR Process; 2/14/03 merged with 30003- V 1.5 2003 $ ($405K bud.), and 30137-ETS chgs to 1.5 ($30K analysis bud.) ADD. 20060A TX SET 1.5 ETS Changes ($250,222) | 3047598 | 4257000 | 685222 | 4942222 | 1894624 | Gruber | Martinez/Diaz | Farley | CO | Transaction Processing |  | 1
PR-30036 | Market | 3.3 | 48 |  | PIP138 Posting BE Forecast | Not designed to be posted publicly; reference to posting currently struck, but boxed for future implementation. In Sept. 2001, said this was no longer needed. Should the box be removed? Posting requirement related to PIP134, PIP153 & PIP155. |  | PRR392 eliminated the box from the Protocols; no longer needed | [8 empty] | 1
PR-30092 | ERCOT | 3.1 | 66 |  | ERCOT Market Structure Study | To have a complete evaluation of the current ERCOT market structure and generate one consolidated ERCOT market status report which can be used as the guidance for ERCOT, PUCT and stakeholders in future market Re-design process. This study will include: a.) ERCOT frequency control performance evaluation and suggestions. b.) ERCOT congestion management performance evaluation and suggestions. c.) The inter-relationship between the ERCOT centralized ancillary service markets and the bilateral markets between the participants. d.) Evaluation the merits and shortcomings between the ERCOT zonal, portfolio model and any proposed nodal model. e.) Evaluation of the proposals to minimize the ERCOT socialized market cost. Other related market topics can also be included in the study scope and one consolidated recommendations will be provided to support any further ERCOT market evolution activity. |  | 4 - HL |  |  | Rolled into PR-30160 Texas Nodal Market Redesign |  | 850000 | -850000 |  |  |  | Young Li |  | EO
[11 empty] | Closed TOTALS | 10022009 | [10 empty] | 45