## Slide 1: Cost-Benefit Concept Group Update
Rick Covington Vikki Gates Cuddy
January 20, 2004

## Slide 2: Accomplishments
The RFP was released on Thursday January 8th.
Sent RFP to 34 parties and posted it on the TNT web site.
Parties were given until January 13th to submit written questions to be responded to at the Pre-Bid Conference.
Received 13 notices of Intent to Bid

## Slide 3: Accomplishments
The CBCG held a Pre-Bid Conference on January 15th at the Airport Hilton Hotel.
Attendance at the Pre-Bid Conference was 28 attending in person and approximately 6 call in lines.
Eight potential bidder firms were represented in person at the conference by one or more individuals.
We responded to 65 pre-submitted questions from bidders as well as additional questions brought up during the discussion.

## Slide 4: Next Steps
Proposals are due January 27th.
The CBCG will meet the morning of January 30th to discuss change cases to be modeled.
Intent is to discuss the proposed changes cases and the process for review and approval of these cases through the Market Operations Concept Group.

## Slide 5: Next Steps - Selection Committee
The afternoon of January 30th will be meeting of the RFP Selection Committee.
The Selection Committee will discuss the proposals received and selection criteria.
The Committee will select a short list on February 3.
Short list bidders will be invited to make presentations to the Selection Committee on February 9th and 10th.

## Slide 6: Selection of Consultant
The Selection Committee will develop its recommendation by February 11th to take to the CBCG meeting on February 13th.
It is anticipated that a recommendation of the firm to conduct the study will be brought to the TNT General Session on February 18th.
The contract negotiation with the selected firm will be completed by March 3, at which time the actual study will begin.

## Slide 7
QUESTIONS ??