# NAESB EDM v1.6

# ERCOT and Market

Testing Approach Document

REVISION HISTORY

| Date | Author | Description of Revision |
| --- | --- | --- |
| 09/17/2003 | TDTWG | Original |
| 01/20/2004 | J. Kassel / J. Prince | Update testing schedules and removed migration plan into separate document |
| 02/03/2004 | TDTWG | Approved |

# NAESB EDM v1.6

# ERCOT and Market Testing Approach

# Document Purpose

The purpose of the Test Approach document is to define a detailed, comprehensive plan for controlling and testing the NAESB EDM 1.6 data transport by organizing the testing activities.  This Test Approach covers the following test phases:

- Phase 1 (ERCOT and TDSPs)

- Phase 2 (ERCOT and CRs)

- Phase 3 (TDSPs and CRs)

- Implementation Plan

# Test Approach and Implementation Dates

| Test Phase | Responsible | Dates Scheduled |
| --- | --- | --- |
| Phase 1 | ERCOT & TDSPs | Week 1: December 01, 2003 |
| Phase 2 | ERCOT & CRs | Week 1: January 05, 2004 Week 2: January 12, 2004 Week 3: January 19, 2004 |
| Phase 3 | TDSPs & CRs | Week 1: February 16, 2004 Week 2: February 23, 2004 Week 3: March 01, 2004 |
| Implementation | All | April 03, 2004 April 04, 2004 |

## Preparation:

In preparation for the NAESB EDM v1.6 market connectivity test, and to ensure that the testing times are upheld the following items will need to be completed at least one week prior to the scheduled testing date for each entity involved in the test.  Completing these items will help to ensure that each entity is ready to begin the exchange of files on their scheduled date on time.  Each entity should maintain an environment separate from their production environment for testing.

Preparation Checklist:

- Verify TCW has been received.

- Confirm TCW information.

  - This should include but not limited to Confirming Contact Information, DUNs numbers, URL, etc.

- Exchange Username and password

  - This can be done via email or telephone.

- Exchange public keys and verify key id or fingerprint.

- Verify network connectivity- Open firewall ports if necessary.

- Complete the setup of Trading Partner.

- Prepare the test data

  - It is recommended that a 997 Functional Acknowledgement for the test data that will be used in the connectivity tests to avoid any potential issues that may be caused by sending retail or wholesale transactions.

Additional key documents necessary for this project can be found on:  http://www.ercot.com/Participants/Committees/TDTWG_comm.htm

# Execution:

On the day that each entity is scheduled to test, testing must begin promptly.  Testing for each market participant will be scheduled in the morning or afternoon.  The morning schedule is identified as 8 AM CST until 11 AM CST.  The afternoon schedule is identified as 1PM CST until 4 PM CST.  The scheduled timeframes are for the execution of the test script as documented in the TDTWG NAESB EDM v1.6 Implementation Guide.  It is mandatory that all preparation work has been completed at least one week prior to the testing begin date.  Resources must be available to perform the tests in the allocated timeframe. The ERCOT Project Managers will be monitoring the progress of all testing and should be included on all correspondence. During testing the ERCOT Project Managers and project team will be receiving and reviewing all EDM responses.  These will be utilized to track individual progress throughout the testing phases.  The test script included in the implementation guide as noted above should be executed with a 997.

An example of a 997 Functional Acknowledgment transaction for use of exchange for the test as reflected in the test script is included below.

ISA*00*          *00*          *01*SENDER         *01*RECEIVER       *030908*1806*U*00401*000002389*0*T*}~

GS*FA*SENDER*RECEIVER*20030908*1806*2390*X*004010~

ST*997*23900001~

AK1*GE*25768~

AK2*814*25768001~

AK5*A~

AK9*A*1*1*1~

SE*6*23900001~

GE*1*2390~

IEA*1*000002389~

In order to utilize the example above as a test file for use in exchange please make the following modifications to the data.

- Replace the words SENDER and RECEIVER in the ISA segment with the appropriate sender and receiver ISA ID value making sure that the data field remains 15 chars long by padding spaces.

- Replace the words SENDER and RECEIVER with appropriate GS ID values in the GS Segment.

- Replace the segment, element, and sub-element delimiters if they are different from the above example with the correct delimiters.

# Issue Resolution

Process to resolve an issue is identified in the TDTWG NAESB V1.6 Project Charter.

# Coordination Schedules

Conference call schedules here.  Schedule Wed. prior to the start of each phase.  Daily conference call schedule (AM/PM) to kick off scheduled tests.

| Conference Call | Purpose | Call Date --Call Number |
| --- | --- | --- |
| Phase 1 – Testing Readiness Call | TDSPs and ERCOT to verify readiness to begin 12/01/2003 testing | 11/21/2003 – time TBD 1-888-397-4671, access code 0192185 |
| Phase I Daily Testing Calls | Two daily testing calls to initiate the schedule test between ERCOT and the designated TDSP | 12/01/2003 thru 12/04/2003 – calls 8:00 AM CST, 01:00 PM CST 1-888-397-4671, access code 0192185 Additional calls could be scheduled on an as need basis |
| Phase II Testing Readiness Call | TDSPs and CR’s to verify readiness to begin 01/05/2003 testing | 12/17/2003 – time TBD 1-888-397-4671, access code 0192185 May require follow-up on 01/02/2004 |
| Phase II Daily Testing Calls | Two daily testing calls to initiate the schedule test between ERCOT and the designated CR | 01/05/2004 thru 01/08/2004 01/12/2004 thru 01/15/2004 01/19/2004 thru 01/22/2004 – calls 8:00 AM CST, 01:00 PM CST 1-888-397-4671, access code 0192185 Additional calls could be scheduled on an as need basis |
| Phase III Testing Readiness Call | ERCOT to verify point to point, TDSPs and CR’s readiness to begin point-to-point 02/16/2003 testing | 02/11/2004 – time TBD 1-888-397-4671, access code 0192185 |

| Conference Call | Purpose | Call Date --Call Number |
| --- | --- | --- |
| Phase III Daily Testing Calls | Two daily testing calls AM and PM to initiate the schedule test between TDSPs and the designated CRs, hosted and managed by ERCOT | 02/16/2004 thru 02/20/2004 02/23/2004 thru 02/27/2004 03/01/2004 thru 03/05/2004 – calls 8:00 AM CST, 01:00 PM CST 1-888-397-4671, access code 0192185 Additional calls could be scheduled on an as need basis |
| GO-LIVE – Implementation Calls | To facilitate the final NAESB v1.6 migration for ERCOT, TDSPs and CRs and used has a mechanisms to facilitate communication for quick resolution to any migration issues. | 04/03/2004 -- three calls 8:00 AM CST, 12:00 PM CST, 05:00 PM CST Number TBD 04/04/2004 -- three calls 8:00 AM CST, 12:00 PM CST, 05:00 PM CST Number TBD |

| Sun PHASE 1 TESTING ERCOT & TDSPs | Mon | Tue | Wed December | Thu | Fri 2003 | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 E Rscr. : MP PM A: ESG PM B: ADS | 2 E Rscr. : MP AM A: Oncor AM B: CNP PM A: TNMP PM B: ECT | 3 E Rscr. : MP AM A: ADS AM B: Logica PM A: ESG PM B: ECT | 4 E Rscr. : MP AM A: Oncor AM B: CNP PM A: TNMP PM B: Logica | 5 | 6 |
| 7 WEEK RESERVED FOR REWORK | 8 | 9 | 10 | 11 | 12 | 13 |
| 14 WEEK RESERVED FOR REWORK | 15 | 16 | 17 | 18 | 19 | 20 |
| 21 | 22 | 23 | 24 | 25 | 26 | 27 |
| 28 | 29 | 30 | 31 |  |  |  |

| Sun PHASE 2 TESTING ERCOT & CRs | Mon | Tue | Wed January | Thu | Fri 2004 | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 |
| 4 | 5 E Rscr. : MP PM A: ESG PM B: ADS | 6 E Rscr. : MP AM A: ECP PM A: FCP/C PM B: ECP | 7 E Rscr. : MP AM A: ECP PM A: CNST | 8 E Rscr. : MP PM A: SPRK | 9 E Rscr. : MP AM A: RRI | 10 |
| 11 | 12 E Rscr. : MP AM A: ECT AM B: ECP PM A: RRI PM B: INTL | 13 E Rscr. : MP AM A: PGSYS SPRK AM B: TXU PM B: TXU | 14 E Rscr. : MP AM A: GME AM B: XERS PM A: GME | 15 E Rscr. : MP AM A: RRI AM B: PEGSUS PM A: INTL | 16 E Rscr. : MP AM A: TXU AM B: XERS PM A: INTL | 17 |
| 18 | 19 E Rscr. : MP PM A: RRI PM B: INTL | 20 E Rscr. : MP AM A: PGSUS PM A: XERS | 21 E Rscr. : MP AM A: RRI AM B: GME PM A: PGSUS SPRK PM B: INTL | 22 E Rscr. : MP AM A: PGSUS SPRK AM B: TXU PM B: TXU | 23 | 24 |
| 25 WEEK RESERVED FOR REWORK | 26 | 27 | 28 | 29 | 30 | 31 |

PHASE  2  TESTING (ERCOT & CRs)

6 week duration

3 weeks of initial testing

1 week for rework

2 weeks for retest

ADS – Alliance Data Systems

CNST – Constellation New Energy

ECP – EC Power Int. Inc.

ECT – ECT\Systrends

ESG – Energy Services Group

FCP/C – First Choice Power/Certain

GME – Green Mountain

INTL – Intelsys Inc.

PGSUS – Pegasus Star

RRI – Reliant Retail Services (All Reliant companies)

SPRK – Spark Energy / Firefly Powered By Spark

XERS – Xcel Energy Retail Services

AM A – 8:00 a.m. Start, ERCOT Resource A (TBD)

PM A – 1:00 p.m.  Start, ERCOT Resource A (TBD)

AM B – 8:00 a.m. Start, ERCOT Resource B (TBD)

PM B – 1:00 p.m.  Start, ERCOT Resource B (TBD)

KEY:

PHASE 3 TESTING

TDSPs & CRs

| Sun | Mon | Tue | Wed February | Thu | Fri 2004 | Sat |
| --- | --- | --- | --- | --- | --- | --- |
| 1 RESOURCES WILL BE AVAILABLE FOR ERCOT/CR RE-TEST | 2 | 3 | 4 | 5 | 6 | 7 |
| 8 RESOURCES WILL BE AVAILABLE FOR ERCOT/CR RE-TEST | 9 | 10 | 11 | 12 | 13 | 14 |
| 15 | 16 TDSPs : CRs PM Group: RRI | 17 TDSPs : CRs AM Group: TXU PM Group: TXU | 18 TDSPs : CRs AM Group: INTL PM Group: INTL | 19 TDSPs : CRs AM Group: GME PM Group: GME | 20 TDSPs : CRs AM Group: RRI | 21 |
| 22 | 23 TDSPs : CRs PM Group: ECP | 24 TDSPs : CRs AM Group: ADS PM Group: ADS | 25 TDSPs : CRs AM Group: ECT PM Group: ECT | 26 TDSPs : CRs AM Group: PGSUS SPRK PM Group: PGSUS/ SPRK | 27 TDSPs : CRs AM Group: ECP | 28 |
| 29 KEY: |  |  |  |  |  |  |

PHASE  3  TESTING (TDSPs & CRs)

6 week duration

3 weeks of initial testing

1 week for rework

2 weeks for retest

ADS – Alliance Data Systems

ECP – EC Power Int. Inc.

ECT – EcTrends Services /Systrends

GME – Green Mountain

INTL – Intelsys Inc.

PGSUS – Pegasus Star

RRI – Reliant Retail Services (All Reliant companies)

SPRK – Spark Energy  / Firefly Powered by Spark

TXU – TXU Energy Services (TXU companies)

AM Group: Oncor; TNMP; Systrends; ESG

PM Group: CNP, AEP, ADS, ERCOT*

*Only would have to retest with ERCOT if prior testing phase was missed or not completed due to re-work

| Sun PHASE 3 TESTING TDSPs & CRs (cont) | Mon | Tue | Wed March | Thu | Fri 2004 | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 TDSPs : CRs PM Group: ESG | 2 TDSPs : CRs AM Group: CNST PM Group: CNST | 3 TDSPs : CRs AM Group: XERS PM Group: XERS | 4 TDSPs : CRs AM Group: FCP/C PM Group: FCP/C | 5 TDSPs : CRs AM Group: ESG | 6 |
| 7 WEEK RESERVED FOR REWORK | 8 | 9 | 10 | 11 | 12 | 13 |
| 14 WEEK RESERVED FOR REWORK | 15 | 16 | 17 | 18 | 19 | 20 |
| 21 WEEK RESERVED FOR REWORK | 22 | 23 | 24 | 25 | 26 | 27 |
| 28 | 29 | 30 | 31 |  |  |  |

| Sun | Mon | Tue | Wed April | Thu | Fri 2004 | Sat |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 Go-LIVE (Times in CST) 07:00 AM TXN Stop 08:00 AM Con Call 12:00 PM Con Call 05:00 PM Con Call |
| 4 Go-LIVE (Times in CST) 08:00 AM Con Call 12:00 PM Con Call 05:00 PM Con Call | 5 | 6 | 7 | 8 | 9 | 10 |
| 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| 25 | 26 | 27 | 28 | 29 | 30 |  |