# TDTWG

# NAESB EDM v1.6

# ERCOT and Market

# Migration Plan

REVISION HISTORY

| Date | Author | Description of Revision |
| --- | --- | --- |
| 01/20/2004 | TDTWG / J. Kassel | Draft – removed section from original Testing Approach document to create new document |
| 01/30/2004 | Clay / Naga | Straw man for testing schedules with market |
| 02/03/2004 | TDTWG | General discussion of entire document – draft sent to TDTWG for comments by 2/11/04 |
| 03/10/2004 | TDTWG -NAESB sub-team | Addition of Pre-Migration checklist page 3 and wording changes for clarification on Migration Plan schedule page 4 |
| 03/17/2003 | TDTWG | Additional group comments and approval as Final Version |

# TDTWG NAESB EDM v1.6

# ERCOT and Market Migration Plan

# Document Purpose

The purpose of the TDTWG NAESB EDM v1.6 ERCOT and Market Implementation Plan document is to define the activities required to switch over from existing GISB v1.4 transport protocols to the new NAESB EDM v1.6 transport protocols.

The associated testing schedules were an integral part of the overall process to ensure all market participants within the Texas deregulated retail electric market could successfully transmit their retail transactions after April 3, 2004.

The market testing approach was divided into three phases as outlined below…

- Phase 1 (ERCOT and TDSPs)

- Phase 2 (ERCOT and CRs)

- Phase 3 (TDSPs and CRs)

# Testing Approach and Implementation Dates:

| Test Phase | Responsible | Dates Scheduled |
| --- | --- | --- |
| Phase 1 | ERCOT & TDSPs | Week 1: December 01, 2003 |
| Phase 2 | ERCOT & CRs | Week 1: January 05, 2004 Week 2: January 12, 2004 Week 3: January 19, 2004 |
| Phase 3 | TDSPs & CRs | Week 1: February 16, 2004 Week 2: February 23, 2004 Week 3: March 01, 2004 |
| Connectivity Testing | ERCOT, TDSPs & CRs | March 29, 2004 – April 2, 2004 |
| Implementation | All | April 03, 2004 April 04, 2004 |

Pre-Migration Plan

Preparation Checklist for NAESB EDM v1.6 Migration Activities

|  | Task | Due Date | Justification | Date Complete |
| --- | --- | --- | --- | --- |
| 1 | Production TCWs due | 03-19-04 | Critical setup information conveyed between all market participants is mandatory. Provide required information for setup ahead of the planned migration date. |  |
|  | Distribute PGP/GPG Keys |  |  |  |
| 2 | Review of Migration Plan | 03-19-04 | Review of migration plan is required for full understanding of what is needed. Without guidance a seamless integration is not possible. |  |
| 3 | Pre-Migration Readiness Conference Call –Mandatory - Call is scheduled for 2:00 pm CST | 03-22-04 | A conference call is required so that all market participants are on the same page and have full understanding of status, timelines, resources (Network Administration, Software Support, Operations) and requirements. |  |
| 4 | Network level set-up - Firewall set up if applicable - Ports must be open Web-server set-up - URL - Digital Certificate - A separate SSL Certificate is needed for Market Test and Production URLs NOTE: Refer to TDTWG NAESB EDM v1.6 Testing Document from Clay for additional issues discovered during testing | 03-26-04 | Network connectivity is the most important part of this effort. If market participants cannot simply "see" each other then this effort will be moot and cause unnecessary delays. A pre setup is necessary to make sure that the go live date will in fact happen and to make sure all network issues are resolved in advance. |  |
| 5 | Pre-Connectivity Testing (for those that are capable of performing this step) - ERCOT and Market Participants - MPs' Point - to - Point | 03-29-04 thru 04-02-04 | Ensure setup of task #4 is complete. Minimizing setup efforts required for the go-live date. A passive test - a single entity initiated test and reporting status to ERCOT. |  |
| 6 | Provide Status of Pre-Connectivity Testing to ERCOT PMs (John Kassel, jkassel@ercot.com Jill Prince, jprince@ercot.com) | 03-29-04 thru 04-02-04 | Used to follow-up with market participants that could be at risk in not meeting the migration deadline. The status report is an email to the ERCOT PMs indicating a pass / fail status with the market participant. |  |
| 7 | Final Pre-Migration Readiness Conference Call – Mandatory - Call is scheduled for 2:00 pm CST | 04-01-04 | A conference call is required to ensure final migration preparations are in progress or are complete |  |

Migration Plan

Friday, March 19th

Deadline for Production TCWs to be exchanged between all Trading Partners.

Monday, March 29th

Conduct “Server-Level” tests that are intended to ensure Firewalls are open and SSL is being used.

- Connectivity testing between MPs and ERCOT.

- No transactions will be sent

- Designed to mitigate risks during implementation

- 08:00 AM – 09:00 AM CST	Testing with ESG, ECP

- 09:00 AM – 10:00 AM CST	Testing with ECT, INTL

- 10:00 AM – 11:00 AM CST	Testing with ADS, GME

- 01:00 PM – 02:00 PM CST	Testing with RRI, XERS

- 02:00 PM – 03:00 PM CST	Testing with CNST, FCP/C

- 03:00 PM – 04:00 PM CST	Testing with TXU

Tuesday, March 30th

Conduct “Server-Level” tests that are intended to ensure Firewalls are open and SSL is being used.

- Connectivity testing between MPs and ERCOT (continued)

- No transactions will be sent

- Designed to mitigate risks during implementation

- 08:00 AM – 09:00 AM CST	Testing with TNMP

- 09:00 AM – 10:00 AM CST	Testing with Logica

- 10:00 AM – 11:00 AM CST	Testing with Oncor

- 01:00 PM – 02:00 PM CST	Testing with CNP

- 02:00 PM – 03:00 PM CST	Testing with PGSUS, SPRK

Wednesday, March 31st through Friday, April 2nd

- Point-to-Point Connectivity testing between TDSPs and CRs to continue throughout the week.  Testing should be completed by COB Friday, 4/2/04.

Saturday, April 3rd

- 12:30 AM CST Stop sending all Inbound and Outbound transactions

- All MPs and ERCOT

- 8:00 AM CST Conference call – Mandatory.

- Each party indicates they have stopped sending transactions

- ERCOT to facilitate call and perform roll call

- ERCOT to create agenda and send out for call

- Line will be open throughout the day - as needed

    - Any party with unresolved issues should contact the ERCOT Technical Assistance “Hot Line” at any time throughout the day (Conference Call Number: 888-397-4671   Pass code: 0192185)

- Conversion activities, for all MPs and ERCOT, begin and include the following steps…

- Updates respective database

- Load mailboxes with data

- Connectivity testing in Production environment using “Test 997” – following the Schedule below…

  - Ensure “Test Flag” is noted on 997 transaction – ISA15

  - Reviews response (HTTP)

--- TP activities with ERCOT will follow similar sequence of events – order is as follows…

- 08:00 AM – 09:30 AM CST	Connectivity test with	ESG, CNP, Logica, Oncor, TNMP, ECT

- 09:30 AM CST Conference Call - Mandatory

- Status Check for TDSP and ERCOT have completed testing

- All MPs must be on conference call

- Point-to-Point Connectivity Testing will take place after notification of successful completion of TDSP Testing with ERCOT.

- All connectivity testing should be completed by the scheduled 1:00 pm conference call.

- 09:30 AM – 10:30 AM CST	Connectivity test with	ECT, INTL, ECP

- 10:30 AM – 11:30 AM CST	Connectivity test with	RRI, XERS, CNST, FCP/C

- 11:30 AM – 12:30 PM CST	Connectivity test with	ADS, GME, TXU, PGSUS, SPRK

- 1:00 PM CST Conference call  - Mandatory

- All MPs must be on conference call and provide status update of connectivity testing. Connectivity activities should be complete at this time.

- 5:00 PM CST Conference call  - Mandatory

- All MPs should be on this conference call.  A “GO LIVE” time will be determined during this call.  All testing participants should have successfully completed testing with their associated trading partners by this time.  Trading partners with unresolved issues should continue resolution efforts throughout the evening.

Sunday, April 4th

- 8:00 AM CST Conference call if needed

Conference Call Number: 888-397-4671   Pass code: 0192185

| Sun | Mon | Tue |  | Wed | Thu | Fri | Sat |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 | 2 | 3 (Times in CST) 12:30 AM TXN Stop 8:00 AM Con Call 9:30 AM Con Call 1:00 PM Con Call 5:00 PM Con Call/ Go Live Decision |
| 4 (Times in CST) 8:00 AM Con Call/ Contingency Go Live Decision Note: Daylight Savings Time Begins… | 5 |  | 6 | 7 | 8 | 9 | 10 |
| 11 | 12 |  | 13 | 14 | 15 | 16 | 17 |
| 18 | 19 |  | 20 | 21 | 22 | 23 | 24 |
| 25 | 26 |  | 27 | 28 | 29 | 30 |  |

2004

April