## Slide 1: TCA/KEMA ERCOT Cost Benefit Analysis Implementation Impacts Assessment
ERCOT CBCG
April 22, 2004

## Slide 2: Topics for the Day
Review Implementation Impact Assessment Plan
Implementation Impacts Deliverables
Progress report
  Where are we today?

## Slide 3: Project Plan Review: Implementation Impacts
March: Design changes are reviewed
April: Inventory current situation
Mid April through early May:
  Assess future operational and business processes
  Identify future systems
May through Mid June: Develop detailed costs
Mid June though October: Review and finalize impacts

## Slide 4: Topics for the Day
Review Implementation Impact Assessment Plan
Implementation Impacts Deliverables
Progress report
  Where are we today?

## Slide 5: Implementation-Related Costs and Impacts
Systems Costs
Staffing
Risk Transition
Training
On-going Maintenance & Support

## Slide 6: Deliverables – Implementation Impacts
Preliminary outline and results (~summer)
Summary of Impacts Report
  Summary of costs
  Major cost drivers and cost risks
  Treatment of other major risks
  Qualitative impacts
Detailed cost spread sheets (Excel workbook format)
  For ERCOT
  For Market Participants, based on reasonable categorization of market participants

## Slide 7: Topics for the Day
Review Implementation Impact Assessment Plan
Implementation Impacts Deliverables
Progress report
  Where are we today?

## Slide 8: Progress Report: Design Changes Summary
Three Formal Changes Case to be considered
  TNT as defined in Concept (white) Papers and Draft TNT Protocols
    Well defined and documentation readily available
  Nodal Light as defined in the Change Case Summary
    Need final definition and description by April 30, 2004
  Northeast System Replication as defined in the Change Case Summary
    Need final definition and description by April 30, 2004
The “Backcast” effort has no system impacts implications

## Slide 9: Progress Report: Inventory of Current Situation (April – May)
What do we need from:
  CBCG?
  ERCOT?
  Stakeholders?
Agree on assumptions for sector list:
  Investor-Owned Utilities, Municipal Utilities, Electric Cooperatives, Independent Power Generators, Independent Power Marketers, Independent Retail Electric Providers, Consumers, ERCOT ISO, PUCT
  Categorization by participant type in each sector:
    Large Participant vs. Small Participant or;
    Find a typical representative if it exist

## Slide 10: Progress Report: Assess Business Processes (April – May)
For:
  ERCOT
  Stakeholder (by agreed upon sectors)
  PUCT
Action:
  Need to agree on suitable representative processes for each

## Slide 11: Business Processes Impacted
Pre-Day Ahead
Day Ahead
Adjustment Period
Operating Day
Real-Time
Post-Real-time Activities
Others?

## Slide 12: Impacted Business Process Sample

## Slide 13: Progress Report: Identify Future Systems (May – June)
For:
  ERCOT
  Stakeholder (by agreed upon sectors)
  PUCT
Actions:
  Initial estimates based on empirical information
  Confirmation via vendor Request for Price Information (RFI) and visits

## Slide 14: Questions?