## Slide 1
Current Market Release TX SET V2.0 / Solution to Stacking

## Slide 2
Move-In/Move-Out Market Solution to Stacking (Texas Set V.2.0)
Presented by: Glen Wingerd
Thursday, June 10th, 2004

## Slide 3: Market Coordination Team for the Solution to Stacking
Agenda
  Progress
  Next Steps

## Slide 4: Market Coordination Team for the Solution to Stacking
Progress
  All MPs progressing through Market Testing
  Changes to market reports and extracts communicated to MCT
Next Steps
  Gather baseline data for Post-Implementation Success Criteria
  Complete Market Test Flight 0504

## Slide 5: Project Overview
Summary of Changes:
Manage customer expectations by accepting and processing all valid requests.
Impact Level
Efficiency
Communication
Competition
Business Problem
Existing NFI logic forces an unreasonable amount of dependency on labor intensive workarounds.
Execution of workarounds are causing synchronization issues between market participants.
Lack of synchronization leads to improper billing and mismanagement of customer expectations
Solution
All valid transactions will be accepted and processed based on a set of market rules.
Drop notifications will be sent at a point in time where the proper recipient can be positively identified.
Rule based cancellations are sent on a pre-determined timeline with enough time for the recipient to react.

## Slide 6: Implementation Shutdown Overview
Wednesday
Midnight
Thursday
Noon
Thursday
Midnight
Friday
Noon
Friday
Midnight
6 hrs
14 hrs
6 hrs
9 hrs
1 am
9 pm
6 hrs
8 hrs
6 hrs
6 hrs
814_01, 814_10, 814_16, 814_24
814_08, 814_12, 814_18, 814_26
8 hrs
2 pm
867
7 hrs
5 pm
650_01
1 hr
Legend
CRs
ERCOT
TDSPs
= Conference Calls
814_20
9 pm
6 hrs
8 hrs
6 hrs
814_PC
2 pm
4 hrs
Initiating
5 pm
1 hr
810, 650_04

## Slide 7: Flight 0504 Update

## Slide 8: Flight 0504 Update
As of 6/2/04 (updated stats will be provided day of RMS)
Testing statistics through Day 13
Week 1 – complete
Week 2 – 97.8% complete
Through Day 13 – 95.0% complete
By RMS (6/10/04)
Two (2) stacking scripts should be complete by the market
Eight (8) non-stacking scripts should be complete by the market

## Slide 9: Flight 0504 Next Steps
By July RMS (7/15/04)
Market scheduled to be on Day 42 of Flight 0504
  The last script (STK19) should be complete on Day 42

## Slide 10: Texas Market Link – phase 2 testing

## Slide 11: TML Phase 2 Functionality
Increased Functionality for:
Find ESI ID
Find Transaction

## Slide 12: Find ESI ID Results Screens

## Slide 13: Business Process Transaction Results Single ESI IDs
Transaction Summary Portlet – Single ESI IDs

## Slide 14: TML Phase 2 Testing
ERCOT believes that the testing, which is scheduled to occur near the conclusion of Flight 0504, will allow Market Participants to test Texas Market Link phase 2 changes as well as confirm that the MIMO/TX SET 2.0 code is working through ERCOT TML.
ERCOT is asking for volunteers for testing.
Test digital certificates will be issued along with the URL for the Retail Market certification environment to conduct the testing. Testing can be executed by business users or IT resources.

## Slide 15: TML Phase 2 Testing
ERCOT will host TML phase 2 training to be held in Austin on July 16th and July 30th. Market notice for training will be sent within two weeks.
Training materials will be provided to the volunteer testers prior to the execution of the tests.
If you have questions about the training session, please contact your Retail Account Manager.
Questions related to the TML phase 2 testing should be directed to Karen Bergman or Glen Wingerd.

## Slide 16: Thank you