## Slide 1
Current Market Release TX SET V2.0 / Solution to Stacking

## Slide 2
Move-In/Move-Out Market Solution to Stacking (Texas Set V.2.0)
Presented by: Glen Wingerd
Wednesday, July 14th, 2004

## Slide 3: Market Coordination Team for the Solution to Stacking
Agenda
  Progress
  Next Steps
  Implementation Plan Review
    Shut Down Etiquette
    Conference Calls
    Start up Etiquette
    Conversion Plan
    Overview

## Slide 4: Market Coordination Team for the Solution to Stacking
Progress
  Market Testing nearly complete
  Clarifications made to Implementation Plan – distributed to RMS
Next Steps
  Gather baseline data for Post-Implementation Success Criteria
  Complete Market Test Flight 0504

## Slide 5: Project Overview
Summary of Changes:
Manage customer expectations by accepting and processing all valid requests.
Impact Level
Efficiency
Communication
Competition
Business Problem
Existing NFI logic forces an unreasonable amount of dependency on labor intensive workarounds.
Execution of workarounds are causing synchronization issues between market participants.
Lack of synchronization leads to improper billing and mismanagement of customer expectations
Solution
All valid transactions will be accepted and processed based on a set of market rules.
Drop notifications will be sent at a point in time where the proper recipient can be positively identified.
Rule based cancellations are sent on a pre-determined timeline with enough time for the recipient to react.

## Slide 6: Shut Down Etiquette
Etiquette
The shutdown times listed will be strictly adhered to.
All MPs should submit transactions well in advance of the shutdown time so that large transaction volumes are not experienced just prior to shutdown
  (i.e. if you run batch jobs, schedule them throughout the day)!!!
All MPs shall call-in to each conference call, on-time, during the implementation.
All times listed are Central Prevailing Time

## Slide 7: Conference Call Times
Wednesday July 21st 2:30 p.m.
  Review of Implementation Plan
  Address questions and issues
Wednesday July 28th 5 p.m.
  ERCOT provides quantities of initiating transactions submitted.
  CRs and TDSPs to provide status (state of systems and processing)
Thursday July 29th 9 a.m.
  ERCOT provides quantities of initiating transactions submitted and completed.
  Confirm ERCOT is not processing initiating transactions received after Thursday 1 a.m.
  CRs and TDSPs to provide status (state of systems and processing)
Friday July 30th 9 a.m.
  ERCOT provides quantities of sub -initiating txns submitted and completed.
  Confirm ERCOT is not processing sub-initiating txns rcvd after Thur 9 p.m.
  CRs and TDSPs to provide status (state of systems and processing)

## Slide 8: Conference Call Times
Friday July 30th 5 p.m.
  CRs & TDSPs to confirm 650s, 810s and 814 P-T-Ps have stopped flowing (excluding responses); Confirm all initiating transactions processed.
  ERCOT to provide status of 867 and sub-initiating transaction processing.
Saturday July 31st 9 a.m.
  ERCOT to provide status of 2.0 code migration & production verification
  TDSPs to provide status of upgrade
Saturday July 31st 7 p.m.
  ERCOT declares Go/No-Go, % complete of production verification
  CRs and TDSPs provide migration status

## Slide 9: Conference Call Times
Sunday August 1st 9 a.m.
  ERCOT declares Go/No-Go, % complete of production verification (fall-back if it can not be made Saturday at 7 pm)
  CRs and TDSPs provide migration status
Sunday August 1st 3 p.m.
  ERCOT provides time at which ERCOT will begin accepting Version 2.0 transactions
  CRs and TDSPs provide migration status
Monday August 2nd 9 a.m.
  ERCOT to discuss any post-implementation issues that have been discovered
  CRs and TDSPs provide system status
Tuesday August 3rd 9 a.m.
  ERCOT to discuss any post-implementation issues that have been discovered
  CRs and TDSPs to provide system status

## Slide 10: Start up Etiquette
Validation of 2.0 prior to resuming normal transaction volumes
  MPs that wish to do this will have to regulate the flow of transactions into and out of their system.
  ERCOT will not run special tests with MPs during the migration prior to opening the market with 2.0 functionality.
  Any responses that are not sent prior to shut-down will be sent after start-up and will be validated against Version 2.0. All stacking rules will apply.

## Slide 11: Conversion Plan
Service Orders ‘In Flight’
  All Transactions that are sent (including re-drops) and received by all market participants after the implementation of Stacking will be processed under the new Stacking rules and will use the Version 2.0 implementation guides
  Date Changes and Cancels received after the implementation of stacking on orders that were scheduled prior to implementation will be processed using the new Stacking rules
  Stacking rules that are designed to be executed at the beginning of the evaluation period or on the scheduled meter read date will be executed on orders that were scheduled prior to stacking
  For Date Changes, it will be required that for any date changes that the REP has not received a response prior to implementation of stacking, they will have to send a new date change request
  For Cancels, it will be required that for any cancels that the REP has not received a response prior to implementation of stacking, they will have to send a new cancel request

## Slide 12: Conversion Plan
Service Orders ‘In Flight’
  814_14s and 814_22s that have been sent out prior to the implementation of stacking will not be sent again during their evaluation periods.
  For Move-Ins and Move-Outs that are scheduled on the same day for the same ESI ID within 2 business days after the implementation of stacking, ERCOT will cancel the Move-Out and allow the Move-In to complete.
    Order information in the form of a spreadsheet and 814_08s for cancelled Move-Outs will be provided to affected TDSPs and REPs
    Move-Outs will be cancelled after the implementation of stacking and 814_08s will be sent to all affected parties
    Volume is expected to be around 1,000
  Once Stacking has been implemented, backdated MVIs/MVOs that are requesting a date prior to implementation of stacking will be processed using stacking rules.

## Slide 13: Conversion Plan
Service Orders ‘In Flight’
  All orders that are in a Cancel Pending state at 11:00 am on Friday will be manually cancelled by ERCOT.
    814_08s will be sent out for these orders after implementation
    The TDSPs will not be able to reject them.
    This will require a concerted effort to clean up all potential CWEs prior to implementation weekend
    Volume is expected to be around 300
  The MCT has reviewed the Option 1 Outages and has determined that implementation will have no affect on it.
  For Move-Ins with a status of Permit Pending during migration weekend, ERCOT will re-calculate the PNR expiration to be Requested Meter Read Date +20 Bus. Days. If that calculation yields a date that is less than the first business day after implementation weekend, ERCOT will default to a date that is equal to the first business day after implementation weekend.

## Slide 14: Implementation Shutdown Overview
Wednesday
Midnight
Thursday
Noon
Thursday
Midnight
Friday
Noon
Friday
Midnight
6 hrs
14 hrs
6 hrs
9 hrs
1 am
9 pm
6 hrs
8 hrs
6 hrs
6 hrs
814_01, 814_10, 814_16, 814_24
814_08, 814_12, 814_18, 814_26
8 hrs
2 pm
867
7 hrs
5 pm
650_01
1 hr
Legend
CRs
ERCOT
TDSPs
= Conference Calls
814_20
9 pm
6 hrs
8 hrs
6 hrs
814_PC
2 pm
4 hrs
Initiating
5 pm
1 hr
810, 650_04

## Slide 15: Flight 0504 Update

## Slide 16: Flight 0504 Update
As of 7/13/04
  Testing statistics through Day 35
  Weeks 1 through 8 – complete
  Week 9 – 84.6% complete (54 tasks outstanding)
  Through Day 41 – 99.9% complete (54 tasks outstanding)
  Total Flight – 99.8% complete (27,792 of 27,846)
  25 of 26 stacking scripts complete (52 tasks outstanding)
  11 of 12 non-stacking scripts complete (2 tasks outstanding)
  STK19 scheduled to complete on 7/14

## Slide 17: Flight 0504 Update
As of 7/12/04
  Currently we have tested over “616” test cases for MIMO across all applications in UAT. Of those test cases, we currently have only 6 open defects of a total of 223 logged.
To date ERCOT has identified 223 Defects
  15 – Portal
  21 – TCH/EAI
  57 – Siebel
  15 – Paperfree
  6 – ETS
  107 – Data or documentation
These defects are categorized as follows:
  107 – Documentation and Script errors or Data
  75 – Bugs (Coding errors requiring application level changes)
  21 – System or Environment related
  20 – Unknown (Root cause not reported to defect or still in analysis)

## Slide 18: Thank you

## Slide 19: Texas Market Link – phase 2 testing

## Slide 20: TML Phase 2 Functionality
Increased Functionality for:
Find ESI ID
Find Transaction

## Slide 21: TML Phase 2 Testing
Testing will begin Monday 7/12/04
Testing scheduled to conclude Friday 7/16/04
Thank you to the 10 different MP companies who volunteered. We have 32 testers from those 10 companies.
Volunteers will be assigned an ERCOT testing analyst who will be responsible for answering any questions during testing, as well as log any issues uncovered.

## Slide 22: TML Phase 2 Testing
ERCOT will host TML phase 2 training to be held in Austin on July 16th and July 30th.
If you have questions about the training session, please contact your Retail Account Manager.
Questions related to the TML phase 2 testing should be directed to Karen Bergman or Glen Wingerd.

## Slide 23: Thank you