## Issues
1 | Checklist/Tracking Tool | Susan Munson | Assigned to | Due Date | Complete | Comments
| Discuss at December 2003 | summary list of scripts for each relationship to be displayed on the checklist | J Teel |  |  | Table this item. 4/7/04 notes - 1)Need to bucket the checklist items so that someone can summarize by relationship - CR 1 / TDSP 1 - here are the 15 scripts that are being done with that relationship Refer back to a script - link on the script ID to open the page of the script.
|  | provide counts of required sent and received and actual sent and received on scripts | J Teel |  |  | keep this tabled item - the calls are going to change the format the market summary page is still there Bring up at the June TTPT meeting
|  | Add script step relationship logic whereby MP's can't check off entries when req'd predecessor script step has not been checked |  |  |  | In Review. Will not be ready for 0504.
|  | Documentation on how to use checklist and what is required to be done on checklist |  |  |  | In Review. Future checklist enhancement. Some will be done in Mkt Orientation. Documentation for take home. Help screen on checklist needs to be updated (Not priority for 0504-future enhancement). Web Conference 5/7
2 | Communication/Education | Elizabeth Moore - Documentation subteam | Assigned to | Due Date | Complete | Comments
|  | Market Orientation - improve communication lines (jen to look at notes) | Kristi and Sherri |  |  | Agenda item for March.
|  | More details of testing process for market participants | Elizabeth Moore |  |  | look at TMTP in May/June TTPT 4/7/04 - feedback - the presentations were more focused, the skit was good, best one we've had, targeted to both technical and business side of the business, wasn't overwhelming, longer meeting, but we didn't have as many people leaving early, kept their attention.
|  | Better Prepared documentation for new market participants - document created and easy to find | Elizabeth Moore |  |  | Look at TMTP in May/June TTPT New MP said it was helpful documentation/clear
|  | FAQ's updated more frequently | Julie Ballentine |  |  | Clean up of old and there is production items listed within (FasTrak?) is there a way to show the date of the item has been updated need to have a team assigned to review should we put a counter on the items to show how often the site is accessed? In a report, put a date of when they are entered - monitor before each meeting, then bring them to the meeting and answer them? Do we need a workshop to clean them up and determine how to address?
|  | Lessons Learned | Karen Bergman |  |  | Talk with Glen about a market meeting 1/2 day for MCT, 1/2 day for testing
|  | Survey - hand it out during the meeting | Sherri Slagowski
| ETOD WebSite |  | Assigned to | Due Date | Complete | Comments
|  | Clean out file Cabinet | Suzette Wilburn |  |  | In Progress
|  | Archive old data | Suzette Wilburn |  |  | In Progress
|  | review security on ETOD site - some things should be accessible by anyone | Suzette Wilburn |  |  | 4/7/04 notes - send list to Susan
|  | Update TSW testing portion of website | Susan Munson |  |  | Part of the MIMO changes 4/7/04 - grammatical errors will be fixed next time business section of the CR / CR in the market - testing a new relationship Contacts - so you see Flight test vs. Production - add Production Contacts to TSW ? Then keep the list out there with a LINK? Making some fields optional Add this to the May agenda for discussion look at how to capture Production contact information
|  | Audit trail needed on TSW |  |  |  | Deferred to after 0504
| Test Flight |  | Assigned to | Due Date | Complete | Comments | AI
|  | improve communication of testing relationships and minimize changes in testing relationships | Flight Admin |  | 06.11.04 | More for new MPs to educate on the amt of work - add to orientation. Will have a lessons learned from Flight 0504 that will be incorporated into the next Flight Test
|  | Make sure ETOD scripts and ETOD files are updated before Frame 1 | Flight Admin |  | 06.11.04 | No ETOD in 0504 - TTPT will create agenda item for future meeting to define requirements for an application that provides the same type of service as ETOD | Agenda item to discuss and define high level requirements for a testing on demand application
|  | SR file updates (maybe part of a Frame 0 step) | script subteam |  | 06.11.04 | Communicated with TDSP expectations. New files for 0504. After 0504, script subteam - do we need to keep this script? 4/7 notes - need new files from the TDSP - are people using them? There has been discussion that people are using them | Script subtream will get request to add files to the file cabinet
3 | Scripts | Jennifer Teel/Brian Shinners | Assigned to | Due Date | Complete | Comments

## Issues Completed
1 | Checklist/Tracking Tool | Susan Munson | Assigned to | Due Date | Complete | Comments
|  | Extra text on checklist - reduce amount of text |  |  | Done | In Demo phase. Will see in the next set of enhancements.
|  | support checklist items with concurrent CR's and between TDSP and CR's |  |  | Done | In Demo phase. Will see in the next set of enhancements.
|  | Add dropdown list for the exception/comment. |  |  | Done | In Demo phase. Will see in the next set of enhancements.
|  | Create new field for ESI ID |  |  | Done | In Demo phase. Will see in the next set of enhancements.
|  | Clean up Frame tables to prevent checklist entries with NO actions |  |  | Done | In Production
|  | Change checklist to allow the "Update Checklist" button to be visiable at any point on the page |  |  | Done | In Demo phase. Will see in the next set of enhancements.
|  | Add logic to highlight receiving party in a different color from the intitating party. |  |  | Done | In Demo phase. Will see in the next set of enhancements.
|  | Addd receiving party symbolic on page header next to initiating symbol |  |  | REMOVE | Have been advised this is not of concern any longer.
|  | Remove FA checkboxs. | Susan Munson |  | Done | In Production
2 | Communication/Education | Elizabeth Moore - Documentation subteam | Assigned to | Due Date | Complete | Comments
|  | Update web pages indicating the correct way to get added or removed to the List Serves (not just TTPT) | ERCOT |  | Done | Updated under all Committee & Subcommittee links. 22 in total.
|  | Testing email for questions that is monitored and responded to by test team | Sherri Slagowski |  | Complete | TTPT voted (03/03/04) that a separate inbox is not needed. General questions could be sent to TTPT list, added to TTPT agendas, to the Flight Admin or their Account Manager.
|  | testing minutes and general testing data on ERCOT website instead of ETOD (like TX SET) | Sherri Slagowski |  | Done | Find out from J Teel why this was requested. Per TTPT meeting discussion (01/07/04), do not feel this is wise. Link in Key Documents to ETOD should suffice.---Just meant the mtg minutes
| ETOD WebSite |  | Assigned to | Due Date | Complete | Comments
|  | Correct links that do not work | Suzette Wilburn |  | Done | Testing Demo as time permits.
| Test Flight |  | Assigned to | Due Date | Complete | Comments
|  | To Do list for what needs to be updated before a flight. | Flight Admin |  | Complete | KB thought this is what pre-flight timeline is for. More for orientation changes to the format of Flight 0504 & orientation have resolved this.
3 | Scripts | Jennifer Teel/Brian Shinners | Assigned to | Due Date | Complete | Comments
|  | New Format for scripts | Script Subteam |  | Done
|  | Method of updating scripts easier | Jen and Brian S |  | Complete | Currently have the ability to change scripts, but not upload new ones. Take the spreadsheets being developed & upload directly. If changes are necessary, GUI to be used to update & can be done in TTPT writing requirements now. MIMO can be loaded directly in - not manually. 4/7/04 - the work done for MIMO flight 0504 completed this item.
|  | Ability to update scripts in TTPT or script subteam | Jen and Brian S |  | Complete | Currently have the ability to change scripts, but not upload new ones. Take the spreadsheets being developed & upload directly. If changes are necessary, GUI to be used to update & can be done in TTPT writing requirements now. MIMO can be loaded directly in - not manually. 4/7/04 - concerns about version control if we had the ability to change in a meeting. Closing the item.

## Documentation Changes
issue number | person submitting | issue | document affected | resolution | notes | date added | status
1 | Chuck Moore | Direct Energy requests that the TMTP be modified so that a REP doesn't need to go through all E2E testing if their service provider has already tested. | TMTP | Issue will be addessed in new testing guidelines matrix | also see DISCUSSION recorded in Apr TTPT minutes | 2004-04-01 | WIP
2 | Sharon Polliard | Do any of you think the TMTP should be amended to have clarification that a change in a TPs already qualified business function status (ie, CSA, SO option, Outage option etc) is considered a non-emergency back end system change and should be tested during a regular scheduled test flight? | TMTP | Issue will be addessed in new testing guidelines matrix | be sure to include the Certification process impacts | 2004-04-01 | WIP
3 | Sharon Polliard | Then, is the Back-end System Change Checklist even needed? Testing and implementation plans are already a natural part of testing and implementation of the test flight changes. | TMTP - page 12 | Issue will be addessed in new testing guidelines matrix | This checklist was included in the TMTP as a guideline for MPs because TTPT can't govern what goes on behind the black curtain of the MP's gateway. | 2004-04-01 | WIP
4 | Jennifer Teel | For Example, becoming CSA certified involves testing CSA01 with only ERCOT. CSA01 involves a CR sending an 814_18, receiving an 814_19 and receiving an 814_22 and sending an 814_23. The transaction samples could satisfy the sending transactions. Also who is at risk if the CR does not get the 814_22 loaded?? | TMTP | Script subteam to determine if CSA script is adequate to test the process | Customer is at risk if no 814_22 loaded: for new construction, first time as CSA, and no energy on MVO | 2004-04-01 | WIP
5 | Jennifer Teel | Another example, a certified and production CR wants to add an additional DUNS number (same EDI, same backend system) - this usually involves connectivity, penny test, transaction samples - possibilility of RA001 or SJ351. Does this need to wait? Can we find alternatives to make this a quicker solution. | TMTP | Issue will be addessed in new testing guidelines matrix | Be sure to include the Certification process impacts. Address the different components and combinations involved. Same EDI, same backend, different banks, different Data base, differetn translator, etc | 2004-04-01 | WIP
6 | APR TTPT meeting | Scripts sub-team and Docuemenation sub-team are to correlate work on creating a matrix that spells out different scenarios requiring testing or retesting and list the specific testing requirements. This could be referenced from the TMTP instead of contained specifically in the TMTP document. This would allow easier update to the TMTP document that would not require RMS’s approval, as a change to the actual document would require. | TMTP | Create a separate matrix that will be referenced from the TMTP doc | Matrix is not meant to replace all the text sections in the TMTP document. The existing text is meant as a guideline. The matrix is meant to support and clarify the text with specific information. The documenation Sub Team will draft the matrix and spell out the scenarios and requirements. The Script sub-team will look at the scripts to see that the scripts correlate to the requirements spelled out in the matrix and are adequate to test the process. | 2004-04-19 | Documenation sub team is meeting the afternoon of May 5 to begin draft of Testing Requirements Matrix
7 | Sharon Polliard | I am thinking that the TMTP should have a link directly from the Key Documents link of the ERCOT/ RMS/ TTPT site. The only thing there now is the white paper and the address for the testing website. I know you can get it from the testing website but that is too indirect. It is a key document of the TTPT and it should be under that link. | TMTP | Suzette put request in. Link should be added by Fri Apr 23. | add a link to the TMTP under Key Documents of the ERCOT/ RMS / TTPT site | 2004-04-19 | COMPLETE
8 | Sharon Polliard | Put a space in the footer between the version and the page number. Currently displaying TMTP V1.22 OF 36 | TMTP | SIR 8867 submitted on 05/20/04. | Sherri will have updated. Submitted request to have etod updated as well as TTPT site under Key Docs. | 2004-04-21 | WIP
9 | J Teel | Pretest Activities. PowerPoint is hard to read. Possibly go back to Word document. Would prefer to see each flight as being a single sheet. |  |  | ERCOT to take action item to create the Word document. Will keep presentation version for RMS. However, Word doc will be used for posting. | 2004-05-05 | NEW