## Slide 1: ERCOT Project Process & Budgeting
Rob Connell
Director, Program Management Office
TAC Update
August 5, 2004

## Slide 2: Project Process & Budgeting
  Project Process
  Project Progress & Program Updates
  Annual Budgeting & Prioritization Key Dates
  Projects Needing Market Priority for 2005 Budget at PRS this Month
  Questions

## Slide 3: Project Management Process
Program
Management
Project
Management
Software
Development
Prioritizing
Initiating
Planning
Designing
Analyzing
Testing
Implementing
Developing
Closing
Executing & Controlling
Monitoring
Approvals
Approvals
Approvals
Approvals
Prioritizing
Initiating
Planning
Prioritization, Initiation & Planning
Deliverables and Requirements
Software Development Planning Phase
Develop Work Breakdown Structure
Project Deliverables are Defined
Business Case is Developed
Project Schedule is Developed
Detail Cost Estimates for the Project
Notes:   Again, most have seen this slide and the next.
  This slide shows a Project lifecycle in three different views
      Program Management
      Project Management
      Software Development
  The Software Development view will not be covered in this presentation.
  This slide hi-lights Prioritizing, Initiating and Planning
  Requirements, Charter, Schedule and Costs are some of the deliverables that are produced.

## Slide 4: Project Management Process
Program
Management
Project
Management
Software
Development
Prioritizing
Initiating
Planning
Designing
Analyzing
Testing
Implementing
Developing
Closing
Executing & Controlling
Monitoring
Approvals
Approvals
Approvals
Approvals
Executing
&
Controlling
Closing
Executing & Controlling
Managing People and Resources
Monitoring and Measuring
Controlling Budget
Managing Project Schedule
Managing Project Scope
Facilitating Seamless Delivery
Project Closure/Signoff
Notes:   Executing and Controlling
    Managing resources and scope & reporting status
  Closing – Bring the project to closure and get signoff from Business.

## Slide 5: System Operations Program Summary
In Progress Release 3 Resource Plan Change Indicator Resource Plan Improvement Release 4A PRR413 - Optimization for the Whole Operating Day in RPRS Procurement Process Enhancement to OOM tools for congestion management PRR423 - Dispatch of Gen Resources Below Min Operating Level PIP137/PRR211 Association of BE Bids with RPRS PRR422 - OOM Zonal Dispatch Instructions Improvements to VSA/DSA EMMS Parameters Capture for MMS Reclear Fidelity Improve Data Elements for Local Constraints & OOMs Unit Specific Bid Limits based on Generic Costs PUCT Upgrade SPD PUCT Add Corrected MCPEs to the MOS dbase and MMS OOM Participation in Providing Ancillary Services Automate the Implementation of MCSM Special Protection Schemes AS Simultaneous Selection Release 4B Outage Scheduler Dynamic Ratings Constraint Activity Manager CSC Congestion Zone Changes MOMS Enhancements Market Monitoring MOMS Phase I
SO Growth/Program Status
8
12
22
PRI 1
(31)
PRI 2
(24)
PRI 3
(15)
70
To Date
1/31/04
6/30/04
Remaining
PRI 1
(27)
PRI 2
(26)
PRI 3
(14)
40
NO PRI
(45)
107
PRI 1
PRI 2
PRI 3
NO PRI
63
Completed
2
In Planning
SCR723 Remote Access
CSC Thermal and Volt Limits Calcualtions/Posting
Automate DC TIE Schedule tracking process
Load Forecast Performance
Performance monitoring of SCADA /State Estimator
Enhancement to Outage Scheduler/ STNET
System protocol violation notification application/ownership transfer
Increase State Estimator Observability & Improve SE Response to Input Data Conditions
Performance Monitoring for ERCOT, TDSP and QSEs
LAAR /BUL Enhancements
Market Monitoring MOMS 2
Topology Estimation System

## Slide 6
Completed
Release 3
PRR424 - Elimination of Resource Specific Deployment used for Energy Purposes
Stop Oscillation of constraint management
UBES-DBES Ramp Rates
Resource Test Mode
OOME as Instructed Deviation
Archival of Shift Factors
Handling of Equipment Name Changes
CA RAP Contingency Analysis Enhancements
Canceled
Monitor A/S Performance and Freq Cntrl Algorithms - Duplicate
Enhancements to FasTrak – Duplicate
System Operations Program Summary (cont.)
SO Growth/Program Status
8
12
22
PRI 1
(31)
PRI 2
(24)
PRI 3
(15)
70
To Date
1/31/04
6/30/04
Remaining
PRI 1
(27)
PRI 2
(26)
PRI 3
(14)
40
NO PRI
(45)
107
PRI 1
PRI 2
PRI 3
NO PRI
63
Completed
In Planning
In Progress
Canceled
2

## Slide 7: Market Operations Program Summary
MO Growth/Program Status
PRI 1
(15)
PRI 2
(8)
PRI 3
(11)
PRI 1
(28)
PRI 2
(16)
PRI 3
(11)
NO PRI
(5)
7
5
10
To Date
1/31/04
6/30/04
Remaining
PRI 1
(9)
PRI 2
(7)
PRI 3
(8)
NO PRI
(4)
34
59
28
Completed
Lodestar Data Loading Improvements - 1.1
PRR371 - OOM Compensation - 1.1
Settlement Reengineering - 1.1
CASUP (Phase I) - 2.1
Oracle upgrade for L* - 2.1
TGR Trading
PRR440 Interim Removal of Market Solution
In Planning
RPRS Market Redesign – 1.1
PRR359 Improve Resource Plan – 2.2
IDR Estimation logic changes – 1.1
Q2 Enhancement SIRs – 1.1
TCR Report Enhancement – 1.2
In Progress
Q1 Enhancement SIRs – 1.1
Energy Procured from ERCOT - PRR404 – 1.1
Clarification of Ancillary Services Obligation Calculation – 1.1
SCR 725 - ERCOT Settlement Estimation – 1.3
Load Research Sampling – 1.3
Tradable Generation Rights – 1.3
CASUP Lode* 3.7 – 2.1
CASUP Oracle Upgrade – 2.1
PRR359 Improved Resource Plan – 2.2
PIP204/PRR283 EPS Meter Data – 3.3
Completed
In Planning
In Progress
9
Canceled
ERCOT Run Day Ahead Market Rule 27678 - Duplicate
IDR Estimation logic changes – Duplicate
SCR 727 ESID Service History – 1.1
Switcher Extract - 1.2
PCOOM Adjustment Requirements – 2.2
Change Perl Scripts to all 2 Finals/2 Trueups – 2.3
MOStoBE Data Recovery – 3.3
PIP204/PRR283 EPS Meter Data - Duplicate
MOStoLodeStar Re-write Testing -

## Slide 8: Retail Operations Program Summary
PRI 1
(5)
PRI 2
(5)
PRI 3
(7)
7
6
3
RO Growth/Program Status
PRI 1
(7)
PRI 2
(9)
PRI 3
(7)
NO PRI
(7)
PRI 1
(2)
PRI 2
(3)
PRI 3
(7)
NO PRI
(4)
17
32
15
1/31/04
6/30/04
Remaining
To Date
Completed
In Planning
In Progress
Completed
Competitive Metering in 2004 for Large Non-Residential Customers – 1.1
Texas Set 1.6 – 1.1
EDI Pipeline Arch & Trans – 1.1
Commercial Systems Upgrade: SeeBeyond, Paperfree and Oracle Upgrades – 2.1
810 Performance Enhancement
HTTP/HTTPS for Market Certification – 2.1
NAESB - 2.3
In Planning
Replace TCH See PR 30082 – 2.1
Enhancements to FasTrak
ETS Performance – 1.2
Siebel Upgrade – 2.1
2004 Enhancement SIRs – TS – 1.2
2004 Enhancement SIRs – ETS – 1.2
In Progress
TML Phase 1 & 2 – 1.1
MIMO – 1.1
Siebel Upgrade/Replacement - Actually CRM – 2.1
Canceled
Account Management CRM - Duplicate
Canceled
1

## Slide 9: IO/CO Program Summary
IO/CO Growth/Program Status
PRI 1
(18)
PRI 2
(15)
PRI 3
(7)
40
To Date
1/31/04
6/30/04
Remaining
PRI 1
(36)
PRI 2
(25)
PRI 3
(8)
NO PRI
(7)
76
10
0
19
Completed
In Planning
PRI 1
(16)
PRI 2
(12)
PRI 3
(6)
NO PRI
(5)
39
Completed
MS Project Phase I
EDW-Enterprise Data Warehouse
Database Management
Market Operations Test Environment
Enterprise Physical Security Remaining
Employee and Node Access System Upgrade
Taylor Blue Building Remodel
Taylor Plaza Buildout
Taylor Plaza Cardshop Buildout
SCR727 Phase IB
In Progress
EDW EMMS RSS
EDW Generic RSS to ODS Transformation
EDW Lodestar ODS
EDW EMMS ODS
IT Computing Servers and Data Storage
HW/SW; includes HP Openview
Professional Services (Labor)
Hawk/Tibco
EMMS 3.0 Hardware Change request
Data Center Upgrade and Mgmt
ITEST Buildout
EDW Phase 2
EDW Generic Data Delivery Module
NICE Playback System
New Taylor Office Complex
Austin MET 1st Floor Finish Out
Network Systems Management Software
ISO 17799 - CyberSecurity
MS Project Phase II
Console Operations Service Desk
Document Imaging system
HR System
Canceled
170 Systems Enhancements
MS Project Phase III
SIR on HEAT (Consolidated tracking tool)
3
In Progress
Canceled

## Slide 10: Overview of Project Requests
ERCOT
PMO
ERCOT
PM Process
PUCT
Market
Participants
ERCOT
Program Management Office
Overall Management of:
  Project portfolio
  Project budgets, priorities and approvals
Project Management Process
Management of:
  Project delivery
  Project resources, costs, timelines
Initiation of Project Requests
PUCT Rulings
System Change Requests (SCRs)
Protocol Revision Requests (PRRs)
Project Requests (PRs)

## Slide 11: Annual Prioritization Process
Priority categories are high, medium, and low, with subcategories of high, medium, and low, which result in the following priorities:
  High-High (1.1), High-Medium (1.2), High-Low (1.3), Medium-High (2.1), Medium-Medium (2.2), Medium-Low (2.3), Low-High (3.1), Low-Medium (3.2), Low-Low (3.3)
  High – Critical to continued operations and reliability of the market, or in response to legal requirements. (Assumes that current services or functions provided are below acceptable level.)
  Medium – Important to improve service or efficiency of operations of the market. (Assumes that the current services or functions provided are tolerable but not up to the desired state or target.)
  Low – Recommended to further automate operations or improve efficiencies of services currently provided by the market. (Assumes that the current services or functions provided are acceptable but action is needed to prevent degradation of services.)
  The subcategories (H/M/L) prioritized the projects within the category in terms of the value/impact to the market.

## Slide 12
Key Dates
Please take note of the following important dates in the 2005 prioritization process:
  8/19 – ERCOT completes internal prioritization process
  8/27 – PRS Prioritization Meeting
  September – Prioritized list goes to Finance & Audit Committee

## Slide 13: Projects Sponsored Not Initiated - SO
From SO CART – projects that will not be executed in 2004 and is sending back to the market.
  PRR307 Controllable Resources PR-30039
  PRR457 Block Deployment for Resp. & Non-spin PR-30189
  PRR496 Balancing Energy Down Requirement PR-30194
  PRR359 Improved Resource Plan PR-30131
  PRR492/513/515 Congestion Mgmt Reports PR-30105
  Entity Name Change in ERCOT
  RT Market Ramp Rate PR-30018

## Slide 14: Projects Sponsored Not Initiated - MO
From MO CART – projects that will not be executed in 2004 and is sending back to the market.
  PIP106 Direct Load Control
  PRR478 Lagged Dynamics PR-40056
  PIP128 Synchronous Condenser Compensation PR-30034
  UFE Analysis Metering PR-30022
  TCR Synchronization of Credit Payment PR-30103
      with Settlement Invoices
  BLT OOME PR-30132
  Day Ahead/Forward Market PR-40039
  PRR408 DC-TIE Transaction Accounting PR-40036
  PRR409/PIP102 Voltage Support Compensation PR-30032
  TGR (trading piece) (related to PRR397) PR-40069
  PRR426 URC for Uncontrollable Renewable PR-40057

## Slide 15
Projects Sponsored Not Initiated - RO
From RO CART – projects that will not be executed in 2004.
  PR40038–1.2 – Mass customer transition
  PR40037–3.3 – MSP competitive metering phase 2
  PR40039–3.3 – Day-ahead market (cross impact to MO)
  SCR734 – CSA Report for CRs
  PR30133–3.3 – Fix retail XML transaction format to MPs

## Slide 16
Questions?