## Slide 1
Source: Market
Program Area: SO
Project Description:
The solution will allow Transmission Providers (TSPs) to remotely and securely access STNET network study cases in the EMS component of the Market Operations Testing Environment (MOTE).
TSPs will thus be able to work in conjunction with ERCOT modeling engineers to tune the network model, enhancing its efficiency.
Initial phase of the project involves prototyping for technical feasibility and security assurance, hardware sizing validation, and definition of rollout scope.
Hardware procurement has been initiated
Initial prototyping has begun on existing hardware
Project Scope/Deliverables
Timeline
Issues / Actions
Executive Summary of Status
PR-30129 Remote Access to Study Cases
Strict dependency on the successful re-delivery of EMP 2.2.
MOTE environment unavailable for 5 weeks, due to EMP 2.2 testing in iTest, with MOTE serving to support 2.1.1 testing; this causes a gap in the delivery schedule.
Resource and environment constraints may affect delivery schedule.
Prototyping may identify lack of technical feasibility and/or security concerns, which would require an alternate technical approach. It may also identify additional hardware needs to support full rollout, necessitating additional investment or a more limited scale rollout.
PM: Shoulders
Del Mgr: Gonzalez-Perez
Activity | Estimated Completion Date | Status
Hardware/Software Procurement | 08/20/2004 | In progress
MOTE Environment Build-Out | 08/27/2004 | pending
Prototyping | 09/03/2004 | In progress
EMP 2.2 Install in MOTE and Testing | 10/29/2004 | pending
Training | 11/05/2004 | pending
Roll Out | 11/12/2004 | pending
Sponsor: Saathoff
Bus Lead: Wilkerson
Last Update
This Update
Bus Align/ Scope Risk
Technical Risk
Schedule Risk
Staffing Risk
Financial Risk
Overall
G
Y
Y
R
Y
Y
X
Updated
Y
G
Y
Status Date: 08/06/2004
Notes: DEFINITIONS AND NOTES:
Approved Budget:
- if capital budget has NOT been approved: $0
- if capital budget has been approved: $$ of capital budget approval, in as much detail as is known
Total Forecast:
- total forecast numbers to date, based on current understanding of work
-- includes change requests to date
-- if this presentation is to execute a Change Request, the Total Forecast should differ from the Approved Budget by the amount of the CR.
Committed to Date:
- total of dollars that have been committed to be spent
-- including amounts from POs already issued for HW, SW and Other
-- including labor costs for labor/contract already worked
-- excluding labor costs for labor/contract that is expected, but not yet worked
Actual to Date:
- dollar amounts that have hit the books with Finance & Accounting