## Slide 1: ERCOT Project Process
Troy Anderson
Program Management Office
DEWG Update
August 10, 2004

## Slide 2: Project Budgeting Process
  Overview of Project Requests
  Process for Market Requests
  Process for Internal ERCOT Requests
  Program Area Teams (PATS)
  Retail Program Area Information
  Annual Prioritization Process
  Questions

## Slide 3: Overview of Project Requests
ERCOT
PMO
ERCOT
PM Process
PUCT
Market
Participants
ERCOT
Program Management Office
Overall Management of:
  Project portfolio
  Project budgets, priorities and approvals
Project Management Process
Management of:
  Project delivery
  Project resources, costs, timelines
Initiation of Project Requests
PUCT Rulings
System Change Requests (SCRs)
Protocol Revision Requests (PRRs)
Project Requests (PRs)

## Slide 4: Process for Market Requests
BoD
TAC
PRS
WMS
RMS
ROS
CMWG
QSE PM WG
DS TF
TF
TX Set WG
TTPT WG
TD WG
PAR
SCR
PRR
*Subcommittee will identify if this request requires a change to protocols. If no, then submitted via SCR
*Any system change that does not require a change to the protocols will be submitted via SCR
Note:
SCRs – need to be submitted to TAC. They have to be submitted through a sub-committee.
PRRs – need to be submitted to PRS. They can be initiated from sub-committees, working committees or submitted directly to PRS (ex: from ERCOT).
Sub Committee
Working Committee

## Slide 5
Internal ERCOT Requests
Is it an enhancement?
  Improves operations
  Fulfills regulatory obligations
  Supports strategic goals/objectives
  Positive cost benefit
Complete a project request?
  Complete a request
  Obtain manager or director sponsorship
  Submit to CART for prioritization and rank
Is it a fix?
  Addresses a system error
Submit as a SIR/SPR
Submit as a project request

## Slide 6
Project Management Process
Program
Management
Project
Management
Software
Development
Prioritizing
Initiating
Planning
Designing
Analyzing
Testing
Implementing
Developing
Closing
Executing & Controlling
Monitoring
Approvals
Approvals
Approvals
Approvals
Prioritizing
Initiating
Planning
Prioritization, Initiation & Planning
Deliverables and Requirements
Software Development Planning Phase
Develop Work Breakdown Structure
Project Deliverables are Defined
Business Case is Developed
Project Schedule is Developed
Detail Cost Estimates for the Project

## Slide 7
Project Management Process
Program
Management
Project
Management
Software
Development
Prioritizing
Initiating
Planning
Designing
Analyzing
Testing
Implementing
Developing
Closing
Executing & Controlling
Monitoring
Approvals
Approvals
Approvals
Approvals
Executing
&
Controlling
Closing
Executing & Controlling
Managing People and Resources
Monitoring and Measuring
Controlling Budget
Managing Project Schedule
Managing Project Scope
Facilitating Seamless Delivery
Project Closure/Signoff

## Slide 8
ERCOT Program Area Teams
Strategic Review
Team
Strategic Team
BUS PMO IT
Continuous Analysis
& Requirements
Team
BUS PMO IT
Release Team
BUS PMO IT
Responsibilities
Communications
Prioritize program issues/impacts/
projects
Develop program goals
Monitor program performance
Prog Review
Market Subcom
Cont Req Team
Manage project requests
Coordinate requirements
Detailed impacts
Monitor protocol updates
Recommend priorities
Strategic Team
Release Core
Coordinate project teams
Assess CRs for release projects
Cont Req Team
Front-line Mgrs
Monitor requests: PUC, market, internal
Prioritize cross-functional issues
Coordinate X-functional schedules, $’s
Board
Officers
Program Area

## Slide 9
CARTs
  Continuous Analysis & Requirements Team
  SO System Operations
      Jeyant Tamby, Richard Howard
  MO Market Operations
      Betty Day, Ken Ragsdale
  RO Retail Operations
      James Cohea, Karen Bergman
  IO Infrastructure Operations
      Steve Grendel, Scott Middleton
  CO Corporate Operations
      Mike Petterson, Cheryl Yager
    Names listed are examples of regular attendees at each CART

## Slide 10
In Progress Release 3 Resource Plan Change Indicator Resource Plan Improvement Release 4A PRR413 - Optimization for the Whole Operating Day in RPRS Procurement Process Enhancement to OOM tools for congestion management PRR423 - Dispatch of Gen Resources Below Min Operating Level PIP137/PRR211 Association of BE Bids with RPRS PRR422 - OOM Zonal Dispatch Instructions Improvements to VSA/DSA EMMS Parameters Capture for MMS Reclear Fidelity Improve Data Elements for Local Constraints & OOMs Unit Specific Bid Limits based on Generic Costs PUCT Upgrade SPD PUCT Add Corrected MCPEs to the MOS dbase and MMS OOM Participation in Providing Ancillary Services Automate the Implementation of MCSM Special Protection Schemes AS Simultaneous Selection Release 4B Outage Scheduler Dynamic Ratings Constraint Activity Manager CSC Congestion Zone Changes MOMS Enhancements Market Monitoring MOMS Phase I
SO Growth/Program Status
8
12
22
PRI 1
(31)
PRI 2
(24)
PRI 3
(15)
70
To Date
1/31/04
6/30/04
Remaining
PRI 1
(27)
PRI 2
(26)
PRI 3
(14)
40
NO PRI
(45)
107
PRI 1
PRI 2
PRI 3
NO PRI
63
Completed
2
In Planning
SCR723 Remote Access
CSC Thermal and Volt Limits Calculations/Posting
Automate DC TIE Schedule tracking process
Load Forecast Performance
Performance monitoring of SCADA /State Estimator
Enhancement to Outage Scheduler/ STNET
System protocol violation notification application/ownership transfer
Increase State Estimator Observability & Improve SE Response to Input Data Conditions
Performance Monitoring for ERCOT, TDSP and QSEs
LAAR /BUL Enhancements
Market Monitoring MOMS 2
Topology Estimation System
System Operations Program Summary

## Slide 11
Completed
Release 3
PRR424 - Elimination of Resource Specific Deployment used for Energy Purposes
Stop Oscillation of constraint management
UBES-DBES Ramp Rates
Resource Test Mode
OOME as Instructed Deviation
Archival of Shift Factors
Handling of Equipment Name Changes
CA RAP Contingency Analysis Enhancements
Canceled
Monitor A/S Performance and Freq Cntrl Algorithms - Duplicate
Enhancements to FasTrak – Duplicate
System Operations Program Summary (cont.)
SO Growth/Program Status
8
12
22
PRI 1
(31)
PRI 2
(24)
PRI 3
(15)
70
To Date
1/31/04
6/30/04
Remaining
PRI 1
(27)
PRI 2
(26)
PRI 3
(14)
40
NO PRI
(45)
107
PRI 1
PRI 2
PRI 3
NO PRI
63
Completed
In Planning
In Progress
Canceled
2

## Slide 12
Market Operations Program Summary
MO Growth/Program Status
PRI 1
(15)
PRI 2
(8)
PRI 3
(11)
PRI 1
(28)
PRI 2
(16)
PRI 3
(11)
NO PRI
(5)
7
5
10
To Date
1/31/04
6/30/04
Remaining
PRI 1
(9)
PRI 2
(7)
PRI 3
(8)
NO PRI
(4)
34
59
28
Completed
Lodestar Data Loading Improvements - 1.1
PRR371 - OOM Compensation - 1.1
Settlement Reengineering - 1.1
CASUP (Phase I) - 2.1
Oracle upgrade for L* - 2.1
TGR Trading
PRR440 Interim Removal of Market Solution
In Planning
RPRS Market Redesign – 1.1
PRR359 Improve Resource Plan – 2.2
IDR Estimation logic changes – 1.1
Q2 Enhancement SIRs – 1.1
TCR Report Enhancement – 1.2
In Progress
Q1 Enhancement SIRs – 1.1
Energy Procured from ERCOT - PRR404 – 1.1
Clarification of Ancillary Services Obligation Calculation – 1.1
SCR 725 - ERCOT Settlement Estimation – 1.3
Load Research Sampling – 1.3
Tradable Generation Rights – 1.3
CASUP Lode* 3.7 – 2.1
CASUP Oracle Upgrade – 2.1
PRR359 Improved Resource Plan – 2.2
PIP204/PRR283 EPS Meter Data – 3.3
Completed
In Planning
In Progress
9
Canceled
ERCOT Run Day Ahead Market Rule 27678 - Duplicate
IDR Estimation logic changes – Duplicate
SCR 727 ESID Service History – 1.1
Switcher Extract - 1.2
PCOOM Adjustment Requirements – 2.2
Change Perl Scripts to all 2 Finals/2 Trueups – 2.3
MOStoBE Data Recovery – 3.3
PIP204/PRR283 EPS Meter Data - Duplicate
MOStoLodeStar Re-write Testing -

## Slide 13: Retail Operations Program Summary
PRI 1
(5)
PRI 2
(5)
PRI 3
(7)
6
4
4
RO Growth/Program Status
PRI 1
(7)
PRI 2
(9)
PRI 3
(7)
NO PRI
(7)
PRI 1
(2)
PRI 2
(3)
PRI 3
(7)
NO PRI
(4)
17
30
16
1/31/04
6/30/04
Remaining
To Date
Completed
In Planning
In Progress
Completed
  Competitive metering in 2004 for large non-residential customers
  Texas Set 1.6
  EDI pipeline arch and trans
  Commercial systems SeeBeyond and Paperfree Oracle upgrades
  810 performance enhancement
  NAESB 1.6
In Planning
  Replace TCH; see PR 30082
  Enhancements to FasTrak
  ETS Performance
  Siebel Upgrade
In Progress
  TML Phase 1 & 2
  MIMO
  HTTP/HTTPS for Market Certification
  Siebel Upgrade/Replacement - CRM

## Slide 14
IO/CO Program Summary
IO/CO Growth/Program Status
PRI 1
(18)
PRI 2
(15)
PRI 3
(7)
40
To Date
1/31/04
6/30/04
Remaining
PRI 1
(36)
PRI 2
(25)
PRI 3
(8)
NO PRI
(7)
76
10
0
19
Completed
In Planning
PRI 1
(16)
PRI 2
(12)
PRI 3
(6)
NO PRI
(5)
39
Completed
MS Project Phase I
EDW-Enterprise Data Warehouse
Database Management
Market Operations Test Environment
Enterprise Physical Security Remaining
Employee and Node Access System Upgrade
Taylor Blue Building Remodel
Taylor Plaza Buildout
Taylor Plaza Cardshop Buildout
SCR727 Phase IB
In Progress
EDW EMMS RSS
EDW Generic RSS to ODS Transformation
EDW Lodestar ODS
EDW EMMS ODS
IT Computing Servers and Data Storage
HW/SW; includes HP Openview
Professional Services (Labor)
Hawk/Tibco
EMMS 3.0 Hardware Change request
Data Center Upgrade and Mgmt
ITEST Buildout
EDW Phase 2
EDW Generic Data Delivery Module
NICE Playback System
New Taylor Office Complex
Austin MET 1st Floor Finish Out
Network Systems Management Software
ISO 17799 - CyberSecurity
MS Project Phase II
Console Operations Service Desk
Document Imaging system
HR System
Canceled
170 Systems Enhancements
MS Project Phase III
SIR on HEAT (Consolidated tracking tool)
3
In Progress
Canceled

## Slide 15: Annual Prioritization Process
Priority categories are high, medium, and low, with subcategories of high, medium, and low, which result in the following priorities:
  High-High (1.1), High-Medium (1.2), High-Low (1.3), Medium-High (2.1), Medium-Medium (2.2), Medium-Low (2.3), Low-High (3.1), Low-Medium (3.2), Low-Low (3.3)
  High – Critical to continued operations and reliability of the market, or in response to legal requirements. (Assumes that current services or functions provided are below acceptable level.)
  Medium – Important to improve service or efficiency of operations of the market. (Assumes that the current services or functions provided are tolerable but not up to the desired state or target.)
  Low – Recommended to further automate operations or improve efficiencies of services currently provided by the market. (Assumes that the current services or functions provided are acceptable but action is needed to prevent degradation of services.)
  The subcategories (H/M/L) prioritized the projects within the category in terms of the value/impact to the market.

## Slide 16
Key Prioritization Dates
Please take note of the following important dates in the 2005 prioritization process:
  8/19 – ERCOT completes internal prioritization process
  8/27 – PRS Prioritization Meeting
  September – Prioritized list goes to Finance & Audit Committee

## Slide 17
Questions?