## Slide 1
Current Market Release TX SET V2.0 / Solution to Stacking

## Slide 2
Move-In/Move-Out Market Solution to Stacking (Texas Set V.2.0)
Presented by: Glen Wingerd
Thursday, August 12th, 2004

## Slide 3: Market Coordination Team for the Solution to Stacking
Agenda
  Implementation
  Production Verification
  Monitoring
  Issues
  Next Steps

## Slide 4: Market Coordination Team for the Solution to Stacking
Implementation
  One ‘In Review’ transaction remained unresolved Thursday evening by the cut-off time.
  No ‘Cancel Pending’ transactions from July remained unresolved Friday noon at the cut-off time.
  One REP-initiated date change transaction did not receive a response by Friday noon at the cut-off time.

## Slide 5: Market Coordination Team for the Solution to Stacking
Production Verification
  ERCOT completed migration and began production verification at 9:30 on Saturday morning.
  21 Testers worked until 7:40 pm Saturday evening verifying the implementation.
  9 issues discovered:
    3 – data related
    3 – environment/configuration
    3 – bugs
      2 repaired on Saturday (SIRs 9043, 9054)
      1 previously identified, deferred (SIR 8898 scheduled for implementation 8/28

## Slide 6: Market Coordination Team for the Solution to Stacking
Production Verification - continued
  No issues were reported by any MPs in the 6 conference calls for shutdown leading up to the Go/No-Go call Saturday night.
  A Go was declared by all TDSPs and ERCOT on the first Go/No-Go call Saturday night.
  Transactions begin flowing in and out of ERCOT at 4:33 pm on Sunday afternoon.

## Slide 7: Market Coordination Team for the Solution to Stacking
Monitoring
  Retail Batch (new functionality with Stacking) We verified the batch ran successfully and tracked the metrics of the batch
    5 batch workflow agents processing batch records
    Running on 3 dedicated servers

## Slide 8: Market Coordination Team for the Solution to Stacking
Monitoring
Weekend batch:
Batch Start Time: 8:10 PM
Batch End Time: 10:14 PM
Total Run Time: 124 minutes
Total ESI IDs processed: 74,635
Total outbound transactions processed: 5,971
Monday Batch:
Batch Start Time: 12:02 AM
Batch End Time: 12:37 AM
Total Run Time: 35 minutes
Total ESI IDs processed: 16,301
Total outbound transactions processed: 2,861

## Slide 9: Market Coordination Team for the Solution to Stacking
Continued Monitoring
Batches
Cancels
Rejects
Throughput timings
Issues
SIRs
Monitoring parties
  EDIM
  Production Support
  Project Managers
  Release Management
  Testing

## Slide 10: Market Coordination Team for the Solution to Stacking
Issues
MOX cancels
  Missed effect of ERCOT Operating Rule #8
  Working with TDSPs for a resolution
  Caused by implementation weekend, not re-occurring
867 throughputs / NAESB outage
  Not MIMO related
  Error handling shuts down NAESB
  SIR 8952 scheduled for 8/28
TCH throughput timings
  Implementation start-up Volumes
  Continue to monitor this, expect closure by end of week
814_20 slowdown
  MIMO related issue requiring code fix
  Emergency SIR implemented 8/4

## Slide 11: Market Coordination Team for the Solution to Stacking
Issues
Timing for ERCOT Operating Rule #3 on weekends
  SIR 9052 emergency migration to production 8/4/04
814_29 invalid reject code
  SIR 9060 scheduled for implementation 8/28
Invalid segments on 814_11
  SIR 9082 scheduled for implementation 8/28
Duplicate 814_08s
  Issues with procedure for manual cancels
  Procedure has been fixed, issue closed

## Slide 12: Market Coordination Team for the Solution to Stacking
Issues
Transaction Collisions
  Transactions arriving at Siebel simultaneously on same order
  SIR 9099 scheduled for implementation 8/28
CCA code being used instead of MOX code
  The MOX cancellation includes Move-Outs ‘In Review’, but using wrong code
  SIR 9098 scheduled for implementation 9/25
824 configuration
  824s were queued for transmission, but not being sent
  Emergency SIR 9110 implemented 8/10 5:00 p.m.
814_20 responses
  1% to 9% of 814_20s not receiving responses
  Emergency SIR 9109 implemented 8/11 1:45pm

## Slide 13: Market Coordination Team for the Solution to Stacking
Next Steps
  Continue to monitor production
  Complete gathering baseline data for Post-Implementation Success Criteria
  Begin gathering Stacking data for Post-Implementation Success Criteria
    Data gathering will occur through end of September
    Data compiled and analyzed by MCT in October
    Results delivered to RMS in November

## Slide 14: Market Coordination Team for the Solution to Stacking
This project was a team effort I want to extend my sincerest gratitude to all who assisted with it’s success
In my attempt to recognize individuals who have made significant contributions, I fear that I will leave somebody out and for that I apologize in advance
The following slide lists some of the key individuals who contributed to the Stacking project through MIMO Task Force, Market Coordination Team for the Solution to Stacking, Tx SET, and TTPT.

## Slide 15: Contributor Recognition
MIMO Task Force / MCT / TTPT
Angela Hurdle
Annette Morton
Bill Bell
Bill Reily
Cary Reed
Charlie Bratton
Chris Crawford
Cory Phillips
Daryl Everett
Dave Gibson
Diana Rehfeldt
Ed Skiba
Jennifer Teel
Kris Brown
Kyle Patrick
Liz McConnell
Lora Steen
Michael Heselton
Mike Tuggle
Rick Campbell
Rita Morales
Rob Bevill
Sharon Polliard
Shelley McKain
Steve Weaver
Warren Duke
Zachary Collard
Countless Others…

## Slide 16: Contributor Recognition
ERCOT Teams
Jill Prince – IT Project Manager
Mike Lynch – IT Development Lead
Angela Martindill – Business Subject Matter Expert
EDIM (James Cohea – Manager)
TML Phase II (Dave Odle – PM)
Transaction Services (Dave Farley – Manager)
Production Support (Dave Johnson – Manager)
Retail Client Services & Testing (Karen Bergman – Manager)
The following teams at ERCOT were instrumental in the successful implementation at ERCOT

## Slide 17: Texas is Stacked! Thank you