## Slide 1
Austin, TX
August 12, 2004

## Slide 2: Discussion Topic
TX SET Version Release Schedule
RMS Assignment /Action Item Form

## Slide 3: TX SET Version Release Schedule
It was decided at the July meeting of TX SET that TX SET will release two new versions of the TX SET Implementation Guides.
  Version: TX SET 2.0A
    Implemented: November 2004
  Version: TX SET 2.1
    Implemented: December 2005

## Slide 4: Version: TX SET 2.0A
Published: Early November 2004
Implementation Date (I.D.): Late November 2004
Test Flight: TX SET does not recommend that 2.0A be associated with a Test Flight. The Change Controls associated with this release will not be impacting MPs systems, and therefore do not require testing
Contains: Gray Box and Example Changes
Market Benefit: TX SET wants to keep I.G.s clean and updated for market benefit

## Slide 5: Version: TX SET 2.0A
July
Aug
Sep
Oct
Nov
Dec
TX SET to send Market the list of “Graybox” CCs to be included in 2.0A
TX SET requesting comments from Market on “Graybox” CCs. CCs objected to by Market will be removed from 2.0A
TX SET to REDLINE 2.0A
TX SET incorporates comments to REDLINE 2.0A reissues to Market
TX SET distributes REDLINE 2.0A to the Market
TX SET produces final REDLINE 2.0A posts to website
TX SET publishes 2.0A
I.D.

## Slide 6: Version: TX SET 2.1
Published: March 2005
Implementation Date (I.D.): Early December 2005
Test Flight: 0905
Contains: Code, Gray Box, and Example Changes
Market Benefit:
  Will provide CRs with “Billing Determinants” on the 810_02 Invoice
  650_04 will have indicator requesting MVO for permanent meter removal
  814_24 will have indicator code for 2nd MVO request

## Slide 7: Version: TX SET 2.1
Jan
Feb
March
Nov
Dec
Flight 1005
TX SET to REDLINE 2.1
TX SET incorporates comments to REDLINE 2.1 reissues to Market
I.D.
TX SET distributes REDLINE 2.1 to the Market
TX SET publishes 2.0A
Market Participant system: design, build, test,
TX SET produces final REDLINE 2.1 posts to website

## Slide 8: Recommendation to RMS
TX SET recommends that RMS vote to approve the two new scheduled versions of TX SET Implementation Guides to be developed, and to approved the timeline to which they will be developed under.

## Slide 9: RMS Assignment /Action Item Form
In order to properly deliver Assignments/Action Items to Working Groups and Task Forces TX SET recommends that RMS create a standard form or form of documentation that clearly states what RMS is requesting discussion of, and what & when RMS expects to have results delivered back to the Subcommittee.
In addition, Task Force documents should have their own website and any RMS approved documents should be posted their for all Working Groups benefit.