## Slide 1: Load Research Sampling (LRS) Project Update
8/12/2004

## Slide 2: LRS PROJECT BACKGROUND
Project initiated by ERCOT/PUCT/Market in 2Q2003 with a 1.3 priority (PUCT Order 25516)
LRS project to collect and assimilate IDR information from TDSPs to create/update ERCOT settlement load profiles
LRS project to distribute IDR information to CRs and qualified MUNI/Co-Ops MASKING customer related information
ERCOT to work with Market to establish economically feasible method to develop LRS program
ERCOT working with the Market to determine sample points, replacement points, sampling procedures and processes, and data transmission/validation
ERCOT to start-up LRS project in production in 2004

## Slide 3: LRS PROJECT TIMELINE
October 2003 – February 2004
February 2004 – May 2004
May 2004 – October 2004
05/04
TDSPs starts ordering IDRs
07/04
Complete internal ERCOT testing of LRS solution
08/04
Start Pilot for TDSPs
02/04
Install Load Research Software at ERCOT
04/04
TDSPs validate samples and send installation schedules
05/04
Start receiving sample point installation data from TDSPs
10/03-12/03
TDSP and CR surveys completed and results published
10/03
Kick off meeting with Market
12/03
FTP Replacement technology agreed for data transportation mechanism
04/04
Design and select TDSPs samples
05/04
Complete Development for LRS solution at ERCOT
02/04-3/04
CR Handshake test
completed
10/03
ERCOT purchases LRS solution software
01/04
ERCOT LRS hardware set up complete
05/04-07/04
ERCOT Internal Business and System Testing
09/04
Start Pilot for CRs
10/04
Migration from Pilot to Production
10/31/04
Migration Complete, Go Live
12/03
TDSP Handshake test completed

## Slide 4: LRS PROJECT INFORMATION
Market Updates
  TDSP Installation update as of 8/2/2004
  Significant progress in LRS IDR installation has been made
  TDSPs will start submitting IDR data automatically to ERCOT once in Pilot
  ERCOT will be working with each TDSP on any Pilot related issues

## Slide 5: LRS PROJECT UPDATE
Market Updates
  TDSPs to start Pilot at the beginning of August
  TDSPs have been working with ERCOT on any sample point replacements that are required
ERCOT Updates
  Completed ERCOT internal testing
    2 months of system and business process testing
    18 Defects found and corrected
    19 additional enhancements to LRS requirements tracked
  All systems are up in Pilot and ERCOT business and IT teams will be monitoring throughout
  All LRS materials can be found on the ERCOT LRS website
    http://www.ercot.com/Participants/loadresearchsampling.htm

## Slide 6: LRS PROJECT OUTLOOK
CRs are planned to start Pilot testing in September 2004
ERCOT is planning for a 1 week outage of the LRS system in October to transition the Pilot data to Production
ERCOT is planning to have all systems up in the Production Environment by end of October

## Slide 7
Thank You