# PWG Update Report

By

Ernie Podraza

of Reliant Energy

### ERCOT PWG Chair

for

# RMS Meeting

# September 16, 2004

## Contents

- ERCOT Load Research Project Timeline.

- Annual Validation of Profile Type 2004.

- Protocols Section 18.6.5, Future IDRs Impact Analysis.

- Oil and gas properties profile change request.

- Gas/Convenience 24 hr Stores profile change request.

- PRR471 for NIDR to IDR Default Profile.

- PRR478/LPGRR2003-004 – Lagged Dynamic for new profile.

- PRR488 Weather Responsiveness Determination.

- PRR514 Twelve month Window for Non-IDR Scaling.

- PRR of Mandatory IDR Threshold Reduction.

- Annual Validation of Profile Type 2005.

- Extending ERCOT Forecasted Profiles by one additional day.

- Profile ID assignment responsibility changes

  - Next PWG Meeting 9/28

1) ERCOT Load Research Project Timeline

1. 10/23/03 Kickoff meeting with TDSPs.

2. 11/06/03 Second TDSP coordinating meeting.

3. TDSPs have agreed to use ebXML, FTP Replacement for sample data transfer in .LS format.

4. 11/26/03 CR Survey due.

5. 12/05/03 CR coordinating meeting.

6. 2/9/04 Load Research meeting was held.

7. 3/12/04 Conference call was held.

8. 3/22/04 Load Research meeting was held.

9. Sample Selection to TDSPs: Delayed due to outlier data issues. Due end of March.

10. Revised estimated sample selection acceptance by TDSPs: pending outlier issues.

11.

Estimated complete IDR sample meter installation: 6 months post sample selection acceptance by TDSPs. Estimated completion end of September 2004.

12. Sample sites selections delivered to TDSPs in April 23.

13. CR handshake testing in April complete by 14 participating CRs.

14. At the LRS 5/23 meeting provided updates on the TDSP progress on site installations and the CR .csv file format was approved.

15. Project sample sites are 31% complete as of 7/26. Completion is targeted at end of October. TDSP Pilot test to begin in Early August.

16. Project sample sites are 50% complete. Pilot test with TDSPs is ongoing.

•

• See ERCOT Report for the RMS meeting for the latest timeline and current status.

2) Annual Validation of Profile Type

1. PWG on 1/28 discussed the annual validation of profile type process.

2. PWG discussed extensively on 2/26 lessons learned from 2003.

3. Sample set of ESIID’s current usage was used to predict how many profile changes may occur during the 2004 Annual Validation. Results indicate substantially less migration, 11% Residential and 7% Business.

4. ERCOT to perform additional analysis based on many good suggestions from the PWG.

5. CNP and ERCOT staff to investigate the possible changes needed for ERCOT to assume profile id assignment responsibility from the TDSPs.

6. PWG completed on 3/23/04 discussion of issues. CNP and ERCOT to formulate a plan of action for PWG review.

7. ERCOT submitted possible actions based on the issues list ranked by the PWG priorities. CNP is to submit a plan of action for profile id assignment responsibility changes to ERCOT. Work on the issues shall continue.

8. Several issues on Annual Validation shall be discussed at the June PWG meeting. Specifically, AEP questioned whether requests for backdating

profile id changes beyond an annual re-assignment period should be

limited.

9. CNP proposed changes to profile id assignment responsibilities is being evaluated by ERCOT Staff. Surprisingly, ERCOT Staff’s preliminary analysis of profile id migration indicates that perhaps due to weather variance between 2003 and 2004 current Decision Tree cut points would yield migrations in excess of 20% for some profiles in some areas. ERCOT Staff shall be reporting on additional analysis of the cut points for the July PWG. A survey of annual validation suggested changes has been sent to the TDSPs to respond with what items are possible candidates for 2004 implementation.

10. On 7/7/04, the PWG held a conference call to discuss the anticipated quantity of profile id assignment changes for annual validation 2004.

11. At the July RMS meeting a motion was made to suspend 2004 Annual Validation that subsequently passed by a subsequent email vote.

12. At the 7/27 PWG meeting the group reviewed the language of the PRR draft sponsored by RMS to authorize the ERCOT Board and TAC subcommittees to suspend parts of the annual validation process.

13. Final lists of profile id changes are available from ERCOT staff for requesting CRs.

14. PRS on 8/26 approved urgent status for PRR534 - Temporary Modifications to the Annual Load Profile ID Assignment and Validation Process.

15. PRR534 and an RMS resolution to suspend the 2004 Annual Validation shall be on the TAC and Board September meeting agenda.

3) Protocols Section 18.6.5, Future IDRs Impact Analysis

1. Per 8/19/03 PWG meeting discussions began on compliance to Protocols Section 18.6.5.

2. Protocols 18.6.5    Future Requirements for IDRs

ERCOT and the appropriate ERCOT TAC subcommittee shall evaluate the impact of the IDR Requirement as defined in this Section for possible revision prior to the introduction of competitive metering services to the market on January 1, 2004.

3. ERCOT staff is working on comparing current IDR premises below 1000 KW versus if the premise had been on a NIDR profile as the basis of the impact study.

4. At 10/22 and 11/05 PWG meetings, part of the impact report was  presented comparing current IDRs below 1000 kW as if they had been NIDR. Remaining analysis is on schedule.

5. Outline of final analysis was reviewed at the 12/4 PWG meeting.

6. ERCOT staff began issuing the report to the PWG on 12/31/03.

7. Analysis discussed at both PWG meetings in January 2004.

8. PWG supports ERCOT to continue suggested recommendations for further analysis.

9. Estimated completion by mid May for additional analysis on recommendations 1 and 2 in the report;

a) Extend the mandatory installation analysis to a lower level (at least to 200 kW).

b) Repeat the analysis taking into consideration the impact on UFE by modifying the IDR installation and removal thresholds, and incorporating the impact of UFE allocation on the calculation of settlement cost errors.

Other recommended analysis requires the load research sample data.

9. The mid May target for the ERCOT IDR Analysis update was completed and presented at the PWG 5/22 meeting.

10. Additional analysis on this project is dependent on the collection and availability of current load research data being installed currently.

11. No Change.

4) Oil and gas properties profile change request

1. Submitted to ERCOT 3/6/03 by Pioneer Natural Resources, Priority Power Management, and Energy Data Source .

2. ERCOT to post to WEB.

3. Argument is that the aggregate profile is a very high load factor profile, close to flat.

4. ERCOT is to evaluate and submit recommendation to PWG.

5. May test the new PUCT Rule 25516 for reimbursement.

6. ERCOT shall post the methodology request to the Market Information System (MIS) and respond to the request within sixty (60) days of the posted date of the request.  This period does not include the time to analyze and render the complete assessment of the request.

7. “ERCOT withholds a decision on making a recommendation on whether to adopt or to deny adoption of the suggested profile change; instead ERCOT finds the request, as submitted, is incomplete and deficient.  The requestors are invited to address the incompleteness and deficiencies listed below and re-submit the request for further review.”

8. Per 6/19 PWG meeting, a straw-man in development for changes to the profile change request process and to allow lagged dynamic samples. PRR drafts to be reviewed at the 9/30 and 10/1 PWG meetings.

9. ERCOT staff has submitted a load research sample design to the requestor for approval.

10. PWG submitted to RMS on 11/13, PRR and LPGRR for added validation of profile change requests and lagged dynamic samples.

11. Requestor has concerns there are little CR interest in the profile.

12. Two of the Three Requestors have withdrawn from this request.

13. Sample design is being revisited using new MBSS tools.

14. No change.

5) Gas/Convenience 24 hr Stores profile change request

1. Request submitted to ERCOT by Coral Energy.

2.ERCOT staff is discussing a load research sample design with the requestor.

3.Requestor has supplied 600 of an expected 1000 ESIIDs for sample design.

4. No change.

6) PRR471 for NIDR to IDR Default Profile

1. RMS approved 9/26/2003.

2. PRS issued to market 10/09/2003 requesting a vote on urgency, comments due 10/22.

3. PRS to review 10/23.

4. To TAC 1/8/04.

5. Board approved 1/21.

6. Pending implementation into ERCOT systems.

7. Assigned project number of PR 40005 with a priority of 1.1.

8. At the PWG 7/27/04 meeting it was agreed to write a draft PRR to be reviewed to reexamine the 6 month look back period in lieu of PRR 514 approval.

9. At the PWG 8/24/04 meeting a draft PRR was approved. The draft is on the RMS 9/16/04 agenda as a voting item.

7) PRR478/LPGRR2003-004 – Lagged Dynamic for new profile

1. Approved by RMS 11/13.

2. PRS reviewed 12/18/03.

3. To TAC 2/5/04.

4. Board Approved 2/17.

5. Implementation in conjunction with the Load Research Project.

6. Pending implementation into ERCOT systems.

7. Implementation issues were discussed at the June PWG. A survey of market participant’s preferences of the PRR implementation is being conducted to the profiling exploder.

8. At the 7/27 PWG meeting the survey results were reviewed. It was agreed to review at the next PWG meeting at a high level some pros and cons for lagged dynamic profiles vs. the current static models. PWG shall provide feedback to PRS on PRR478 priority after the next PWG meeting.

9. RMS has a meeting to prioritize all outstanding projects. The PWG agreed with the RMS assignment.

8) PRR488 Weather Responsiveness Determination

1. PRR draft has been written and introduced at the 12/4 PWG mtg.

2. RMS approved in January.

3. PRS approved 2/20.

4. TAC approved April 8, 2004.

5. Board approved April 20, 2004.

6. To be implemented in ERCOT systems.

9) PRR514 Twelve month window for Non-IDR Scaling

1.PWG reviewed 7/30/03.

2.NIDR default profile settlement routine was discussed at the 9/30 and 10/22 PWG meetings. ERCOT to review possible options with the current software.

3.PRR draft discussed at PWG 12/4 meeting, and reviewed on 1/28.

4.ERCOT staff to provide supporting data for the PRR draft before final PWG approval and sending to RMS.

5.PWG reviewed ERCOT supporting data on 2/26. ERCOT to summarize the findings. PWG shall review for final approval on 3/23/04. NOTE LESS THAN 1% OF THE ESIIDS ARE BEING SETTLED ON DEFAULT NIDR PROFILES.

6.At the 3/23/04 PWG, the consensus was to monitor the decrease in population of ESIIDs. ERCOT Project 30135, Load Estimation for Settlement, targets early June for release of reports on the number of ESIIDs defaulting to scalar of 1.0. There are currently about 19,000 ESIIDs affected at final settlement.

7.In addition, the PWG did support a draft PRR to change the settlement procedure to look back 12 months for proxy data instead of the current 6 month period. The PRR shall be presented to RMS on 4/14/04.

8. PRR draft approved by RMS on 4/14/04.

9. PRS requested comments for PRR514.

10. PRS approved 5/21/04.

11. TAC approved on July 8.

12. Board approved on 7/20/04.

13. To be implemented in ERCOT systems.

10) PRR draft of Mandatory IDR Threshold Reduction

- At the 6/22/04 PWG, draft language was developed to lower the 1000 kW threshold down to 700 kW. Speed of implementation is still a consideration for the next PWG meeting.

- At the 7/27/04 PWG meeting, the original draft language was approved. However, AEP wanted a two phase in approach and CNP wanted a three phase in approach, but the majority voted for the draft language at the 700 kW level.

- Draft PRR language approved by RMS on 8/12/04. PRS assigned as PRR536. PRS to review 9/24/04.

11) Annual Validation of Profile Type 2005

- At the 7/27/04 PWG meeting, the group decided to begin an item by item review of various ideas to improve the annual validation process beginning at the next PWG meeting using the previously developed ideas and issues list already existing as a work in progress. The goal is to approve revisions this fall in time for TDSPs and ERCOT to implement into system process for the 2005 Annual Validation Year.

- At the 8/24 PWG meeting the group identified several items that are possible changes for the 2005 annual validation process. ERCOT staff shall provide additional analysis at the 9/28 PWG meeting. TDSPs are asked to evaluate the short list and estimate timelines to be discussed at the 9/28 PWG meeting as well.

12) Extending ERCOT Forecasted Profiles by one additional day

1. At the 7/27/04 PWG meeting, ERCOT Staff reported that adding one day to the number of forecasted days requires considerable system changes. The possibility shall be reviewed further when ERCOT staff has resources to pursue.

2. No Change.

13) Profile ID assignment responsibility changes

1. At the PWG 8/24/04 meeting, a draft process document by CNP and ERCOT Staff was reviewed. ERCOT Staff is to develop a flowchart of the process. Issue shall continue to be discussed in subsequent meetings.