## Slide 1: Load Research Sampling (LRS) Project Update
10/14/2004

## Slide 2: LRS PROJECT UPDATE
Market Update
  All TDSPs have successfully submitted CSV and LS data to LRS Pilot system, and most are continuing to submit data as frequently as a daily basis
  TDSPs have all started to work on systems to automate transfer of meter reading information (LS) either batched once a week/month or on meter read cycle date.
  TDSP have had a couple of issues resolved recently:
    Multiple IDRs on the same sample point
      AEP helped with standardizing a methodology for all TDSPs on how to produce a LS file that did not have skewed data. Resolution was the multiplier has to be the same for all IDRs on the single sample point
    Replacement Meter Reading information is difficult to separate within a LS transfer file for TDSPs
      ERCOT mentioned that it will take the ownership of separating replacement meter reading data in the TDSP transfer files.
  Continue to have Tuesday morning LRS status conference call to address any issues.

## Slide 3: LRS PROJECT UPDATE
Market Updates
  TDSP Installation update as of 10/1/2004
  Significant progress in LRS IDR installation, previous report period at ~50%
  TDSPs surpassed 70% installation milestone
  Sharyland and CNP completed with installations (11 of CNP sample points were not in safe locations and did not have IDR replacement samples)

## Slide 4: LRS PROJECT UPDATE
ERCOT Updates
  Still no significant issues in Pilot to date
    Build out of production environment is on schedule and should be ready for cut-over at the end of this month
    1 minor release scheduled for next week to help read database, low risk to project
  ERCOT to publish files for CRs this week and help CRs get up to speed