## Slide 1: Flight 0904 Update

## Slide 2: Flight 0904 Update
Flight manifest
13 New REPs are scheduled to test in 0904
7 Existing REPs testing in new territories
3 Existing REPs testing for DNP
2 Existing REPs testing for Bank changes
2 Existing REPs testing for change in EDI Provider

## Slide 3: Flight 0904 Next Steps
Pre Flight Check
All Pre-Flight activities were complete on schedule by 9/9/04
Flight Takeoff
Flight kicked off on schedule Monday 9/13/04
Cruising Altitude
Progress As of 10/5/04 (Day 17 of Flight 0904)
67.3% complete by task count
No scripts have required re-start
Currently 71 Point to Point transactions outstanding through Day 17
All transactions in and out of ERCOT complete through Day 17

## Slide 4: Flight 0904 Next Steps
Final Approach
By October RMS (10/14/04)
Market scheduled to be on Day 24 of Flight 0904
  12 total scripts
  Five (5) scripts should be complete by the market
By November RMS (11/11/04)
Market scheduled to be on Day 44 of Flight 0904
  The last script (STK23) should be complete on Day 31
Landing
Flight is expected to complete on time as scheduled with all testing completed successfully