## Master
MARKET METRICS CHANGE CONTROL LOG
Change Control Number | Date Submitted to MMWG | Description | Requestor | Company | Date of MMWG Approval | MMWG Website Update Date
MMCR 2004-001 | 8/20/04 | MIMO Stacking Solution causes the calculation of In Protocol of the 814_02 and 814_03 related to a switch and the 814_17 and 814_03 related to a move in to change because of the retry queue process. This change documents the calculation made by the ETS in determining whether a transaction is processed within the specified protocol timeframe. | Mike McCarty | ERCOT | 2004-08-20 | 2004-08-23
MMCR 2004-002 | 8/20/04 | PIP 188 was implemented in the MIMO 2.0 Stacking Implementation; PIP 188: Meter read data received by ERCOT prior to 0000 (midnight) will be forwarded to CRs by 0400 the next day. Meter read data received by ERCOT between 0000 (midnight) and 0600 will be forwarded to CRs by 1200 (noon) the same day. The Protocol calculation is set to 4 hours which produces the most conservative reporting calculation | Mike McCarty | ERCOT | 2004-08-20 | NA
MMCR 2004-003 | 9/2/2004 | Add a column in the Protocol Calculation Table that references the Performance Measures Row. This will allow for quick reference between the two documents. | Johnny Robertson | TXU ES | 2004-09-29 | 2004-10-01