## 2004 Open Action Items
Meeting Month | Sponsor | Issue | Action Item | Resolution | Status | Date
June-08-2004 | Leadership | Email Notification from MMWG member | o Leadership was requested to send out draft Meeting Minutes and Agenda to marketmetrics@lists.ercot.com at least 2-weeks prior to MMWG meeting. | On-going | Open
June-08-2004 | Leadership | Email Notification from MMWG member | o Leadership was requested to provide the Market with Working group procedures either in draft form and again later in final approved version via email to marketmetrics@lists.ercot.com at least 2-weeks prior to MMWG meeting. | On-going | Open
June-08-2004 | Leadership | Notification of meetings and agenda need to be sent to the Market early enough to allow for travel and meeting scheduling | o Notification to schedule meetings should be sent to the Webmaster for ERCOT posting on meeting calendar, as well as, copy request to Denise Taylor dtaylor@ercot.com and Mike McCarty mmccarty@ercot.com for ERCOT follow-up. Leadership must provide | On-going | Open
June-08-2004 | MMWG | MMWG should communicate with MCT to coordinate what reporting requirements will be needed for pre- and/or post MIMO Implementation | Kyle Patrick, Denise Taylor, and Jamie Lavas will represent MMWG at the MCT meetings and have agreed to provide MMWG with meeting updates | Mike McCarty coordinated with Glen Wingerd to meet with MMWG on MCT reporting requirements current and future. 08/20/2004 - Follow-up Post MIMO - Repoting Requirements were discussed at this meeting. (see next item on this same subject) | Open
Aug-20-2004 | MMWG | Group discussed whether this team is appropriate place for determining if the 48 hour re-try should be cut back to 31 hours. | It was determined that TX SET would be the more appropriate place for this type of discussion, but that the MMWG would provide statistics to help assist Texas SET in determining if there is a need to cut back the hours | MCT will actually be reviewing this item for the next 3 months. After 3 months if there has been no change and no recommendation will be made, MMWG will review after MCT analysis | Open
Aug-20-2004 | MMWG | Draft RMG Change Request to add test to the guide regarding the PUCT reporting of diconnect and reconnects per calendar month | D, McKeever Request RMGR for Disconnect/Reconnect Reporting |  | Open
Aug-20-2004 | MMWG | Get a list of Retailers that have the high number of zip code rejects and educate on the tools available for determing zip code for a premise | J. Lavas to work with Mike McCarty to get a list of Retailers that have the high number of zip code rejects and educate on the tools available for determing zip code for a | 09/29/04 - Mike McCarty will provide MMWG with ZIP Code ERROR report analysis providing total number of transactions for that particular month for comparion 10/19/2004 - ERCOT will get individual CR lists and work with the Retail Client Services. These numbers may be the result of a timing issue of getting zip codes updated with an 814_20 processed and posted in time.
Sept-29-2004 | RMS Request | MMWG Review RMS Assignment Form and offered comments | Kathy Scott will schedule a meeting and/or conference call with Karen Farley, chair(s) and vice chair(s) of working groups and taskforce to discuss comments and next steps fror RMS Assignment Form document before presenting to RMS | On-going | Open
Oct-19-2004 | MMWG | MMWG will need to submit a Retail Market Guide Change Request to add MMWG Working Group Procedures. Currently there are no mention on the Market Metrics Working Group in the Retail Market Guide documentation | Kathy Scott will make the changes to our current Market Metrics Group Procedures document as recommended by MMWG and distribute via email to the team for comments. The final result will be a Retail Market Guide Chage Requst submission to RMS as for inclu | 11/18/2004 - Pam Wheat asked if the team thought including the different filing requirements fro the different prjects Market Metrics is responsible for monitoring. Robert Manning (Staff) noted that there is an appendix at the end of the PUCT substative | Open
Nov-18-2004 | MMWG | 3rd Quarter Report Review | ERCOT to Review 3rd Quarter Overall Performance Metrics Report | Reviewed and will submit to RMS for Market Communications | Open
Nov-18-2004 | MMWG | Mike McCarty proposed that the cancelled report to include an additional column reflecting that they type of service order and cancel. | MMWG will bring to RMS this suggestion of adding this infornation to the query with an estimated implementation date. A Change Control Request form will be created to request this reporting enhancement. Mike McCarty will also inlcude which orders are |  | Open
Nov-18-2004 | MMWG | The PUCT can't use some of the metrics becausde of inconsistency in the way they are reported. Trying to accomplish definitions to provide consistency. Some definitions are not clear as they are defined in the Rule. | PUCT Staff (Robert Manning) would like all the CRs on the same page with the way definitions are interpreted. Robert Manning will start the document to identify those metrics that are interpreted differently. |  | Open
Nov-18-2004 | RMS Request | RMS Request MMWG create a List of their 2004 Accomplishments and Goals for 2005 | Leadership to coordinate a conference call with MMWG members to discuss accomplishments and goals for 2005 | Pam Wheat emailed ListServ with Meeting notice for Tuesday December 7, 2004 at 4:00 PM - Initial Draft of Accomplished was also included in email. | Open

## 2004 Closed Action Items
Meeting Month | Sponsor | Issue | Action Item | Resolution | Status | Date
May-11-2004 | ERCOT | Questions or Clarifications needed for Template | o ERCOT will provide their narrative portion of the 2nd Quarter Metrics Report that was provided to the Market at the next MMWG meeting for open discussion. | Scheduled for the June 2004 Meeting ERCOT has completed and posted to the Performance Metrics Website a detailed definitions document of each line item listed in the spreadsheet document | Closed | 2004-06-08
May-11-2004 | ERCOT | Questions or Clarifications needed in Template | o ERCOT will make the appropriate typographical (misspelling) changes as discussed in today’s meeting. The following corrections will be made | Denise Taylor (ERCOT) made the appropriate changes as oulined in this document | Closed | 2004-06-08
May-11-2004 | ERCOT | Questions or Clarifications needed in Template | o ERCOT will make the following changes to the header of the template: Below | Denise Taylor (ERCOT) made the appropriate changes as oulined in this document | Closed | 2004-06-08
May-11-2004 | Pam Wheat/Kathy Scott | TDSP meeting need to be scheduled to discuss Template wording changes | o TDSPs will need to meet to discuss changing the language/description of some of the data fields found in the current Performance Metrics template. Pam (Chair) and Kathy (Vice-Chair) will co-ordinate a meeting time and place with the TDSPs prior t | Meeting Scheduled at CenterPoint Energy on June 17, 2004 | Closed | 2004-07-07
May-11-2004 | M. Mcarty | MIMO Input needed to determine Future Reporting Requirements | o Suggestion is to have Glen Wingerd (ERCOT) attend the next MMWG meeting to discuss possible future MIMO effects on Reporting Requirements. | Glen Wingerd was unable to attend the June Meeting but has been re-scheduled for the July 7, 2004 MMWG meeting 08/20/2004 - Follow-up Post MIMO Reporting Requirements documented | Closed | 2004-08-20
May-11-2004 | MMWG | MMWG Working Group Procedures | o MMWG Procedures Document will be sent out to the MMWG Listserv for comments must be returned to Chair by COB Friday, May 28th. If there are no comments or if comments include minor grammar or typographical changes, the document would submitted t | MMWG Working Group Draft document was not emailed out to the Working Group in time for review and commnets. This document has been re-scheduled to be emailed on June 14 to the MMWG for comments to be returned no later than June 21st. | Closed | 2004-07-07
May-11-2004 | MMWG | MMWG Change Control Procedures and Process | MMWG Procedures document Change Control Process and ERCOT created Change Control Request Form document. | MMWG Working Group approved Change Control Procedures and Process. Change Control Form posted on ERCOT. Com website | Closed | 2004-07-07
June-08-2004 | RMS Request | At May 2004 RMS Meeting members requested Performance Metrics working group determine the number of Estimated Meter Readings in the Market by TDSP Territory and ERCOT provide this report, especially those involved in MVI/MVO and those numbers where estima | o Mike McCarty will complete the SCR Estimate Meter Reading Request document to incorporate CR remarks in sections shown | Mike stated the document should be available and emailed to the Chair and Vice Chair by noon June 21, 2004. SCR 737 requirements were finalized and approved by MMWG - Submitted to RMS for approval at the August 2004 Open Me | Closed | 2004-07-07
June-08-2004 | RMS Request | Action Items from RMS May's Meeting - Estimated Meter Reading Report and Market Metrics Working Group Procedures document | SCR for Estimated Meter Reading Report and Market Metrics Working Group Procedures need to be emailed to Larry Grimm for the RMS July 15, 2004 Agenda no later than July 8, 2004 | These documents need to be emailed to Larry Grimm for the RMS July 15, 2004 Agenda no later than July 8, 2004 | Closed | 2004-07-07
Aug-20-2004 | MMWG | Get a list of Retailers that have the high number of zip code rejects and educate on the tools available for determing zip code for a premise | J. Lavas to work with Mike McCarty to get a list of Retailers that have the high number of zip code rejects and educate on the tools available for determing zip code for a | 09/29/04 - Mike McCarty will provide MMWG with ZIP Code ERROR report analysis providing total number of transactions for that particular month for comparion 10/19/2004 - ERCOT will get individual CR lists and work with the Retail Client S
Aug-20-2004 | MMWG | 2nd Quarter Report Review | ERCOT to Review 2nd Quarter Overall Performance Metrics Report | Reviewed and Submitted to RMS for Market Communications | Closed | 2004-09-29
Sept-29-2004 | MMWG | Team requested updated status report on FasTraK Projedt for review with team of what requirements have been identified to date. | Mike McCarty will bring to the next meeting the lastest information on the FasTrak Project | 10/19/2004 - Initial Requirements are gathered and any additonal requirments would be added in at later porject. The intial prject has been approved and prioities for the 2005 Budget. Scott Egger discussed requirements with Market on 11/30/2004 for SCR | Closed | 2004-11-18
Sept-29-2004 | DNP Taskforce | Need to schedule a MMWG conference call with Lauren Damen to get specific guidelines for reporting on each section provided in the Disconnect Reconnect spreadsheet for Project 29760 | Pam Wheat will arrangement conference call with Lauren Damen and provide call information to MMWG List service for team notification | 10/19/2004 - Kathy Scott makde suggested changes to the Disconnect/Reconnect Project 29760 Requirements/Definitions Document and finalized this document. The Power Point Document was created and sent to RMS for Market Communications | Closed | 2004-11-18
Oct-19-2004 | MMWG | Kathy Scott received Questions that were Answered by PUCT Staff (Robert Manning) on the correct count procedures for invoices. | MMWG suggested that we add a Q&A segment to the Metrics Website on ERCOT.com. Kathy Scott will forward questions and answers received to Mike McCarty who will create a Q&A section on the website and add these questions to that section. | 11/18/2004 - Q&A Section added to Website by ERCOT | Closed | 2004-11-18

## Approved MMWG Change Controls
Current List of Approved Change Controls for Future Release
Approved Change Controls
Change Controls No# | Status | Date of Approval | Scope of Change | Description/Reason for Change | Communication to Market Date | Implementation Date