## Slide 1: Flight 0105 Update

## Slide 2: Flight 0105 Update
Flight manifest
3 New REPs – 11 New Relationships
4 New Umbrella DUNS – 17 New Relationships
5 Existing REPs testing in new territories – 8 New Relationships
1 Existing REP testing new functionalities
2 Existing REPs changing Service Providers
About 4000 Tasks total

## Slide 3: Flight 0105 Update
Progress
Flight sign-up deadline was December 8th
Final Test Matrix was sent out December 14th
Test beds were due January 10th
Connectivity Testing began December 17th
Connectivity over 80% complete – on schedule
Readiness for January 21st -- We are a go!

## Slide 4: Flight 0105 Next Steps
Flight Takeoff
Daily kick off call Friday January 21st
Transactions start to flow Monday 1/24 at 8:00 am
Daily status calls - MANDATORY
By February RMS (2/8/05)
Market scheduled to be on Day 12 of Flight 0105
  Connectivity should be complete
By March RMS (3/8/05)
Market scheduled to be on Day 32 of Flight 0105
  Last script scheduled to complete on Day 31