## Slide 1: EMMS - SMP/EMP SCADA Management Platform 3.3 Energy Management Platform 2.2
Jim Burke, Project Manager
January 10, 2005

## Slide 2: SMP/EMP Scope and Objectives
SCADA Management Platform / Energy Management Platform
The Telemetry Front End (TFE) is outdated and needs replacement. The SMP
will replace this old technology. Other changes in the migration include:
PR20159 Load Rollover
PR30050 EMS Front-End Replacement
PR30074 Enhance STNET Multiple Selected Time Ranges
PR30094 DCP Enhancement (VSAT/TSAT Enhancement)
PR30096 Move PTI Bus Translation to Genesys
PR30144 EMP 2.2 Upgrade
PR30170 Implement A Selected Contingency Into Power Flow
PR40099 CTGS Import/Export Dump Utility
PR40094 Constraint Activity Manager (CAM) 2.2 Version

## Slide 3: SMP/EMP Progress
Hands On Operator Readiness - In Progress
Initial Operator Training - Complete
Second Operator Training - In Progress
Third SMP “500 Hr” Stability Test - Complete
Migration Planning - In Progress
Market Notice Development - In Progress
Migration Rehearsal Meeting - Scheduled

## Slide 4: SMP/EMP Schedule
Site Fail Over To TCC On - 1/24/05
  POS Fail Over On The Morning Of 1/24
  “Hot Line Call” From ERCOT Operations
  MOS Fail Over During The Afternoon
  No MOS Impact
  ERCOT Operations Will Be Fully Staffed
  Contingency, Fail Back To Previous Site
Site Fail Over To ACC On - 2/7/05
  Same Sequence As 1/24 Fail Over

## Slide 5: Questions