## Sheet1
Description | Should be implemented regardless of ERCOT future market design | Could be done with minumum time and cost impacts to the system | Should not be implemented now if we plan to move to a nodal design in near future | Priority from WMS | Priority Comment from Patton | Cost Impact | Implementation Timeline | Status | Action Items
1. Improve the process for designating zones to minimize the effects of the simplifying zonal assumptions; | X |  |  |  | High Priority | No system change is required | Can be implemented right after PRR is approved |  | ERCOT to draft PRR to modify/add wording to Protocols to strengthen ERCOT's role in determining zones and CSCs and submit to PRS by April 1
2. Improve process for evaluating and revising CSC definitions; | X |  |  |  | High Priority | No system change is required | Can be implemented right after PRR is approved |  | Assign to CMWG to further define criteria for establishing CSCs and improve process for evaluation.
3. Modify the calculation methodology of the zonal average shift factor to exclude generation whose output is generally fixed (e.g., nuclear units); | X |  |  |  | Medium Priority - should do regardless of nodal | No system change is required | Can be implemented right after PRR is approved | ERCOT has re-calculated zonal average shift factors to exclude some generators. (Please refer to the attached spreadsheet) | ERCOT will draft PRR to implement, including options for criteria to exclude units
4. Provide ERCOT the operational flexibility to temporarily modify the definition of a CSC associated with topology changes; | X |  |  |  | Medium Priority - should do regardless of nodal | No system change is required | Can be implemented right after PRR is approved | only changes to the transmission element that comprise each CSC and list of CREs | ERCOT Operations to propose Protocol language changes to enable ERCOT to modify the definition of a CSC based on operational issues submit to PRS by April 1.
5. ERCOT should modify is multi-step balancing energy market optimization to reognize the interactions between its local congesiton management and zonal balancing energy deployments to minimize the costs of both classes of deployments. |  | X |  |  | Highest Priority - Most significant recommendation; should be done regardless of nodal | 100k~500k | 9~12 months after PRR is approved | ERCOT has met with Dr. Patton to discuss this recommendation. Please refer to the attached file to see the details of this recommendation and ERCOT's comments. | ERCOT will draft PRR and submit to PRS.
6. ERCOT examine its load forecasting model to determine whether there are additional factors that could be considered or other changes to their model that would improve its accuracy. | X |  |  |  | Low Priority - can do regardless of nodal |  |  | ERCOT has met with Dr. Patton and explained to him what ERCOT is doing to improve Load Forecast accuracy and data issue. It seems that Dr. Patton is satisfied with ERCOT's explanation. | Done with this recommendation until the model gets retrained and to see how well it does.
7. Allow QSEs to submit an energy schedule for the end of the next hour that would be used by ERCOT to produce 15-minute schedule quantities by interpolating across the hour; | X |  |  |  | Low Priority | 200k~600k | 9~12 months after PRR is approved |  | B. Helton to review - this could be done voluntarily by enough market participants through education however, mismatch issue needs to be addressed
8. Implement an optional capability for QSEs to automatically adjust their hourly balancing energy offers for the changes in their 15-minute schedules. This would help ensure that the participant’s portfolio energy offer is consistent with its energy schedules when the energy schedule is changing each interval; |  | X |  |  | High Priority | 100k~200k | 6~9 months after PRR is approved |  | B.Helton will discuss this in WMS meeting and find someone to draft a PRR.
9. Eliminating the load and generation plateau in the middle of the interval by changing the modeling approach for load and generation; |  | X |  |  | High Priority - one of the the higher priorities along with recommendation #5 - should do regardless of nodal | 60k~100k | 4~5 months after PRR is approved | ERCOT needs to change URC and SCE calculation. No SPD change is required as the ramp period is a parameter in SPD | QSEs and ERCOT to see what affect this will have on their systems
10. Require that QSEs submit physically feasible energy schedules. It would be difficult to automatically validate the schedules for feasibility since they can be submitted well before the operating hour. However, it could be monitored and enforced through ex post validation of compliance; | X |  |  |  | Medium Priority | No system change is required |  |  | Compliance to draft a plan on how to accomplish this - enforcement type situation
11. Implement uninstructed deviation charges that allocate a portion of the regulation costs to the QSEs exhibiting large SCEs in the periods during each hour with the largest regulation needs. In particular, we propose specific changes to PRR 356 that has been pending for more than two years; |  | X |  |  | High Priority - should do regardless of Nodal | ERCOT will file Impact Analysis when PRR 356 is resumed to be discussed in PRS |  |  | Policy Issue - PRS(PRR 356) to discuss. PUCT staff is continuing to work on PRR 356 and will submit when ready
12. Consider a specific modification of its portfolio ramp rate methodology that would recognize the changes in energy schedules; |  | X |  |  | High Priority | 500k~1M | 12 ~ 14 months after PRR is approved | SPD Change. Step 1 and 3 change should be simple, but it is more complicated when portfolio ramp rate is considered in unit specific deployment process in step 2 | ERCOT to draft PRR
13. ERCOT modify the limit on the quantity of responsive reserves provided from a single unit to make it less binding on relatively small units |  | X |  |  | Medium Priority | 50k | 3 months after PRR is approved | OGR (161) in the pipeline to revisit this issue | Concerns with reliability - ROS to evaluate
14. ERCOT institute procedures to monitor whether QSEs are meeting their reserve obligations in real time. |  | X |  |  | Low Priority | 100k | 3 ~ 4 months after PRR is approved | To implement this recommendation requires monitoring units’ ramp capability. To monitor units’ ramp capability either requires QSEs sending real time units’ ramp capability via SCADA system or at least requires QSEs providing more accurate ramp rate information in their resource plan. | Monitoring issue - Compliance to review