## Slide 1
Objectives:
Define and implement a website layout that enables users to find key information efficiently
Develop a process to ensure the sustainability of the investment in the enhancements
Scope:
Search engine functionality (including metadata strategy)
Improve navigation - create a new information architecture for the site (task driven focus)
Content owners can post updates easily – content manager
Process for maximizing the use of key real estate for critical and timely information
All information and processes are maintained after the redesign
Dependencies:
None at this time
Project Objectives / Scope / Dependencies
PR-40106 ERCOT.com

## Slide 2
Phase:
Initiation – completed in Sept ‘04
Planning – in progress
Execution – goal mid March ’05
Closing – goal July ‘05
Recent:
Vendor delivered ‘Solution Definition’ recommendations
Next steps:
Project plan w/resource allocation
Prepare to update Directors on Planning phase activities
Prepare to enter next phase (Execution)
Summary of Project Status
PR-40106 ERCOT.com

## Slide 3
** All target dates – will have firm dates after project plan is completed
Requirements (pens down) – March ’05
Design (published document) – April ’05
Testing – May ’05
Training – June ’05
Production (Go live) – July - August ‘05
High level timeline
PR-40106 ERCOT.com

## Slide 4
Bus Lead: Scott Egger ph. 512-248-3162
PPL: Source: ERCOT Priority: 1.1 Rank: 24 Program Area: RO
What prompted the project:
  Market Survey
  TML Phase II Mid-Term Requirements
  Strategic Fit
Supporting business drivers:
  Data from the Market Survey strongly encouraged the implementation of a search engine
  Peer website comparisons between the other ISOs
  Practical usage feedback
Additional Information
PR-40106 ERCOT.com