## Slide 1
EXECUTION
Factory Acceptance Testing Started.
INITIATION TO PLANNING WITH NO CAPITAL BUDGET YET APPROVED
Project Scope/Deliverables
Timeline
Issues / Actions
Financial Milestones as of 11/30/04
Executive Summary of Status
PR-30183 EMMS R4
PM: Jeffrey Robinson
Del Mgr: Obadina
Activity | Frcstd. Completion Date | % Complete | Status
Scope Lock | 5/28/04 | 100% | Completed
Detail Design | 10/29/04 | 99% | In Progress
Build and Unit Test | 12/3/04 | 100% | Complete
Pre-FAT | 1/24/05 | 100% | Complete
Factory Acceptance Test | 3/4/05 | 35% | In Progress
Site Acceptance Test | 4/29/05 | 0% | Not Started
User Acceptance Test | 5/6/05 | 0% | Not Started
Market Participant Test | 5/17/05 | 0% | Not Started
Production Migration | 5/27/05 | 0% | Not started
Sponsor: Saathoff
Bus Lead: Patterson
Last Update
This Update
Bus Align/ Scope Risk
Technical Risk
Schedule Risk
Staffing Risk
Financial Risk
Overall
G
G
G
G
G
R
G
G
G
G
 | Approved Budget |  |  | Current Forecast / Actual |  | 
 | Capital | Expense | Total | Total Forecast | Committed to Date | Actual to Date
Labor |  |  |  |  |  | 
Consult |  |  |  |  |  | 
HW |  |  |  |  |  | 
SW |  |  |  |  |  | 
Other |  |  |  |  |  | 
Total |  |  | 7,657,633 |  |  | 
X
Updated
G
G
G
10 major deliverables from AREVA (MOS–5, POS-4, PUCT-1) + 7 internal sub projects (4 Billing & Settlements, 3 DA/DW)
Billing & Settlements development underway. OOM Tool Enhancements planning near completion.
DA/EDW planning completed.
XML Specifications released 2/2/05.
Factory acceptance testing progressing slower than expected. This may require additional testing time.
G
Y

## Slide 2: Deliverables
Market # | Project # | Project Title
PIP137 PRR211 | PR-20130 | PIP137/PRR211 Association of BE Bids with RPRS
PRR413 | PR-30161 | PRR413 - Optimization for the Whole Operating Day in RPRS Procurement Process
 | PR-30085 | Special Protection Schemes
PRR359 | PR-30131 | Resource Plan Improvement (Phase II)
PRR342 PRR414 | PR-30140 | AS Simultaneous Selection
PRR423 | PR-30162 | PRR423 - Dispatch of Generation Resources Below Minimum Operating Level
PRR422 | PR-30163 | PRR422 - OOM Zonal Dispatch Instructions
 | PR-40049* | Improve Data Elements for Local Constraints & OOMs
 | PR-40095 | Enhancement to OOM tools for congestion management
 | PR-40048 | EMMS Parameters Capture for MMS Reclear Fidelity
PRR485 | PR-40050 | Unit Specific Bid Limits based on Generic Costs
 | PR-40051 | OOM Participation in Providing Ancillary Services
 | PR-40062 | PUCT Upgrade SPD
 | PR-40072 | PUCT Add Corrected MCPEs to the MOS dbase and pass to MMS
 | PR-40092 | Improve Power System Model Maintenance via Database Archive Comparison
 | PR-40096 | Improvements to VSA/DSA
Notes: |  | 
* A Business Process will be put in place to address standardization of Constraint Names. |  |