## Slide 1: Houston Area Constraint Mitigation Project
ERCOT Board of Directors
March 15, 2005

## Slide 2: Description of Project
Upgrade Jewett-Tomball/TH Wharton 345kV double circuit ($9.5M)
Construct new Hillje 345kV switching station in the STP-Holman 345kV line ($10.8M)
Build new Parish –Hillje 345kV double circuit ($79.25M)
Add STP-Hillje 345kV circuit on open position of existing STP-Parish line ($8.35M)
Replace autotransformers at Greens Bayou, Tomball, Addicks and O’Brien ($12.2M)
Replace miscellaneous breakers, terminal equipment, and 138 kV conductors ($1.86M)

## Slide 3: Cost and Savings of Project
Jewett-Tomball/TH Wharton upgrade and autotransformer change outs scheduled in-service in 2007
Remainder of package scheduled in-service in 2008
Total cost of package of projects is $122 million (or approximately $20 million annual carrying cost)
Projected production cost savings (in nominal $millions):
Annual savings of ~$63M significantly exceeds the $20M annual carrying cost of the project
2007 | 2008 | 2009 | 2010
14.5 * | 57.4 | 60.9 | 69.6

## Slide 4: Options Considered
Centerpoint evaluated 28 different packages of projects
ERCOT performed an economic evaluation of over 90 different combinations of these projects
Sensitivities to the economic savings on the final recommendation:
  Retirement of TX Genco units
  Lower natural gas price forecast
The Hilje option 27 increases the transfer capability into Houston while improving system reliability, operation flexibility and market efficiency

## Slide 5
The Stakeholder review period for this project began in September 2004. Comments supporting the initial package of projects were received from:
      TXU Energy
      Austin Energy
      Direct Energy
      STEC – supported, however, did not believe STEC portion of package was required
A second comment period was held in January 2005 following the economic analysis performed by ERCOT. Comments supporting the results were received from:
      CenterPoint Energy
      Reliant Energy
      TXU Energy
      City Public Service of San Antonio
      Austin Energy
      Constellation
      AEP
Stakeholder comments at all stages of the review have been in support of the project, with no dissenting comments
TAC endorsed the recommendation on March 3, 2005
Stakeholder Review

## Slide 6
ERCOT staff recommends that the Board endorse the need for the Houston Area Constraint Mitigation Project as described in the ERCOT report to the Board.
Recommendation