## Slide 1: Load Research Sampling (LRS) Project Summary
12/16/2004

## Slide 2: LRS Project Summary -- Project
Project Measurement and Metrics
  Timeline
    Project start date -- 2Q2003
    Scheduled Project deployment date (agreed to by Market) – 11/1/2004
    Actual Deployment date --11/1/2004
  ERCOT Budget
    Original Project Budget -- $1.5MM (impact analysis)
    Revised Project Budget -- $700k
    Actual charges to date -- $660k
    ~$40k in outstanding invoices that should be reconciled over the next month
  5 TDSPs fully engaged in the program
  13 CRs fully engaged in the program

## Slide 3: LRS Project Summary -- Market
TDSPs Commitment
  All TDSPs completed Pilot testing
  Inspected over 4500 IDR sample Sites
  Installed over 4200 IDR sample points
  Sample point readings have been transmitted to ERCOT starting in August 2004
  TDSPs have been diligent about replacement points, and working with ERCOT staff on sample point issues
CR Commitment
  All CRs have completed Pilot testing
  ERCOT is in the process of building data to transmit to CRs
  CRs will be working with ERCOT staff if there are any additional issues

## Slide 4: LRS Project Summary
Market Summary
  TDSP Installation update as of 12/1/2004
  ERCOT verification of sample point installation and transaction confirmation underway
  ERCOT working with TDSPs on remaining installations and replacements (on-going)
  ERCOT transitioning to O&M role for sample point management and tracking

## Slide 5: LRS Project Summary -- ERCOT
ERCOT Software solution
  Deployment of new software applications
    Client/server Lodestar
    Client/server SAS
  Deployment of “Retail like” transaction management solution
  Deployment of back end sample tracking system
ERCOT Hardware and Environments
  Built out 11 new servers for the project (all on new Blade technology)
  Built 4 new environments for internal testing, Pilot, and Production

## Slide 6: LRS Project Summary -- ERCOT
Transactions
  Tracking solution completely transaction based (minimal data clean-up required)
  Utilized existing MV-90 technology transactions to minimize cost for data formatting, data clean-up, and data transmission
  Created 4 new transactions for TDSPs to transmit sample data to ERCOT
  Created 19 additional internal transactions
Issues and Resolutions
  Identified over 20 critical issues during testing and all were resolved
  Identified numerous additional fixes and enhancements throughout the project. Most have been completed and remaining are being rolled into O&M
  No critical or High issues or defects outstanding

## Slide 7: LRS Project Finale
Many thanks to the following groups (since there are way too many people to list):
  TDSP Metering staffs
  TDSP Load Profiling depts.
  TDSP Transaction Management depts.
  CR Load Profiling groups
  ERCOT Load Profiling dept.
  ERCOT Transaction Services
  ERCOT Web Services
  ERCOT Infrastructure and Networking
  ERCOT Production Support
  PWG
  RMS
  And probably many more….
  Thanks again for everyone’s hard work and commitment ---Ultimately, that is what made this project a success !!