## TX SET Information
TX SET |  |  |  |  | DATE | 2005-01-26 | 2005-01-27 | 2005-02-28 | 2005-03-01 | 2005-03-16 | 2005-03-17 | 2005-04-05 | 2005-04-06 | 2005-05-17 | 2005-05-18 | 2005-06-21 | 2005-06-22 | 2005-07-19 | 2005-07-20 | 2005-08-16 | 2005-08-17 | 2005-09-20 | 2005-09-21 | 2005-10-18 | 2005-10-19 | 2005-11-07 | 2005-11-08 | 2005-12-05 | 2005-12-06
[5 empty] | CITY | 2005-01-26: Austin 206A; 2005-02-28: Austin 168; 2005-03-16: Houston; 2005-04-05: Corpus Christi; 2005-05-17: New Orleans; 2005-06-21: Houston; 2005-07-19: Tulsa; 2005-08-16: Dallas; 2005-09-20: Austin; 2005-10-18: Houston; 2005-11-07: Austin; 2005-12-05: Austin
OFFICER | NAME | COMPANY | EMAIL@ADDRESS | PHONE | MEETING VENUE | ERCOT MET CTR | ERCOT MET CTR | ERCOT MET CTR | ERCOT MET CTR | CenterPoint Energy | CenterPoint Energy | American Electric Power | American Electric Power | Entergy Corporate Ofice | Entergy Corporate Ofice | Reliant Energy Office | Reliant Energy Office | American Electric Power | American Electric Power | TXU ED Office | TXU ED Office | ERCOT - TBD | ERCOT - TBD | CenterPoint Energy | CenterPoint Energy | ERCOT - TBD | ERCOT - TBD | ERCOT - TBD | ERCOT - TBD
| Baum, Thomas | ERCOT | tbaum@ercot.com | 512-248-6550 | bar: 2005-01-26 to 2005-03-17
| Bear, Jason | Direct Energy | bar: 2005-03-17
| Beaver, Tammy | Interlink | tbeaver@epway.cm | 512-268-8765 | bar: 2005-01-26 to 2005-03-01
| Bevill, Rob | Green Mountain | rob.bevill@greenmountain.com | 512-691-6134 | bar: 2005-01-26 to 2005-03-01
| Blumenthal, Ellen | GDS Associates | ellen.blumenthal@gdsassociates.com | 361-949-1578
| Bowling, Shannon | Cirro Energy | bar: 2005-03-17
Vice Chair | Bratton, Charlie | TXU Energy | cbratto1@txu.com | 214-875-8137 | bar: 2005-01-26 to 2005-01-27; 2005-03-01 to 2005-03-17
| Burke, Allan | TNMP | aburke@tnpe.com | 817-377-5532 | bar: 2005-01-26; 2005-02-28; 2005-03-16
| Callender, Wayne | City of Public Service SA | wdcallender@cps-satx.com | 210-353-2779
| Campirano, Eduardo | BPUB | ecampirano@brownsville-pu.com | 956-983-6279
| Collard, Zach | CenterPoint Energy | zachary.collard@centerpointenergy.com | 281-433-7050
| Conner, Mike | BTU | mconner@btutilites.com | 979-821-5830
| Damen, Lauren | PUCT | lauren.damen@puc.state.tx.us | 512-936-7410
| Dauterive, Eddie | Envision Utility Software | eddied@envworld.com | 512-266-7787
| Davis, Mike | ERCOT | mdavis@ercot.com | 512-248-6763 | bar: 2005-01-26
| Dawson, Bernie | Envision Utility Software | bernardd@envworld.com | 512-266-7787 | bar: 2005-01-26; 2005-02-28 to 2005-03-01; 2005-03-17
| Duke, Warren | Peace Software
| Farley, Karen | ERCOT | kfarley@ercot.com | 512-248-3141 | bar: 2005-01-27
| Fisher, Sarah | NEC | sfisher@nueceselectric.org | 361-387-2581
| Flores, Eloise | Nueces Electric Coop | eflores@nueceselectric.org | 800-632-9288 | bar: 2005-01-26; 2005-02-28 to 2005-03-17
| Flowers, BJ | TXU Energy | bj.flowers@txu.com | 214-812-4330
| Frederick, Jennifer | ERCOT | jfrederick@ercot.com | 512-248-6733 | bar: 2005-01-26; 2005-02-28 to 2005-03-17
| Garcia, Jennifer | USA Interlink
| Godoy, Ernie | SPEC | egodoy@sanpatricioelectric.org | 361-364-2220
| Harper, Brett | First Choice | bharper@firstchoicepower.com | 817-437-1479 | bar: 2005-01-26 to 2005-03-17
| Hensley,Bryan | Cuemon Consulting | br_hensley@yahoo.com | 469-667-6469 | bar: 2005-02-28 to 2005-03-01
| Hermes, Connie | STEC | connie@stec.org | 361-485-6173 | bar: 2005-01-26 to 2005-01-27; 2005-03-16 to 2005-03-17
| Hernandez, Ron | ERCOT | rhernandez@ercot.com | 512-248-6523
| Heselton, Michael | DEBS | michael.heselton@na.centrica.com | 972-409-3282 | bar: 2005-02-28 to 2005-03-01; 2005-03-17
| Jackson, Tom | Austin Energy | Tom.Jackson@austinenergy.com | 512-322-6324
| Kalips, Leo | NISC | leo.kalips@nisc.cc
| Kassel, John | ERCOT | jkassel@ercot.com | bar: 2005-03-01
| Kernick, Kristina | Envision Utility Software | kristinaak@envworld.com | 512-266-7787
| Leith, Brent | First Choice | bleith@firstchoicepower.com | 701-306-6810
| Lowder, Dave | NEC | dlowder@nueceselectric.org | 361-387-2581 | bar: 2005-02-28
| MacDonald, Amy | Green Mountain | amy.macdonald@greenmountain.com | bar: 2005-03-17
| McCarty, Mike | ERCOT | mmccarty@ercot.com | 512-248-3927
| McKain, Shelley | ADS Mutual Energy | smckain@alldata.net | 918-493-9515
| McKenna, Will | EPSolutions | wmckenna@epway.com | bar: 2005-01-26 to 2005-01-27
| Minooee, Anahita | Direct Energy | anahita.minooee@na.centrica.com | 713-877-3577 | bar: 2005-03-16 to 2005-03-17
| Moast, Pat | ERCOT | pmoast@ercot.com | 512-261-9925
| Moore, Chuck | Direct Energy | chuck.moore@na.centrica.com | bar: 2005-01-26 to 2005-01-27; 2005-03-16 to 2005-03-17
| Morales, Rita | Direct Energy | rita.morales@na.centrica.com | 972-480-8224 | bar: 2005-01-26 to 2005-03-17
| Numrich, Lisa | ADS Mutual Energy | bar: 2005-03-01; 2005-03-17
| Ohrt, Wendy | STEC | wendyjo@stec.org | 361-485-6172
Chair | Patrick, Kyle | Reliant Energy | kpatrick@reliant.com | 713-497-3396 | bar: 2005-02-28 to 2005-03-17
| Phillips, Cory | GEXA | cory.phillips@gexaenergy.com | 713-740-0464 | bar: 2005-03-16 to 2005-03-17
| Polliard, Sharon | AEP | srpolliard@aep.com
| Reed, Cary | AEP | careed@aep.com | 918-260-0093 | bar: 2005-01-26 to 2005-03-16
| Rehfeldt, Diana | TNMP/First Choice Power | drehfeldt@tnpe.com | 817-377-5580
| Reily, Bill | TXU Electric Delivery | breily@txued.com | 214-875-2520 | bar: 2005-01-26 to 2005-03-17
| Riordon, Ken | LCRA | ken.riordon@lcra.org | 512-473-3215
| Robertson, Johnny | TXU | jrobert1@txu.com | 214-875-1565 | bar: 2005-01-26 to 2005-03-01
| Robinson, Laura | Starlight Electric | laura@starlightelectric.com | 817-548-0808 | bar: 2005-01-26
| Rodriguez, Robert | Constellation New Energy | Robert.Rodriguez@constellation.com | 281-793-6339 | bar: 2005-01-26 to 2005-01-27
| Saenez, Fernando | BPUB | fsaenez@brownsville-pu.com | 956-983-6266
Vice Chair | Scott, Kathy | CenterPoint Energy | Kathy.scott@centerpointenergy.com | 713-582-8654 | bar: 2005-01-26 to 2005-03-17
| Shillington, Shawn | TNMP | sshillington@tnpe.com
| Smith, Lori | TNMP/First Choice Power | lsmith@tnpe.com | 817-337-5532 | bar: 2005-01-26; 2005-02-28 to 2005-03-17
| Steen, Lora | Entergy | lsteen@entergy.com | 936-525-2034
| Teel, Jennifer | EC POWER | jennifer.teel@ec-power.com | 713-403-8731 | bar: 2005-03-17
| Thomas, Jeff | Direct Energy |  | 214-509-2122
| Weaver, Steve | Entergy Solutions | sweave1@entergy.com | 832-681-3146 | bar: 2005-01-26 to 2005-01-27; 2005-03-01 to 2005-03-16
| Wilburn, Suzette M. | ERCOT | swilburn@ercot.com | 512-248-3991 | bar: 2005-01-26 to 2005-03-17
| Wilson, Frank | Nueces Electric Coop | fwilson@nueceselectric.org | 361-387-2581
| Wingerd, Glen | ERCOT | gwingerd@ercot.com

## 2004 & 2005 Open Action Items
Meeting | Segment | Sponsor | Issue | Action Item | Resolution | Status | Date
2004-11-17 |  | ERCOT | Modify the existing reject code A78 (“Item or Service Already Established”) to include CRs as well as TDSPs and ERCOT. This would allow CRs to reject 814_08 transactions where the BPI has already been completed. | TX SET agreed this needed to be added as an agenda item for discussion and to develop a process, if necessary for this scenario | 1/27/05 - Further discussion to take place 02/28/05 - Still needs discussion and investigation 03/17/05 - Still needs discussion and investigation | Open
2004-11-17 |  | FCP | Discuss pending change control for 814_09, ERCOT will query all 814_09 rejects received since V2.0 was implemented to get an idea of the reasons the TDSPs and CRs are rejecting 814_08s. ERCOT will work with FCP in getting some examples of what they are seeing and will provide analysis at the November TX SET meeting | Change Control was withdrawn by FCP for TX SET to discuss as an agenda item for the December meeting. Need to determine what the problem is and identify solution along with process to prevent. | 1/27/05 - Further discussion to take place 02/28/05 - Still needs discussion and investigation 03/17/05 - Related to Item row number 2 of this spreadsheet | Open
2005-01-05 |  | FCP | How TDSPs communicate the additions and removals of unmetered devices. | By the end of 1st quarter 2005, CRs will review and document if they are being impacted by inconsistent communications between the differenct TDSPs. | 02/28/05 - Still open for further discussion and investigation. Sub-team will meet to revise and clarify 814_20 03/17/05 TX SET currently working out the process and updating 814_20 for unmetered services | Open
2005-01-05 |  | TX SET | Submit completed PRR regarding section 15 of the ERCOT protocols to include the update of using the 814_08 & 814_09 transactions on a cancel drop to AREP. | This PRR will be submitted closer the Implementation of version 2.1 | 02/28/05 - Holding off on creating and processing PRR for this until v2.1 has been implemented creating this as the Market process. 03/17/05 - TX SET will turn over to MCT for updates to Chapter 15 as applicable to version 2.1 implementation | Open
2005-01-05 |  | CRs | Usage Smoothing - CRs created a list of questions for the TDSP to address regarding usage smoothing/adjustments. | TDSPs to bring answers to the Feb. TX SET meeting. | 02/28/05- TDSPs still need to meet to discuss document as a group and return results back to TX SET 03/17/05 - TDSPs still need to meet to discuss hopefully will be available to provide reply on at the April or May 2005 meeting | Open
2005-01-05 |  | CRs | For Future Discussion: Timing on rejected 867 corrections and when they need to be sent. | Place on Future Agenda for Discussion | 02/28/05 - need to place on agenda for discussion at later date 03/17/05 - still open for discussion- | Open
2005-01-05 |  | CRs | CRs being required to cancel their order on a demand cancel if they already show the order as completed. | Place on Future Agenda for Discussion | 2/28/2005 - Still Open for discussion and investigation. 03/17/05 - still open for discussion- same as item number 2 and 3 | Open
2005-02-28 |  | SET | Need to update all Visio flows to be applied to version 2.1 Implementation Guide - MOU/EC need to be created | Place on Future Agenda for Discussion and Assignment | 03/17/05 - still open for discussion- ERCOT will check with Bernie Dawson to see if he has started/completed this task | Open
2005-02-28 |  | Subteam assigment | Action Item: TX SET subgroup to work on the 814_20 guide for unmetered services. Tom Baum, Bill Reily, Kyle Patrick, Bryan Hensley, Cary Reed, Kathy Scott, Suzette Wilburn Proposal: When updating the number of unmetered devices on an ESIID, the MA and MR data elements will be used to communicate the addition or removal of devices and a new data element (UT) will be added to the NM101 to communicate the Unit Total of devices after the MA/MR is applied. | Subteam Meeting Schedule 3/15/05 in Houston at CNP office to address 814_20 issues concerning un-metered services | 03/15/05 -The subteam met on 3/15/05 to start the discussion of what needs to be revised and updated on the 814_20 | Open
2005-02-28 |  | CR | 650_01 only says from "CR to TDSP" does that mean Muni/Coop? or not? • Yes. In addition to the 650 series there are other transaction series where the MOU/EC is not specified. TX SET suggests the following language to be added to the V2.1 Market Requirements document: ATTENTION: Within this implementation guide, when the term “TDSP” is used, it is meant to include both IOU TDSPs and MOU/EC TDSPs. In those instances when “MCTDSP” is specified, the transaction/segment/data element is intended for use by the MOU/EC TDSP alone. (814 series, 867 series, 824, 650 series) | TX SET suggests the following language to be added to the V2.1 Market Requirements document: ATTENTION: Within this implementation guide, when the term “TDSP” is used, it is meant to include both IOU TDSPs and MOU/EC TDSPs. In those instances when “MCTDSP” is specified, the transaction/segment/data element is intended for use by the MOU/EC TDSP alone. (814 series, 867 series, 824, 650 series) |  | Open
2005-02-28 |  | ERCOT | Update on 008/SBD Exception Report to TDSPs – FasTrak v. Report on the TML • TDSPs were interested in finding out if the process would be consistent with what is in place today for ERCOT reporting 008/SBD exceptions. From the January meeting, TDSPs were going to follow up on what they validate on to determine a Duplicate and what they are expecting ERCOT to do with this information. | Action Item: ERCOT will stop creating FasTrak issues for these exceptions and instead will provide this information on the existing MIMO exception report. TDSPs can review this report and open a FasTrak issue at their discretion. ERCOT will provide an update on the Retail Market Call with when the change will occur. |  | Open
2005-02-28 |  | ERCOT | Update on TDSP Rejects for DUPLICATES. From the January meeting, TDSPs were going to follow up on what they validate on to determine a Duplicate and what they are expecting ERCOT to do with this information. | Action Item: ERCOT will bring examples to the April TX SET meetings of any use of the ‘ABN’ reject reason to determine approach for process in handling the ABN code. |  | Open
2005-02-28 |  | TX SET | Review proposed TX SET Change Control Procedures Redlined version was sent out with the January TX SET meeting information and review at the February meeting . | Action Item: TX SET needs to define the term ‘emergency’ |  | Open
2005-02-28 |  | Eloise Flores/NEC | Developing a process for discretionary charges We are trying to develop a process on charging CRs for discretionary charges. I am assuming that we will use the 810_02 but we are not sure how to indicate that the charge is to the CR and not the customer. | Action Item: Place on Agenda for Future Discussion |  | Open
2005-02-28 |  | TX SET | 2.1 Redline Assignments • Tom Baum assigned 2.1 redlines to the TX SET membership for review. | Action Item: Members need to have their assigned redlines completed and returned to Tom Baum by Close of Business 3/14/05 to be discussed at the March TX SET meeting (16th & 17th) |  | Open
2005-03-17 |  | TX SET | TX SET Representatives need to review proposed TX SET WG Procedures and modified Change Control form | TX Review of updated TX SET Working Group Procedures and modified Change Control form and should be ready to approve at the April meeting. |  | Open
2005-03-17 |  | TX SET | Re-write Change Control 2003-503 to add clarifed information | Kathy Scott will re-write the change change |  | Open
2005-03-17 |  | TX SET | Write an urgent change control for v2.1 implementation to add DTM~215 Suspension Date as an optional segment for permanent meter removal situtations - BGN08 = R8 | Rita Morales will write urgent change control for v2.1 implementation |  | Open
2005-03-17 |  | TX SET | Protocols Chapter 15 - Update for version 2.1 Implementation guides and business process | TX SET will turn-over to Market Coordination Team |  | Open
2005-03-17 |  | TX SET | Protocols Chapter 19 - Update for version 2.1 Implementation guides and business process | TX SET will update |  | Open

## 2004 & 2005 Closed Action Item
Meeting | Segment | Sponsor | CC | Issue | Action Item | Resolution | Status | Date
January |  | RRI |  | Would like to investigate possibility of adding a flag to indicate whether the meter is temporary or permanent | CRs will meet to re-frame the question and provide the TDSPs with exactly what they'd like to see |  | Closed | 2004-02-17
January |  | RRI |  | Would like to investigate the possibility of adding a code on the 814_16 and 650 series that would provide gate access codes | Group agreed that more time was necessary to determine if there was a need for this type of information from all CRs |  | Closed | 2004-02-17
January |  | ERCOT |  | Review of the draft 867_01 IG for opting in entities | TDSPs to review guide with SMEs at their companies to verify guide contains all necessary segments and data elements | TX SET believes that the cost for re implementing the 867_01 is much larger than the cost for using a flat file on a on going basis. | Closed | 2004-05-13
January |  | ONCOR |  | Outdated scheduled transactions in ERCOTs system that cannot be completed | ERCOT to investigate if a common theme exists for the manual processes used to 'fix' these scheduled transactions to get a better idea of where TX SET needs to focus their attention | Comment 5/19/04: No true common theme, but the problem centers around previous versions (1.4, 1.5) trxs cannot be completed with future releases (1.6, 2.0). Kyle Patrick will refer to MCT for future discussion. | Closed | 2004-05-13
January |  | ERCOT | Y | Clarification needed on how maintenance to unmetered service devices are communicated in the 814_20 | 814_20 guide needs to be updated if the 814_20 is not used when maintaining unmetered service devices. TX SET to investigate the possibility of adding this functionality to the 814_20 | TDSPs waiting for response on whether they send 814_20s. | Closed | 2004-05-13
January |  | CNP | Y |  | 867_03 How to Use Section meeting needs to be arranged to convert the How to Use to a BPO and make the appropriate updates in the new BPO document. | Comment April TX SET: This will be an agenda item for the May meeting of TX SET in Dallas. Comment May TX SET: This will be an agenda item for the June meeting of TX SET. | Closed | 2004-05-13
January |  | TX SET |  |  | TX SET Leads need to develop a process that would remind members of outstanding and/or open action items prior to monthly meetings (1 or 2-weeks before if possible) | Leadership will remind team members of action items when meeting notice and agenda are sent. | Closed | 2004-05-13
|  | ERCOT |  | In the case of a MOV to CSA, when an 814_08 is submitted by the Cur CR, is the TDSP expecting the Cur CR or CSA CR Duns in the N1~SJ? I would believe it would be the CSA CRs Duns, because the TDSP would have received an 814_03 with the CSA CRs informatio |  | ERCOT will be putting the CSA CR in the 814_08 | Closed | 2004-05-13
February |  | TX SET |  | Review BPOs for 2.0 | Cary Reed, Kyle Patrick, Suzette Wilburn, JR, and Bill Reily will review. | Comment 5/19/04: Team to meet 5/25/04 in Austin, TX venue to be determined. | Closed | 2004-05-13
February |  | ERCOT | Y | · In the event that there are multiple meters exchanged on a premise, would the profile code be listed in both NM1 loops? We have seen some instances where the profile code update (REF~LO) is included in the second NM1 loop and wanted to verify that prof | S. Wilburn to write a change control to move the REF~LO segment to the LIN loop | Comment 5/19/04: Change control has been written but not submitted. | Closed | 2004-05-13
February |  |  |  | · The N303 in the N3 segment of the 814_20 is alphanumeric. (AN1/55). Would like to find out from the group if they would like to see ERCOT rejecting transactions that send special characters in this field. o Encountered issues with double quotes in th | ERCOT will communicate to the team what decision they decide to go with regarding the cross validation | ERCOT put validation in that reject double quotes in the address field. | Closed | 2004-05-13
February |  |  |  | · Following up on the issue regarding 814_20 retires being received on de-energized ESI-Ids with a scheduled MVI. We have a proposed short term solution o If the SMRD of the MVI is greater than the date on the retire, we cancel the MVI o If the SMRD of t | ERCOT will implement a fix in a near release to reject any 814_20 retires received on a de-energized premise with a scheduled service order. TDSP will open a fastrak issue to get open service order resolved. Release date is still to be determined. ERCO | ERCOT will follow the short term solution in the recommendation | Closed | 2004-05-13
February |  | Nueces |  |  | E. Flores to gather all issues addressed to date regarding the Muni/Coop market to send out to the market | This will be an ongoing list | Closed | 2004-05-13
February |  | TX SET Officers |  |  | TX SET officers to make phone calls to the muni/coops about the meeting | MOU/EC meeting was held on 4/19/04 in Corpus Christi | Closed | 2004-05-13
February |  | ERCOT |  |  | ERCOT Client Services to pull together email to be sent out inviting all Muni/Coops to attend the day meeting on April 20th | MOU/EC meeting was held on 4/19/04 in Corpus Christi | Closed | 2004-05-13
February |  | TCE/STEC | Y | We need to talk about the 650_04 disconnect/reconnect process on the muni/coop side. There was some discussion at Texas Test Plan script sub team on this regarding the current test script calling for a 650_04 cancel of the disconnect request to indicate | TCE to work with STEC to write change control for adding a new code to the 650_04 to communicate this information | Comment 5/19/04: Jeff Thomas to update SET on this. | Closed | 2004-05-13
February |  | ERCOT | Y | Should a REF~IX always exist when a REF~4P is present in the 814-04? · For example, if you have a REF~MT~COMBO and two REF~4Ps should you also have two REF~IXs? · If not, what circumstances exist when you wouldn't, and what type of modifications could be | o (Action Item) S.Wilburn to write a change control to update the examples in the 814_04 | Comment 5/19/04: Change control was written, and withdrawn. The text will be left in the example. TX SET again stresses that MPs should code to the guide section not the examples section. | Closed | 2004-05-13
February |  | TX SET |  | "Future Implementation CCs aka Unassigned CCs" Review. (SEE WORKBOOK PAGE UNASSIGNED CHANGE CONTROLS) | TX SET members to review all "Unassigned" Change Controls at future meetings. | TX SET will begin to work on the Future Version of the I.Gs using the Unassigned change controls in this next release. | Closed | 2004-06-23
February |  | TX SET |  | Revised Working Group Procedures | TX SET members should review the Working Group Procedures Redline | Comment 5/19/04: TX SET reviewed the WG procedures they will be posted for review. WG procedures to be an agenda item at the June meeting. (6/23/04) Approved with changes on June 22, 2004- | Closed | 2004-06-23
April |  | TX SET Chair |  | ERCOT should not be completing Safety Net MVIs without electronic trx. |  | TX SET presented this back to RMS in its RMS report at the May '04 Meeting. It was TX SETs opinion that all MPs and ERCOT who participate in the Safety Net process should follow the approved guidelines. | Closed | 2004-06-23
April |  |  |  | REF~1P removal issue | CRs will discuss and frame issue prior to this becoming a TX SET agenda item. | TX SET discussed at the April meeting, the REF~1P change control was withdrawn. | Closed | 2004-06-23
April |  | ERCOT |  | 814_07 Rejects | ERCOT to develop a proposal for handling 814_07 rejects. | (6/24/04) Suzette Wilburn brought recommendations to TX SET on this. | Closed | 2004-06-23
2004-05-01 |  | ERCOT |  | ERCOT service orders completed without transactions | ERCOT to draft proposal to TX SET for reporting back to RMS | (6/23/04) ERCOT to bring back information to next TX SET meeting regarding instances where complete w/out trx occurs. | Closed | 2004-08-17
2004-05-01 |  | TX SET |  | Flag on 814_24 for instances where the first is '09'd and a second is sent | Suzette Wilburn, Kyle Patrick, Charlie Bratton, Kathy Scott to review 824 Workshop documentation and begin drafting new codes | (6/23/04) Team has not met. (8/17/04) Change Control has been written and update for discussion and approval on 8/18/04 | Closed | 2004-08-17
2004-05-01 |  | RMS |  | TDSPs to document estimation processes |  | (6/23/04) TDSPs did so at June meeting. TX SET chair to either report or request time to report to RMS at July meeting. | Closed | 2004-08-17
2004-05-01 |  | Customer Protection |  | Customer Protection compliance | Bill Reily and Charlie Bratton to organize TDSP/CR reviews of the rule | (6/23/04) Bill and Charlie to bring back report to a next TX SET meeting. (8/17/04) Subteam assigned to discuss issues and make recommendations | Closed | 2004-08-17
2004-05-01 |  |  |  | Change Control 503 | Bill Reily to draft change control | (6/23/04) Bill will draft CC prior to CC deadline for next release. | Closed | 2004-08-17
2004-05-01 |  | TXU ED |  | 867_02 large file of data | Bill Reily to bring recommendation to June Meeting | (6/23/04) Bill will bring back suggestion at a later meeting. (8/17/04) TXU ED will send additional files similar to the same process as CNP | Closed | 2004-08-17
2004-06-01 |  | CNP |  | 867_03 BPO - additional create 867_03 scenario examples to be incorporated along with gray-box changes to create one change control for the 867_03 Implementation guide | Suzette Wilburn, Tom Baum, and Kathy Scott to draft document | (6/23/04) Due to length of this document and the number of changes included in the redline version, a review of this document will be deferred to the next Texas SET meeting for discussions. The updated document will be included in the minutes for SET Mem | Closed | 2004-08-17
2004-07-01 |  | TX SET Sub-team |  | TX SET Subteam will discuss and develop change controls for the 814_24 (TITF Taskforce), 824 and 810_02 (810/867/824 Taskforce), 650_01 (DNP/Reconnect Taskforce) and Redlines for BPOs process changes | Shannon Bowling, Suzette Wilburn, Kyle Patrick, Cary Reed, Charlie Bratton, Brett Harper, Bill Reily, Tom Baum, Robert Rodriquez, Kathy Scott | (8/17/2004) This action item includes several other action items- to eliminate redundancy this one was closed | Closed | 2004-08-17
2004-07-01 |  | RMS |  | TX SET - Discuss an Implementation Timeline for: 810 Billing Determinants for 810/867/824 Workshops Additional SAC04 Codes requested by CNP at July RM |  | (8/17/2004) This action item includes several other action items- to eliminate redundancy this one was closed | Closed | 2004-08-17
2004-07-01 |  | DNP Taskforce |  | TX SET Sub-team develop draft straw man of adding 3 new codes into the current YNQ Segment where CRs must give TDSPs the autohrization to Disconnect service for non-payment at one of the following disconnect points: | Shannon Bowling, Suzette Wilburn, Kyle Patrick, Cary Reed, Charlie Bratton, Brett Harper, Bill Reily, Tom Baum, Robert Rodriquez, Kathy Scott | (8/17/2004) Change Control already written and up for discussion and approval on 8/18/2004 | Closed | 2004-08-17
2004-07-01 |  | Jennifer Teel- EC Power |  | Change Control needed on the 814_02 Transaction LIN Segment for SW data element - Gray Box Clarification needed to remove or eliminate the statement DTM~MRR is required when requesting an off-cycle read. There is no DTM~MRR segment in the 814_02 transa | Suzette Wilburn and Tom Baum | (8/17/2004) Change Control already written and up for discussion and approval on 8/18/2004 | Closed | 2004-08-17
2004-07-01 | PUCT Staff | Customer Protection |  | Lauren Damen (PUCT Staff) reqeusted that Bill Reily (TXU ED) re-send the same email that was forwarded to Brian Lloyd to her attention for clarification concerning competitively sensitive information regarding historical usage for C&I customers | Lauren Damen and Bill Reily | (8/17/2004) PUCT Staff provided Clarification to Bill Reily on this action item | Closed | 2004-08-17
2004-07-01 | TDSP | ERCOT |  | Follow-up 814_20 move the REF~LO Load profile from Meter level to ESI ID Level, however the 814_20 guide has load profiles communited at a meter level. TDSPs will review the proposed chane controls to move the load profile segement from the NM1 loop in | TDSPs to provide an update to this question | (8/17/2004) TDSPs agreed that this is not an issue and there should not be any market reason to make this change | Closed | 2004-08-17
2004-04-01 | MOU/EC | TX SET |  | Change 814_28 to allow move-in to be pended because customer is not a member of the co-op. | High Priority | (6/23/04) Redlined document posted to May meeting documents (08/17/04) No progress yet | Closed | 2004-10-12
2004-04-01 | MOU/EC | Austin En |  | Change 820_03 to allow for a code to reference a credit pmt. | N/A | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discus | Closed | 2004-10-12
2004-04-01 | MOU/EC | Nueces |  | Change 820-payment adjustments 6000 record to allow credits and debits in the total payment field for the batch total. | High Priority | (6/23/04) No progress yet Update 08/25/04 -Change control 2004_607 already | Closed | 2004-10-12
2004-04-01 | MOU/EC | Austin En |  | Change 810_03 to include information on deferred payment agreements that CR has set up with customer. | N/A | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discuss o | Closed | 2004-10-12
2004-04-01 | MOU/EC | Austin En |  | Change 810_03 to include reasons for cancel (BIG segment): usage or monetary correction. Similar to changes that were made to 810_02. | N/A | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to disc | Closed | 2004-10-12
2004-04-01 | MOU/EC | CPS |  | Why can't a 814_01 originate from the MCTDSP since customer remains with MCTDSP? | N/A | (6/23/04) No progress yet Update 08/25/04 - This was not the decision made by the Market prior to Open Competition and was not chosen to be the Current Market model. | Closed | 2004-10-12
2004-04-01 | MOU/EC | LCRA |  | With exception of PC & PD, all other 814's go through ERCOT. Since MOU/EC don't unbundled, why do 814's still need to go thru ERCOT? Same question with 867's? Since CR and TDSP functions handled at same office? | High Priority | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to dis | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | If customer calls TDSP first, can there be an enrollment from the TDSP. Can the TDSP go ahead and set up customer? Since other city services need to be set up? -Responses - lots of discussion about scheduling power, how can you without CR, etc. | N/A | (6/23/04) No progress yet Update 08/25/04 - This was not the decision made by the Market prior to Open Competition and was not chosen to be the Current Market model. | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | Make 814_PC bi-directional. | High Priority | (6/23/04) No progress yet - Update 08/25/04 - Change control will be written to allow the 814_PC to be bi-directional only for MOU/EC Markets. Note | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | In MOU/EC T&C's - city services also paid 1st, or just electricity? -ACTION ITEM - read/interpret T&C's | N/A | (6/23/04) No progress yet Update 08/25/04 - This is not a Texas SET issue | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | More than move-in, would like to see bi-directional move-out. For forwarding of final bill, capital credits check, etc. | High Priority | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discuss or provide any information as to the problems, issues, and possible recommendations for this issue | Closed | 2004-10-12
2004-05-01 |  | 810/867/824 Taskforce |  | 824 new codes | Suzette Wilburn, Kyle Patrick, Charlie Bratton, Kathy Scott to review 824 Workshop documentation and begin drafting new codes | (6/23/04) Team has not met. (8/17/04) Sub-team planning on meeting, hopefully for 8/24/04 meeting in Houston 10/12/04 - Draft Change Control written and discussed by SET | Closed | 2004-10-12
2004-05-01 | TDSP |  |  | 650_01 1 to 1 relationship | TDSPs to verify that they are responding the 650_01s on a one to one relationship and bring back at June Meeting | (6/23/04) Cary Reed to refer this to Blake Gross and Shannon Bowling (DNP/REC TF). Also change control 2003-496 should clear this issue up. (8/17/04) Cary Reed, Suzette Wilburn and Kathy S | Closed | 2004-10-12
2004-05-01 |  |  |  | 814_28 redline document MOU/EC | TX SET to document the different scenarios that would be affected by membership codes suggested for the 814_28 | (6/23/04) The TDSPs will get together along with MOU/EC to make a list of the Reasons for Pending a Move-In or Move-Out to cover the majority or the higher percentage of reasons for pending a request. Cary Reed will send an open invitation to Eloise and | Closed | 2004-10-12
2004-07-01 |  | TX SET Leadership |  | PRS will have their Annual Budget Priorization meeting scheduled August 27, 2004 where TX SET Leadsership will ask for a spot on this meeting's agenda. Tenative Schedule for TX SET for 2005 (4th Quarter Implementation) and a list of approved change contr | Kyle Patrick, Kathy Scott and Bill Reily - TX SET Chair and Vice Chairs | Leadership attended the Annual Budget Priorization Meeting and Texas SET 2.1 has been placed as high priority for 2005 ERCOT Budget | Closed | 2004-10-12
2004-07-01 | Market |  |  | TX SET representatives will go back to their companies to review the approved gray box/example change controls and come back with any concerns for updating the guides with these approved change controls for version 2.0A release schedule |  | Change Controls for version 2.0A have been completed and agreed to by Texas SET | Closed | 2004-10-12
2004-08-17 | TDSP/MOU/EC |  |  | (6/17/2004) Initial discussion has been to change 814_28 to allow move-in to be pended because customer is not a meter of the co-op. With an interval of time expiring and 814_08s being sent for membership fees not sent to the MOU/EC - | Cary Reed will organize a second meeting with the TDSPs and MOU/EC to discuss and flush out issues with using either the 814_28 or 814_04 transactions for membership fees and assigned membership numbers for those customers that have been established as me | Sub-team meeting scheduled August 25 and 26, 2004 in Corpus Christi, Texas - Sponsored by AEP (Cary Reed) Sub-team members/participants: Bernie Dawson, Bill Reily, Eloise Flores, Cary Reed, Bre | Closed | 2004-10-12
2004-08-17 |  | RMS |  | Update on service address comparison request. Identifying how large the issue is with regard to the service address sent on the initiating transactions and what is received on the 814_04 from the TDSPs | ERCOT completed query for the month of July-found 30,000 records- Suzette Wilburn (ERCOT) will breakout these 30,000 ESI IDs into subsets by TDSP territory to be distributed by end of next week. A sample will be taken from this sub-set to determine exte |  | Closed | 2004-10-12
2004-08-17 |  |  |  | Time Table and/or schedule for v2.1 Change Controls | Suzette Wilburn and Tom Baum (ERCOT) will work on developing a time time and/or schedule for v2.1 Change Controls, Communications, Baseline of Implementation Guides, and Posting to ERCOT web-site for updated guides |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2004-597 was marked as a graybox change. This requires adding a new code to the 814_13. Should be marked as system change |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2004-610 request additional language to the 810_02. Now tha we are removing the BPOs, we need to make sure this language was captured in the guide and discuss submitting this CC to be nullified. Charlie Bratton and Jason Bear will create a change con |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2003-496 adds clarificatoin to the 650_02 for disconnects. TX SET will need to review the content of this change contol to determine if it is still valid. |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2003-538 updates examples in the 867_03 but this is marked as a system change. Need to re-classify as gray box/example change. |  | Closed | 2004-10-12
2004-08-17 | TX SET Leadership |  |  | What is the process or procedure for Market participants to take when a Market participant is not following Market Guidelines or Rules? | TX SET Leadership has a question of RMS Leadership | (10/12/04) Kathy Scott will take request to Lon Conn and Karen Farley to add this process to the RMS Assignment Form | Closed | 2004-10-12
2004-08-25 | MOU/EC |  |  | Need to re-visit 2004_609 for Reconnect after Disconnect for Non-Payment | High Priority | 08/25/04 -Bernie Dawson will rework change control 2004_609 to apply correct ANSI standards for Reconnect processing by MOU/EC (10/12/2004) Bernie Dawson provided this change control to Texas SET and some revision were made by the team. Bernie will | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: | The 810/867/824 Workshop Taskforce agreed that extending the 2 day timeframeto 5 days will fix several validations and rejcection problems created by enrollment transacations missing or delayed The agreement by the TDSPs would be the 2 day rule WILL be | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: | The 810/867/824 Workshop Taskforce agreed that extending the 2 day timeframeto 5 days will fix several validations and rejcection problems created by enrollment transacations missing or delayed The agreement by the TDSPs would be the 2 day rule WILL be | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: | The 810/867/824 Workshop Taskforce agreed that the Stacking Solution is designed to fix this with a response driven cancel process for all cancels. TX SET should re-visit this in six months to a year AFTER stacking has been implemented for evaluation th | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: | The 810/867/824 Workshop Taskforce agreed that extending the 2 day timeframeto 5 days will fix several validations and rejcection problems created by enrollment transacations missing or delayed The agreement by the TDSPs would be the 2 day rule WILL be | 10/12/2004 Draft Change Control was created to provide new rejection code to providing this information | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | Dates Don't Match or New CR COMMENTS: | For inadvertent switches, the Inadvertent switch task force will handle the resolution. Remainder should be deferred and governed by the PUC ruling around this issue Re-evaluate after MIMO implementation | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-07-01 | TDSP | RMS |  | TDSPs look at the reasons why estimations are being created, if reason is flagged into any internal systems? What are some of the options for CRs when consecutive estimates are encountered? Discussion was to consider a new segment in the 867_03 and 867 | 09/22/04 Update: Sub-team was asked by Texas SET to add general guidelines in the event of a estimated usage for both CR and TDSP . This information will be brought back to the October TX SET meeting and possibly presented at the October/November RMS | (10/12/04) Update - Bill Reily will be placed on the November 2004 Texas SET agenda to discuss the recommendations of the subteam to Texas SET (1 | Closed | 2004-11-17
2004-07-01 |  | DEWG |  | Linked ESI ID issue- TX SET needs to determine how the TDSPs use the address field in the 814_04, is it echoed back from the 814_03 or do they pull the actual service address from their systems. Note: Where requirements are identified for flushing ou | ERCOT will look into whether this type of information can be obtained | (8/17/2004) Update will be provided to TX SET at the September Meeting - Plan is to take a sample of July's 814_04 to determine where the problems may be initiated (10/12/04) Update - Meeting will be arranged with ERCOT and TDSPs prior to the November 200 | Closed | 2004-11-17
2004-09-22 |  | ERCOT |  | There has been 867_03F showing up on the ERCOT 867 Error Report that is sent to the CRs and TDSPs that have the same date in the DTM150 and DTM151 segments | ERCOT would like to find out what type of scenario would cause this and let the market know that ERCOT is not loading this data, and it doesn't appear that corrected usage was sent | 11/17/2004 Tom Baum reviewed with the group that the TDSPs who were identified as sending the same date in the start and stop time segments. All TDSPs had identified that 867s sent were sent in error and were corrected. TX SET agrees that Start and St | Closed | 2004-11-17
2004-09-22 | MOU/EC | Eloise Flores |  | MOU/EC will need a way to identify the membership number in all EDI Transactions | Change control will need to be written to apply to all EDI transaction to add a new REF Segment (REF~1W) for all EDI transactions that will be used to pass the membership number | (11/17/2004) Closed | Closed | 2004-11-17
2004-09-22 |  | ERCOT |  | Change Control 2004-636 Withdrawn Written to remove the Business Process Ov | Suzette Wilburn and Johnny Robertson will work together to provide a revised change control to remove the BPO from the 814_20 Implementation Guide. | (11/17/2004) Closed- Suzette and Johnny will submit Change Control for approval | Closed | 2004-11-17
2004-09-22 | TDSP | ERCOT |  | How do TDSPs communicate a meter removal on an 867_03? Can ERCOT expect to receive a D | TX SET representatives will check to see if sending a DTM150/DTM 151 with the same date is valid | 11/17/2004 - Change control already written to clarify this process, also currently ERCOT has removed validation process or SIR that rejected these scenarios until this change control is implemented | Closed | 2004-11-17
2004-09-22 | ERCOT | TX SET |  | TX SET requested and required that TX SET be involved in defining the requirements that are used to write the ERCOT SIRs. | ERCOT (Suzette Wilburn) noted that they would include TX SET when writing the requirements and text for the SIRs prior to them being implemented. TX SET also discussed the need for TX SET involvement in the Retail Market Call for those instances when an | 11/17/2004 Closed action item and this information will be added to our Working Group Procedures documentation | Closed | 2004-11-17
2004-10-12 |  | Direct Energy |  | Reject for Original Tracking Number from the originating transaction be provided on the 867-03 Final to provide issuing the 824 Reject transaction | Rita Morales will work with Suzette Wilburn to examine some real instances that apply to this scenario for ERCOT investigation and for Direct to provide some information to other CRs on how they are handling this particular scenario. | (11/17/2004) Closed by Rita Morales | Closed | 2004-11-17
2004-10-12 | Texas SET | ERCOT |  | Request from ERCOT to investigate the FasTrak Inadvertant issue | Texas SET Sub-team will work to investigate ERCOT's recommendations: Kyle Patrick, Suzette Wilburn, Charlie Bratton, Cary Reed, Tom Baum, Rob Bevill, Johnny Robertson, Kathy Scott | (11/17/2004) Closed | Closed | 2004-11-17
2004-10-12 |  |  |  | Change Control 2004-644 Removed the Transformer Loss Adjustment codes TA-TE to approve Change Control | TDSPs will need to discuss that if these codes are necessary for the 810 Billing Determinants - CRs will complete and internal evaluation as well. If it is found to be of value by either side then a change control will be prepared for November 2004 Change | (11/17/2004) Closed and if needed a new change control will be written to submit to Texas SET adding the Transformer Loss Adjustment codes | Closed | 2004-11-17
2004-04-01 |  |  | DNP Taskforce Recommendations | DNP Taskforce to hand off deliverables | (8/17/04) Taskforce still in working and all deliverables jest to be delivered (10/12/04) Change Control written and approved for priority disconnect procedures. There maybe additional change contro | Closed | 2005-01-27
2004-04-01 | MOU/EC | Austin En | Change 810_03 to separate cancel examples into a 3-step process: (1) original (2) cancel (3) re-bill. Similar to changes that were made to 810_02. |  | (6/23/04) No progress yet Update 08/25/04 -Bernie Dawson and Kathy Scott will work to create new e | Open
2004-04-01 | MOU/EC |  | Change 814_18 to handle co-op membership requirements. Landlord billing information. | Low Priority | (6/23/04) No progress yet Update 08 | Closed | 2005-01-27
2004-05-01 |  |  | 864 straw dog example | Johnny Robertson and Cary Reed to draft example | (6/23/04) In progress, expect report in August or September. (8/17/04) Cary and Johnny should be able to provide this information at the September meeting (10/12/04) Cary and | Closed | 2005-01-27
2004-05-01 |  | Mass Transition Taskforce | Mass Transition Phase 1 |  | (6/23/04) To be addressed along with MT Phase II (8/17/04) Phase II Meeting has been scheduled 9/30/04 at ERCOT Met Center Room 168 (11/17/2004) Still open for discussion and Phase II recommendatio | Open
2004-05-01 |  | CNP | 814_21 pass-through to TDSP | Kathy Scott to create draft change control for updating the 814_20 business process | (6/23/04) Kathy submitted the CC at June TX SET (8/17/04) TX SET Sub team had a meeting in Dallas on July 12, 2004. TX SET is waiting for respons | Open
2004-07-01 |  | TX SET Leadership | Action Items List |  | (6/23/04) Leadership will provide a printed copy of the most recent list of Outstanding Action items at each TX SET meeting. | Closed | 2004-11-17
2004-07-01 | TDSP | RMS | TDSPs look at the reasons why estimations are being created, if reason is flagged into any internal systems? What are some of the options for CRs when consecutive estimates are encountered? Discussion was to consider a new segment in the 867_03 and 867 | 09/22/04 Update: Sub-team was asked by Texas SET to add general guidelines in the event of a estimated usage for both CR and TDSP . This information will be brought back to the October TX SET meeting and possibly presented at the October/November RMS | (10/12/04) Update - Bill Reily will be placed on the November 2004 Texas SET agenda to discuss the recommendations of the subteam to Texas SET (11/17/04) - Closed, TX SET will discuss further adding a reason code | Closed | 2004-11-17
2004-07-01 | CR | RMS | CRs what are you doing when you receive an 867_03 transactions with the Estimation Flag indicated in the transaction, as well as, the MEA Segment flag showing EE (Meter reading-beginning estimated/ending estimated) previous and current billing estimated. | 09/22/04 Update: Sub-team was asked by Texas SET to add general guidelines in the event of a estimated usage for both CR and TDSP . This information will be brought back to the October TX SET meeting and possibly presented at the October/November RMS | (11/17/2004) Still open for further discussion and CR responses | Open
2004-07-01 |  | DEWG | Linked ESI ID issue- TX SET needs to determine how the TDSPs use the address field in the 814_04, is it echoed back from the 814_03 or do they pull the actual service address from their systems. Note: Where requirements are identified for flushing ou | ERCOT will look into whether this type of information can be obtained | (8/17/2004) Update will be provided to TX SET at the September Meeting - Plan is to take a sample of July's 814_04 to determine where the problems may be initiated (10/12/04) Update - Meeting will be arranged with ERCOT and TDSPs prior to the November 200 | Closed | 2004-11-17
2004-08-17 |  | RMS | Texas SET v2.1 to be Redline |  | (11/17/2004) initial discussion of v2.1 change controls scheduled for December 2004 TX SET Meeting | Open
2004-08-17 |  | RMS | Customer Protection Rules as per discussions with PUCT Staff. Need to develop a process to support Customer Protection Rule 25.472 Section b Paragraph 3 | Bill Reily will lead a TX SET sub-team to address issues and what is needed to support Customer Protection Rule for Historical Usage for Commercial and Industrial retail customers where usage is considered competitively sensitive. | (10/12/2004) Bill Reily and Texas SET is awaiting guidance from PUCT Staff (Lauren Damen) on this Action Item (11/17/2004) Still pending PUCT answers back to TX SET - This will be moved to an agenda item for Decembe | Open
2004-08-17 | TX SET Leadership |  | Should there be some documented procedures for Market participants to communicate non-emergency system/process and/or procedure changes? | TX SET Leadership has a question of RMS Leadership Communicating Market information - Who does what, when (how early, deadline, or timelines) and how should information be communicated. | (10/12/04) Kathy Scott will take request to Lon Conn and Karen Farley to add this process to the RMS Assignment Form (11/17/2004) Still open to be discussed with the Communications Taskforce of COPS to outline the details of communicat | Open
2004-08-17 |  | ERCOT | If an 814_20 maintain is sent (ASI~7~001) is it expected that there will always be a REF~TD (reason for change) present, either at the header level (LIN Loop) or meter level (NM1 Loop)? | CR's will check to see if they expect a REF~TD when an NM1~MX exists. REF~TD validation cannot be added to the ASI segment. | (10/12/04) To be discussed at the November 2004 Texas SET Meeting (11/17/2004) ERCOT and CRs will need to get together to determine what should be accepted on the 814_20- REF~TD Reason for Change | Open
2004-08-25 |  | ERCOT | In an effort to address 814_23 rejects ERCOT has created reports, by CR, that list the 814_23 rejects received, with the reject reason. The data pulled is from June 03 to current. ERCOT would like to take the same approach as used for the 814_21 reject | ERCOT (Suzette Wilburn and Tom Baum) will compile the results from 814_23 reject to send to the CRs for additional information as to the reasons for the rejection. This will only be analysis and fact finding to resolve the issue of receiving these type r | (10/12/04) ERCOT will bring post MIMO data to the January 05 TX SET Meeting (11/17/2004) Still open time for January discussion 1/27/05-0discussed at Dec 2005 TX SET. Action itemno longer necessary | Closed | 2005-01-27
2004-08-31 | MOU/EC |  | If MOU/EC has disconnected services for Non-Payment for a customer is there a possiblity that the CR would send a MVO for the customer based upon the DNP being completed. Customer may come in to pay outstanding bill to MOU/EC but the ESI ID has been fin | Nueces - will monitor this process to determine if a change control is needed | 08/25/04 - Nueces - will monitor this process to determine if a change control is needed (11/17/2004) Continued Discussion | Open
2004-09-22 |  | Market Rules | Diana Zake is sending out a request for TX SET representatives to attend a meeting on October 5th to review the reamil market-operating guide | Request that Market participants including Texas SET members assist in making revisions/updates and reformatting Retail Market Guide along with it's associated documents | 11/17/2004 - Kyle has sent scope and procedures document need to send change control documentation 1/27/05- RMG TF working to complete changes to the guide. | Closed | 2005-01-27
2004-09-22 |  | BJ Flowers | CNP's Process: for MVI and MVOs with the two day window, CRs submit the current FasTrak spreadsheet directly to CNP that would normally be sent as a FasTrak to the TDSP. CNP then submits an 814_28 Complete Unexecuteable '09' to cancel order using automa | BJ Flowers is requesting other TDSPs to review this change in process made by CNP for handling MVIs and MVOs with the two day wind and to consider implementing this new process. CRs are requesting consistency in this process. | 11/17/2004- Discussion at this time was that AEP, TNMP, and TXU ED have evaluated what could be done internally, however each could not make a definite commentment as to when this process could be done. | Open
2004-10-12 |  | Constellation | Usage Smoothing- What does each TDSP do? Cancel/Rebill True-up in subsequent cycles Other? | Robert Rodriguez will lead a small group of CRs to document the questions that need answering by the TDSPs concerning cancel re-bill procedures, smoothing, and zero usage. Sub-team: Kyle Patrick, Charlie Bratton, Rob Bevill | (11/17/2004) Continued Discussion 1/27/05 - CR provided list of questions for TDSP to respond to. This will be discussed at the Feb TX SET Mtg | Open
2004-10-12 | ERCOT | Texas SET | What is the appropriate process for cancelling DROP to AREP based upon version 2.0 and Protocols. | Because the Implementation Guide for the 814_08 is out of Synch with the documented procedures for a CR to Cancel a Drop to AREP in Protocols in Chapter 19 - Suzette Willburn (ERCOT) will investigate if ERCOT and/or James Cohea's group can provide a stan | (11/17/2004) TX SET has a question to PUCT Staff on this process: Question: Is PUCT Staff OK if we use existing market design and rules for transactions processing during the evaluation period | Closed | 2005-01-27
2004-11-17 |  | Texas SET | Multiple ESI IDs assigned to a single address- Is there any way an address and/or ESI can be uniquely identified to know what is being servicec? Example Guard Light, Barn, Residence, Garage/Tool House. |  |  | Open
2004-11-17 |  | Robert Rodriguez | Robert Rodriguez will hold another conference call to discuss examples and develop a white paper of specific questions on what CRs would like to know with regard to the smoothing process at each TDSP. | Robert Rodriguez will host another conference call to discuss CR examples. Cycles affected by the smoothing/pro-rating/cancel-rebilling. These examples will be forwarded to both ERCOT and the TDSPs. CRs will then review the TDSP estimation procedures an |  | Closed | 2005-01-27
2004-11-17 |  | ERCOT | Currently ERCOT checks the dates on the initiating transactions (16, 24) to make sure they are within the appropriate windows (no more than 90 calendar days in the future or 270 calendar days in the past). Want to find out if TX SET is in agreement to ad | TX SET agrees with adding the date reasonableness validation to the 814_12. ERCOT will write the SIR that will be presented on the Retail Market Call. |  | Open
2004-11-17 |  | Texas SET | 814_28 unexecutables come through for a MVI service order with a MVO in the LIN07 and a MVO action code (ASI02=002). | TX SET recommends that the ERCOT hold off on adding the validation through an internal SIR. ERCOT will write a change control to update the 814_28 guide to remove the LIN07 and make the Action Code ASI segment generic to prevent 814_28s from being reject | 1/27/05 - CC was submitted and withdrawn, this action item remains open for discussion | Open
2004-11-17 |  | ERCOT | In the DTM~649 segment of the 867_03, the IG says that this segment is required when the Bill Type is LDC, but later in the gray box it states ‘not provided on cancel transactions’. Should this segment be included on a MOU/EC 867_03 cancel transaction? C | TX SET agrees that the language needs to be updated. ERCOT will write a change control to remove the requirement that the DTM~649 is not required when sending 867_03 cancels, when the BPT=01 | 1/27/05 - MOU/Ecs have sponsored a future change control to update the inconsistencies in the guide. | Closed | 2005-01-27
2005-01-05 |  | TX SET | TX SET Representative to review the proposed TX SET WG Procedures and bring suggestions to the Febuary TX SET Meeting. | TX SET reps to determine their definition of an 'Emergency' Change Control. Also review redlined TX SET WG procedures posted to the January 2005 Meeting Minutes and bring comments/suggestions to the February TX SET meeting. | 02/28/05 - Still need to finalize and approve redline changes | Closed
2005-02-28 |  | SET Leadership | TX SET reviewed 019RMGRR – Meter Estimation text. Edits made to document noting current TDSPs processes, broken down by TDSP | Action Item: TX SET Leadership will submit the revised RMGRR-019 document to the Market Rules team for distribution to the Market for comments and RMS recommendation for approval | 03/01/05 - Task completed and turned over to Market Rules team for communicating to Market for comments | Closed
2005-02-28 |  | ERCOT | Update on TDSP Rejects for DUPLICATES. From the January meeting, TDSPs were going to follow up on what they validate on to determine a Duplicate and what they are expecting ERCOT to do with this information. | Action Item: ERCOT will bring examples to the April TX SET meetings of any use of the ‘ABN’ reject reason to determine approach for process in handling the ABN code. | 03/01/05 - Answer that any reference to TDSP also included both IOU and MOU/EC | Closed

## Future CCs
Change Controls Slated for "Future Implementation"
Change Control # | Requestor | Description | Transactions | Notes
2003-497 | Ed Skiba | Remove “ZIP” from the REF02 of the REF~7G segment (Rejection Reason). | 814_PD
2003-498 | Ed Skiba | Update 814_PC based on 814_PC sub-team recommendations which were evaluated by TX SET Working Group on February 11, 2003. | 814_PC
2003-532 | Johny Roberstson | This change will provide the CR who submitted a switch with a Meter Ownership Type code to remove a gap in the guideline when “Change Meter Owner”. | 814_04, 814_05
2004-669 | Tom Baum | Update the REF~BLT segment details of the 814_03 to indicate that this segment will not be sent on an 814_03 when it is the result of a MVO to CSA. | 814_03
2004-672 | Tom Baum | Add gray box language to the REF~1W segment (see Change Control 2004-649) to state that only number and alpha characters will only contain uppercase letters (A to Z) and digits (0 to 9). Note that punctuation (spaces, dashes, etc.) must be excluded. | 814_01, 814_03, 814_04, 814_05, 814_08, 814_10, 814_14, 814_16, 814_24, 814_PC, 650_01
2004-674 | Tom Baum | Remove the BPO from the 867_02 and add applicable information back into the appropriate segment gray boxes of the guide. | 867_02
2004-676 | Tom Baum | Remove the BPO from the 824 and add applicable information back into the appropriate segment gray boxes of the guide. | 824
2004-678 | Tom Baum | Update the Example on the 814_22 Implementation Guide to remove the unmetered REF~PRT segment (Unmetered Service Type) since there is already a metered segment in the same NM1 loop. Both Metered and Unmetered Services cannot be sent in the same NM1 Loop. | 814_22
2005-687 | Suzette Wilburn | Add the reject code ‘NFI’ to the list of acceptable reject codes in the REF02 of the 814_19 REF~7G. | 814_19

## Version 2.1 CCs
Change Controls Slated for Version 2.1 Implementation
Change Control # | Requestor | Description | Transactions | Notes
2002-466 | Ed Skiba | Add code to the 650_04 to provide a means for the TDSP to inform a CR that the service is being permanently suspended for an ESI ID. Also add suspension code to indicate that facilities have been removed from the ESI ID. | 650_04
2002-468 | Tom Jackson | The entire 810_03 Implementation Guide was reviewed for completeness, accuracy, and consistency at TX SET meeting 11/06/02. | 810_03
2003-471 | Ed Skiba | Remove the “Must Use” from the YNQ04 of the YNQ~5U segment | 650_04
2003-490 | Ed Skiba | Remove QTR from valid values of Meter Type | 814_14, 814_22
2003-493 | Dave Odle | Currently, there is a disparity between the 814_26 (Adhoc Historical Usage Request) and the 814_27 (Adhoc Historical Usage Response). The N1~8S (TDSP Loop) is OPTIONAL on the 814_26 but the same N1~8S (TDSP loop) is REQUIRED on the 814_27. This change Control is to correct the inconsistency for business and technical purposes. | 814_27
2003-496 | Ed Skiba | Provide additional detail on when the 650_02 should be generated and how the process should work for disconnect and reconnect for non-pay. | 650_02
2003-503 | Kathy Scott | Allow the TDSP to send a corrected invoice when the correction does not involve meter readings, dates, or consumption | 810_02
2003-517 | Bill Reily | Existing Table codes inadequate for providing CR and end use customer reasons for TDSP’s “Complete Unexecutable” | 814_28
2003-527 | Bill Reily | Existing Table codes inadequate for providing CR and end use customer reasons for TDSP’s “Complete Unexecutable” | 650_02
2003-569 | Suzette Wilburn | Provide gray box clarification to the LIN segment to indicate that the Texas Market supports only 1 LIN loop per EDI Transaction. | Entire 814 Series 01-29, PC and PD
2003-571 | Jennifer Teal | Move segment gray box verbiage for A78 being used only by ERCOT and TDSP to gray box on actual code | 814_09, 814_13
2003-572 | Jennifer Teal | Add the short title “Earliest Available Switch Date” to the EAS Reject code (REF*7G) | 814_13, 814_02
2003-576 | Johny Roberstson | 1. Change gray box In the REG = IX, 4P, MT, To NM1 = MQ, Required 2. Add examples | 814_20
2003-578 | Jennifer Teal | Added a new change Code to indicate the annual Load Profile changes | 814_20
2003-582 | Kyle Patrick | Add verbiage to the gray box in the “TWO” status reason code to include references to the Switch and Drop processes. Add code “B30” to the list of acceptable codes. | 814_08
2003-590 | Mark Malinak | Add a new code for a reject generated within ERCOT. Please add the B34 - Customer Notification Name and/or Address Invalid or Missing to the 814_21 REG~7G. | 814_21
2004-596 | Kathy Scott | This change control provides the Market with the appropriate timing procedures as to when the CR should provide an 814_PC Maintain Customer Information Request to the TDSP. | 814_PC
2004-597 | Kyle Patrick | Add RNE to list of status reasons in the REF~7G | 814_13
2004-601 | Suzette Wilburn | Add new reject code ‘ICD’ the list of reject codes in the 814_13 | 814_13
2004-604 | Suzette Wilburn | The gray boxes in CC2003-400 were written such that the ‘OA’ code will be sent on every response from the TDSP, reject or accept. This needs to be changed to only send the ‘OA’ code on rejects to be consistent with CC2003-401, which is the same change for the 814_11. | 814_09, 814_13, 814_25
2004-607 | Bernie Dawson | changes to the 820_03 transaction are needed to add data elements/segments to accommodate payment adjustments to the CR when payments are adjusted on the customer’s Muni-Co-op account due to being applied to an incorrect account, for the wrong amount, or in the case of a returned check | 820_03
2004-616 | Suzette Wilburn | Add ‘SBD’ Reject code to the 814_11 | 814_11
2004-624 | Kyle Patrick | Incorporate the Business Process Overview to the 650_02 Implementation Guide. Remove the Business Process Overview from the 650_02 transaction. | 650_01
2004-627 | Kyle Patrick | Incorporate the Business Process Overview to the 820_02 Implementation Guide. Remove the Business Process Overview from the 820_02 transaction. | 820_02
2004-629 | Tom Baum | Update the 650_01 YNQ (Premium Disconnect Location) YNQ09 PDL graybox and add 2 addition codes in the YNQ09 to give the TDSP clear instructions as to what charges the CR has agreed to pay. | 650_01
2004-631 | Tom Baum | Remove the A75 reject code on the 814_04 as it is no longer needed. | 814_04
2004-632 | Tom Baum | Add a new code to the REF~1P status reason segment in the 814_24 that will be used by CRs when submitting a second MVO that will communicate to the TDSP to do whatever is necessary to turn off the power...per the CRs request. The code should include in a gray box to indicate that this is the second MVO requested by CR. | 814_24
2004-635 | Kathy Scott | CNP request the addition of (6) new SAC 04 codes to be added to the 810 Invoice transaction because of pending True-up filings currently before the Commission. This will allow these new tariffs and/or charge off allowances to be appropriately identified within the invoice transaction. | 810_02
2004-639 | Brett Harper | Add two codes to the existing approved reject codes for 824. | 824
2004-642 |  | Update the 814_08/814_09 IG transaction flow to indicate the 814_08 can be used to cancel a drop to AREP | 814_08, 814_09
2004-643 |  | Update the 820_02 IG to provide clarification on how decimals are used in the BPR02 & RMR04. | 820_02
2004-644 |  | Update SAC09 code list for the Billing Determinants | 810_02
2004-645 | Tom Baum | Additional Codes added to the TED Segment and grayboxes updated in the 824 per the 810/867 Workshop | 824
2004-646 | Tom Baum | Add the REF~BLT (Billing Type) segment to the 814_18 in order to support multiple billing types in MOU/EC territory. Also update examples to include this required segment. | 814_18
2004-649 | Bernie Dawson | Add membership ID to numerous TX SET transactions to support Muni/Co-op business requirement to positively match all move-in, move-out, and switch requests to an existing MCTDSP membership/account. | 814_01, 814_03, 814_04, 814_05, 814_08, 814_10, 814_14, 814_16, 814_24, 814_PC, 650_01
2004-650 | Bernie Dawson | Make 814_PC and 814_PD transactions bi-directional to allow MCTDSP to send updated customer information to the CR and to allow CR to respond to MCTDSP. In the MOU/EC market, the MCTDSP will be doing consolidated billing unless the customer requests dual billing. The MCTDSP is more likely to have current billing information for the customer and needs to be able to send updated customer information to the CR. | 814_PC, 814_PD
2004-652 | Bernie Dawson | Add a new suspension code for use in the MOU/EC market to provide the MCTDSP a way to notify the CR that the retail customer has requested a permanent disconnect and final bill. The new code in the 650_04 should prompt the CR to send an 814_24 for the ESI ID. This code will only be used for ESI IDs within a MOU/EC service territory. | 650_04
2004-653 | Bernie Dawson | Add new Action codes (BGN08) for use in the MOU/EC market to provide the MCTDSP a way to notify the CR that a customer disconnected by MCTDSP for non-payment has been reconnected. This code will only be used for ESI IDs within a MOU/EC service territory. | 650_04
2004-654 | Tom Baum | Update the REF~01gray box in the REF~1P segment to clarify that this segment is used on all responses. | 814_09
2004-656 | Charlie Bratton | The DNP Task Force requested that a change control be created to add reject reasons on the 650_02 for critical care customer and critical load customer. | 650_02
2004-657 | Tom Baum | Update the REF~7G Gray boxes where any code references a MIMO rule but does not specifically state the text “MIMO Rules” | 814_02, 814_11, 814_13, 814_17, 814_19, 814_25, 814_27, 814_29
2004-660 | Suzette Wilburn | Remove the BPO from the 810_03 and add applicable information back into the appropriate segment gray boxes of the guide. | 810_03
2004-661 | Suzette Wilburn | Remove the BPO from the 814_10 and add applicable information back into the appropriate segment gray boxes of the guide. | 814_10
2004-662 | Suzette Wilburn | Remove the BPO from the 814_24 and add applicable information back into the appropriate segment gray boxes of the guide. | 814_24
2004-664 | Bernie Dawson | Replace CR Customer Account Number (REF~11) on the 810_03 with MOU/EC membership number or ID to support Muni/Co-op business requirement to positively match all CR invoices to an existing MCTDSP membership/account. This makes the invoice transaction more consistent with other MOU/EC transactions, which now require Membership ID. | 810_03
2004-665 | Bernie Dawson | Change RMR01 from 11 (Account Number) to 12 (Billing Account). Replace CR Customer Account Number (RMR02) on the 820_03 with MOU/EC membership ID to support Muni/Co-op business requirement to positively match all payments to the CR to an existing MCTDSP membership/account. This makes the remittance transaction more consistent with other MOU/EC transactions, which now require utility-assigned Membership ID. | 820_03
2004-667 | Bernie Dawson | Add membership ID to TX SET 867_03 Monthly Usage transaction to support Muni/Co-op business requirement to positively match all market activity for an ESI ID to an existing MCTDSP membership/account. Including this value in the monthly usage transaction from MOU/EC will enable CR to identify possible out-of synch conditions before invoicing customers. | 867_03
2004-675 | Suzette Wilburn | Remove the BPO from the 820_03 and add applicable information back into the appropriate segment gray boxes of the guide. | 820_03
2004-677 | Tom Baum | In the DTM~649 segment of the 867_03, the IG says that this segment is required when the Bill Type is LDC, but later in the gray box it states ‘not provided on cancel transactions’. Add text to the gray box to indicate that this segment is not required on 867_03 Cancels. | 867_03
2004-679 | Tom Baum | Add the ability to forward the 814_18 to MCTDSPs and provide an 814_19 response back before initiating a CSA agreement for ESI IDs in MOU/EC Territories. | 814_18, 814_19
2005-680 | Bernie Dawson | Change request to modify code for Invalid Membership, previously approved as ‘IMN’ in TX SET Change Control 2004-651 on 11/17/04. | 814_04, 814_05, 814_11, 814_15, 814_25, 814_PD, 650_02 | Replaced CC 2004-651
2005-681 | Bernie Dawson | Change request to modify code for Invalid Membership, previously approved as ‘IMN’ in TX SET Change Control 2004-666 on 12/8/04. | 824 | Replaced CC 2004-666
2005-683 | Suzette Wilburn | Replace proposed text from CC2004-647 that provides guidelines on sending special characters in alphanumeric fields | All Transaction Sets | Replaced CC 2004-647
2005-684 | Eloise Flores | Add Membership ID to the 814_18/19 Establish CSA transactions | 814_18, 814_19
2005-685 | Eloise Flores/Suzette Wilburn | Remove requirement to send the Membership ID on the 814_08 Cancel Switch Request transaction | 814_08
2005-686 | Tom Baum | Add text to the 814_24 REF~1P segment gray box that states CR’s use of ‘B44’ code will bypass the CSA agreement at ERCOT when one exists. | 814_24

## Trx Description Card
`
| TEXAS SET VERSION 2.0A |  |  | 650* | Maintenance Service Order - Work Orders, Meter Config. Details, Outage Notification
814 - Request, Response, Maintenance for Enrollments, Drops, Switches, Maintenance & Request Consumption
| Trx | Definition | Flow | Trx | Definition | Flow
| 814_PC | Maintain Customer Information Request | CR=>TDSP | 650_01 | Basic Service Order | CR=>TDSP
| 814_PD | Maintain Customer Information Response | TDSP=>CR
| 814_01 | Enrollment Request | CR=>ERCOT | 650_02 | Service Order Complete Response | TDSP=>CR
| 814_02 | Enrollment Reject Response | ERCOT=>CR | 650_04 | Suspension of Delivery Svc Notification or Cancellation | TDSP=>CR
| 814_03 | Switch CR Notification Request | ERCOT=>TDSP
| 814_04 | Switch CR Notification Response | TDSP=>ERCOT | 650_05 | Suspension of Delivery Service Reject Response | CR=>TDSP
| 814_05 | Premise Info & Enrollment Response | ERCOT=>CR
| 814_06 | Drop Due to Switch Request | ERCOT=>CR | *The 650_03 functionality was distributed amongst the other 650 transactions.
| 814_07 | Drop Due to Switch Response | CR=>ERCOT
| 814_08 | Cancel Switch Request | CR=>ERCOT | 810 - Statement, Settlement, Wire Charge Invoices
|  |  | ERCOT=>CR | 810_02 | Wires Charge/Service Order Charge Invoice | TDSP=>CR
ERCOT=>TDSP
| 814_09 | Cancel Switch Response | ERCOT=>CR | 810_03 | Muni/Coop Invoice | CR=>MCTDSP
CR=>ERCOT
|  |  | TDSP=>ERCOT | 820 - Payment and Advice through Bank
| 814_10 | Drop to AREP Request | CR=>ERCOT | 820_02 | CR Remittance Advice | CR=>TDSP
| 814_11 | Drop to AREP Response | ERCOT=>CR
| 814_12 | Move-In/Move-Out Dte Chg Request | CR=>ERCOT | 820_03 | Muni/Coop Remittance Advice | MC TDSP=>CR
ERCOT=>CR
|  |  | ERCOT=>TDSP | 824 - Reject Response to 810 or 867 Data - O
| 814_13 | Move-In/Move-Out Dte Chg Response | ERCOT=>CR | 824 | Application Advice | CR=>TDSP
|  |  | CR=>ERCOT |  |  | CR=>ERCOT
|  |  | TDSP=>ERCOT |  |  | ERCOT=>TDSP
| 814_14 | AREP Enrollment Request | ERCOT=>AREP | 867-Interval, Non Interval, Reads & Consumption Data Historical and Monthly Activity
| 814_15 | AREP Enrollment Response | AREP=> ERCOT
| 814_16 | Move-In Request | CR=>ERCOT | 867_02 | Historical Usage | TDSP=>ERCOT
| 814_17 | Move-In Reject Response | ERCOT=>CR |  |  | ERCOT=>CR
| 814_18 | Establish/Delete CSA CR Request | CR=>ERCOT | 867_03 | Monthly Usage | TDSP=>ERCOT
|  |  | ERCOT=>TDSP |  |  | ERCOT=>CR
| 814_19 | Establish/Delete CSA CR Response | ERCOT=>CR | 867_04 | Initial Meter Read Notification | TDSP=>ERCOT
|  |  | TDSP=>ERCOT |  |  | ERCOT=>CR
| 814_20 | Create/Maintain/Retire ESI ID Request | TDSP=>ERCOT
ERCOT=>CR
| 814_21 | Create/Maintain/Retire ESI ID Response | ERCOT=>TDSP
CR=>ERCOT
| 814_22 | CSA CR Move-In Request | ERCOT=>CR
| 814_23 | CSA CR Move-In Response | CR=>ERCOT
| 814_24 | Move-Out Request | CR=>ERCOT
ERCOT=>TDSP
| 814_25 | Move-Out Response | ERCOT=>CR
TDSP=>ERCOT
| 814_26 | Ad-Hoc Historical Usage Request | CR=>ERCOT
ERCOT=>TDSP
| 814_27 | Ad-Hoc Historical Usage Response | ERCOT=>CR
TDSP=>ERCOT
| 814_28 | Completed Unexecutable or Permit Required | TDSP=>ERCOT
ERCOT=>CR
| 814_29 | Response Completed Unexecutable or Permit Required - O | ERCOT=>TDSP
CR=>ERCOT