## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak

## Slide 2
Phase:
Initiation – Completed in Feb ‘05
Planning – March 14, 2005
Execution – Starting August ’05
Implementation – Goal December ‘05
Closing – Starting December ‘05
Recent:
Meeting with Market Participants on Thursday, February 24th to discuss project timeline and requirement prioritization
Next steps:
Prepare to enter next phase (Planning)
Start developing detailed business requirements
Select enhancement method (upgrade current tool, Siebel or AIM)
Summary of Project Status
PR-50007 Enhancements to FasTrak

## Slide 3
** All target dates will become firm after design is complete and project plan finalized
Requirements (pens down) – May/June ’05
Design (published document) – June/July ’05
Internal Testing – August/November ’05
External Testing – August/November ‘05
Internal Training – November/December ’05
External Training – November/December ‘05
Production (Go live) – December ‘05
High level timeline
PR-50007 Enhancements to FasTrak

## Slide 4
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: sdegger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak