## Slide 1
Objectives:
Upgrade Siebel to a supported application
Upgrade to Oracle 9i database
Deliver all existing user functionality with no degradation in performance
Scope:
Upgrade Siebel software v6.3 to v7.7
Upgrade Oracle database 8i to 9i
Maintain all existing Siebel functionality from v6.3
Maintain all existing functionality to interfaces (L*, Reports/Extracts, ETS (internal))
Allow developers to more easily enhance system functionality going forward
Deploy thin-client for external Settlement Disputes & Service Requests
Dependencies:
None
Project Objectives / Scope / Dependencies
PR-40066_03 Siebel 7 Upgrade

## Slide 2
Phase:
Initiation – Completed in Sept ‘04
Planning – Completed in January ‘05
Execution – In Progress – Scheduled Implementation April 15-17 ‘05
Closing – Goal to complete early June ‘05
Recent:
Completed testing in several lower environments
Test Scripts and Final Design sign-off underway
Minor cosmetic modifications remaining
Next steps:
Started our migration to iTest on February 17 ‘05
Prepare internal training materials for week of March 14 ’05
Complete Migration Plan including Contingency “Fall-back” Plan
Summary of Project Status
PR-40066_03 Siebel 7 Upgrade

## Slide 3
Requirements (pens down) – Completed early January ‘05
Final Design (Internal document) – Completed mid February ’05
Build – Completed late February ‘05
Testing – Goal to complete mid April ‘05
Internal Training – Goal to complete mid March ’05
MP Training – Web Cast conducted for Settlement Disputes prior to Deployment
Production (Go live) – April 15-17 ‘05
High level timeline
PR-40066_03 Siebel 7 Upgrade

## Slide 4
Bus Lead: John Kassel ph: 512-248-6516
Email: jkassel@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 15 Program Area: RO
What prompted the project:
This project was a CASUP recommendation approved by ERCOT Executive committee and the ERCOT Board of Directors
Vendor support expired for existing version of Siebel and Oracle in 2004 – cost to maintain becomes significant if major problems arise
Siebel is the Registration system for all ERCOT’s Customers
Current version has limited Portal interaction capabilities
Additional Information
PR-40066_03 Siebel 7 Upgrade

## Slide 5
NOT CHANGING
  Transaction management of ALL 814 and 867 transactions
  Current workflow of service orders and service instances
  Contact administration and relationship management
  Reports and Extracts
CHANGING
  Service Requests functionality and screen design (Wholesale and Retail)
  Settlement Disputes functionality and screen design (Wholesale)
External Functionality
PR-40066_03 Siebel 7 Upgrade

## Slide 6
At this time, ERCOT anticipates the outage timeframe below for the April Maintenance Retail Release
The timeframe is subject to change and confirmation will be provided prior to the release
Friday, April 15, 2005 through Sunday, April 17, 2005.
During the outage:
All transactions sent to ERCOT will be held at the Paperfree server during the outage
867 transactions WILL be forwarded during the outage
NAESB EDM and ANSI responses WILL be sent during the outage (i.e. This includes 997 Functional Acknowledgements)
USA functionality will not be available
Retail components of the TML and API will NOT be available (i.e. This includes Find ESI, Find Transaction and Submit Transactions)
Settlement Disputes and Service Requests will NOT be available
ERCOT System Outage Overview
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 7
The shutdown times listed will be strictly adhered to unless prior notice is given to all MPs
All MPs should submit transactions well in advance of the shutdown time so that large transaction volumes are not experienced just prior to shutdown
  (i.e. if you run batch jobs, schedule them throughout the day)!!!
All MPs will have the opportunity to call-in to each conference call during the implementation if they wish to hear a progress update
All times listed are Central Prevailing Time
Shutdown Procedure
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 8
Friday, April 15th (mid-day)
ERCOT will…
  Keep up NAESB and Paperfree
  Shut down XML Mover (for 814 & 824 transactions) and 867 Upload
  Shut down TML component for Settlement Disputes – for QSEs
  Shut down TML component for Service Requests
This will isolate TCH processing…
    Inbound MP transactions will be held at Paperfree
        NAESB EDM Response
      ANSI Responses
Held transactions will be converted to XML and staged for TCH
After inbound shut down, all in-flight transactions will continue to be processed and corresponding outbound transactions will be delivered throughout the day until the queues have been cleared
Transaction Processing - Inbound
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
ERCOT will continue to send…

## Slide 9
Friday, April 15th (early evening)
ERCOT will…
    Stop sending 814 & 824 transactions
    Begin Siebel code migration and data conversion
Transaction Processing - Outbound
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 10
Beginning Saturday, April 16th through Sunday, April 17th
ERCOT will…
    Evaluate where we are in the conversion process
    Identify any remaining activities
    Take periodic “Go Live” Check Points
  No-Go…
    Continue to work through conversion
    Identify remaining effort and determine next check-point
    Back out Plan (Time schedule being finalized)
  Go Live…
    Test verification of Production systems
    Turn on all Inbound and Outbound processing
    Begin monitoring transaction flows
Upgrade Activities
PR-40066_03 Siebel 7 Upgrade
Implementation Plan

## Slide 11
Monday (4/11) & Wednesday (4/13) 2:00pm Retail Market Calls
  ERCOT discussion of upcoming shut-down schedule
Friday April 15th (mid-day)
  ERCOT transaction processing update
    “in queue”
    “in process”
    Overall system health
  CRs & TDSPs to provide status of transaction volumes
Friday April 15th (early evening)
  ERCOT transaction processing update
    “in queue”
    “in process”
    Overall system health
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
Conference Calls

## Slide 12
Saturday April 16th (late afternoon)
  Migration Progress
  Issues
  Go / No-Go Decision
Sunday April 17th (morning)
  Migration Progress
  Issues
  Go / No-Go Decision
Sunday April 17th (late afternoon if needed)
  Migration Progress
  Issues
  Go / No-Go Decision
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
Conference Calls

## Slide 13
  ERCOT has run “<value>” v7.7 Test Cases with all applications in iTest.
  ERCOT currently has only “<value>” open defects out of a total of “<value>” logged.
  To date, ERCOT has identified “<value>” Defects
  These defects are categorized as follows…
      xx - Documentation and Script errors or Data
      xx - Bugs (Coding errors requiring application level changes)
      xx - System or Environment related
      xx - Unknown (Root cause not reported or still in analysis)
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
Testing Results

## Slide 14
Below is the status to-date of the Siebel 7.7 Testing Efforts in anticipation of the 04/17/2005 roll-out.
  Test Description UAT Performance
  Transaction Processing XX % complete XX % complete
  eService / CRM XX % complete XX % complete
  GUI XX % complete XX % complete
  Data Archive Reporting XX % complete XX % complete
PR-40066_03 Siebel 7 Upgrade
Implementation Plan
Testing Results