## Slide 1: Market Coordination Team
Update to RMS

## Slide 2
MCT Kick-off Meeting Update…
  1st MCT Meeting was held on 3/2 (Austin)
    Twenty five people were in attendance for our kickoff meeting
    Requirements document was handed over from the TX SET Working Group
    V2.1 approved Scope
      55 Change Controls
      49 Requirements
Kick-off Meeting

## Slide 3
MCT Meeting Update…
  Reviewed TX SET handoff document
    Discussed each Requirement and Change Control
      Made appropriate updates to the wording for clarity
      Generated Issue Log for items needing further clarification
    Made a high-level determination of the proposed changes and content to each transaction / business process
  RMS Presentations
    Identify Content and Format for monthly updates
      Graph of all MPs status (Design, Code, Test)
  Discussed future meeting schedule
    This and future meetings will piggy-back the TX SET working group meetings
Team Activities

## Slide 4
Action Items
  Internal review of requirements (All)
    Identify any system issues that would prohibit implementation upon review of Change Controls
      Will any Market Reports be affected?
      Will Protocols be affected?
    Review of Issues Log for future meeting topics
  Return with questions/comments COB Friday 3/18
    Comments will be summarized and distributed for review during April meeting
Action Items

## Slide 5
Meeting Dates and Locations
MCT made the recommendation to host meetings in alternate locations to encourage participation
  April – AEP’s offices in Corpus Christi (4/6 & 4/7)
  May – Entergy in New Orleans
  June – Reliant in Houston
  July – Direct Energy / AEP in Tulsa
  August – TXU in Dallas
  September – ERCOT in Austin
  October – Center Point in Houston
  Meeting dates for the above schedule will be coordinated with TX SET and communicated as soon as they have been confirmed
Future Meetings

## Slide 6
Feb
Mar
Apr
May
Jun
Jul
2005
Aug
Sep
Oct
Nov
Jan
Flight Testing
Proposed Timeline
Dec
Connectivity Testing
Implementation
UAT
Delivered Code
Detailed
Requirements
Kick-off Meeting
In Austin
Future MCT Meetings