## Slide 1: TAC Update
Trip Doggett
Facilitator, Texas Nodal Team
February 3, 2005

## Slide 2: Agenda
ERCOT Protocol Development
Economist Issues
January 12 Voting

## Slide 3: ERCOT Protocol Development
Round 2 started November 1
Completed Round 2 final review of all sections that should remain unchanged by the economist’s comments.
Completed Round 1b intermediate review of sections impacted by economist’s comments on January 18.
Round 2 final review of sections impacted by economist’s comments scheduled to begin January 31 and finish in early March.

## Slide 4: Economist Issues History
On November 8, we decided to adopt:
  Addition of Co-Optimization of AS and energy in the Day-Ahead Energy Market (DAEM)
  Change in the Reliability Unit Commitment (RUC) allocation multiplier
  Creation of a demand curve for a small quantity of Responsive Reserve Service
We decided not to adopt:
  A must-offer in DAEM
  ERCOT “pre-commitment” of units in DAEM that it deems required for the following operating day
  Any zonal allocation of RUC costs
  Allocation of Congestion Revenue Rights to Loads
On November 15, we decided to:
  Request ROS’s review of Section 6.8.2 Uninstructed Resource Parameters
  Adopt Greer’s proposed DAEM changes
  Adopt fully funded CRRs, with offer floors, CRRs not sold on radial lines with resource on either end
  Adopt alternate settlement for CRR Options
  Adopt allocation of CRR Auction Revenues to Loads

## Slide 5: Economist Issues Update
Discussed on December 12:
  Addition of Real-Time Co-Optimization of AS and energy
  Any changes in CRR ownership reporting rules or limits
  Any changes to address Wolak’s cross-subsidy concerns
  Any additional mitigation to address physical withholding
  Any additional requirements of the IMM to restrict virtual trades
  Any mitigation of Ancillary Services
  Ability of QSEs to adjust Output Schedules up to time of SCED execution
We will have further discussion on:
  Addition of Real-Time Co-Optimization of AS and energy
  Ability of QSEs to adjust Output Schedules up to time of SCED execution
Any changes adopted will be incorporated in the Round 2 Protocol review process.

## Slide 6: January 12 Voting
Vote | Result
Motion to approve the revised language under Section 0.6.2 (5), which states that the RUC process will use 150% of verifiable costs (for Resources that did not submit a 3-part supply offer) instead of the 2-step process originally described in the whitepaper. Motion to adopt Alternative B under Section 0.6.2 (6), which treats the inability of a Resource to provide Ancillary Services as a forced outage. | Approved by a unanimous voice vote with one abstention by Direct Energy. The motion failed by a ballot vote of 24% in favor and 76% opposed.