## Slide 1: Retail Market Subcommittee Update to TAC
February 3, 2005

## Slide 2: Voting Items
RMS Leadership
  Tommy Weathersbee – Chair
  Lan Conn – Vice Chair
Update Test Schedule for Flight 0405, 0605 and 1005

## Slide 3: Voting Items
Flight V2.0A -0105
New CRs
Jan
Feb
Apr
Jun
May
Mar
Aug
July
Sept
Oct
Nov
Dec
2004
2005
3/18/05 Flight Ends
8 Wk. Test
0705 Flight Notice
5/04/05
8 Wk. Test
Flight V2.0-1005
New CRs & V2.1 Release
1005 Flight Notice
8/17/05
10 Wk. Test
8/9/05 Flight ends
8/30/05 Contingency ends
Flight V2.0A -0705
New CRs
Flight V2.0A -0405
New CRs
5/24/05 Flight ends
6/10/05 Contingency ends
8 Wk. Test
0405 Flight
Notice
2/2/05
12/16/05 Flight Ends
Black out Period for Existing CRs
Sign-up Deadline
3/9/05
Sign-up Deadline
6/8/05
Sign-up Deadline
9/21/05

## Slide 4: Voting Items
Update Flight Schedule for Flight 0405, 0605 and 1005
  “Time to Market” primary driver for change
  Reduced from 100 days to 62 or 76 days
  Average 31% shorter
  Contingency testing added to timeline
RMS approved current schedule in black
  Proposed changes are in red

## Slide 5: Voting Items

## Slide 6: Voting Items

## Slide 7
Data Extract Working Group Moving from RMS to COPS

## Slide 8
???
Questions
???