## TX SET Information
[5 empty] | DATE | 2004-01-20 | 2004-01-21 | 2004-02-17 | 2004-02-18 | 2004-03-23 | 2004-03-24 | 2004-04-19 | 2004-04-20 | 2004-05-18 | 2004-05-19 | 2004-06-22 | 2004-06-23 | 2004-07-20 | 2004-07-21 | 2004-08-17 | 2004-08-18 | 2004-09-21 | 2004-09-22 | 2004-10-19 | 2004-10-20 | 2004-11-16 | 2004-11-17 | 2004-12-07 | 2004-12-08
[5 empty] | CITY | 2004-01-20: Austin; 2004-02-17: Austin; 2004-03-23: Austin; 2004-04-19: Corpus Christi; 2004-05-18: Austin; 2004-06-22: Austin; 2004-07-20: Austin; 2004-08-17: Austin; 2004-09-21: Austin; 2004-10-19: Austin; 2004-11-16: Austin; 2004-12-07: Austin
OFFICER | NAME | COMPANY | EMAIL@ADDRESS | PHONE | MEETING VENUE | Comfort Suites | Comfort Suites | Comfort Suites | Comfort Suites | Comfort Suites | E M 206 A | AEP | AEP | AmeriSuites | AmeriSuites | E M 206 A | E M 206 A | AmeriSuites | E M 206 A | AmeriSuites | AmeriSuites | AmeriSuites | AmeriSuites | AmeriSuites | E M 206 A | AmeriSuites | E M 206 A | E M 206 A | E M 206 A
2004 VC | Bear, Jason | TCE | jason.bear@mytce.com | 214-509-3952 | bar: 2004-01-20 to 2004-03-24
| Bevill, Rob | Green Mountain | rob.bevill@greenmountain.com | 512-691-6134 | bar: 2004-01-20 to 2004-03-24
| Bratton, Charlie | TXU Energy | cbratto1@txu.com | 214-875-3703 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24
| Dawson, Bernie | Envision Utility Software | bernardd@envworld.com | 512-266-7787 | bar: 2004-01-20; 2004-02-17 to 2004-03-24
| Flores, Eloise | Nueces Electric Coop | eflores@nueceselectric.org | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-03-24
| Flowers, BJ | TXU Energy | bj.flowers@txu.com | 214-812-4330 | bar: 2004-01-20
| Hensley, Bryan | TCE | bryan.hensley@mytce.com | 214-509-2195 | bar: 2004-01-20 to 2004-03-24
| Hermes, Connie | STEC | connie@stec.org | 361-485-6173 | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-03-24
| Jackson, Tom | Austin Energy | Tom.Jackson@austinenergy.com | 512-322-6324 | bar: 2004-03-23 to 2004-03-24
| Johnson, Jennifer | ERCOT | jjohnson@ercot.com | 512-248-6733 | bar: 2004-01-20 to 2004-03-23
| McKain, Shelley | ADS Mutual Energy | smckain@alldata.net | 918-493-9515 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24
| Moore, Chuck | Direct Energy | chuck.moore@ngwi.com | bar: 2004-01-20; 2004-03-23
| Morales, Rita | Direct Energy | ritamorales@ngwi.com | 972-480-8224 | bar: 2004-01-20; 2004-03-23 to 2004-03-24
| Ohrt, Wendy | STEC | wendyjo@stec.org | 361-485-6172 | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-03-24
2004 Chair | Patrick, Kyle | Reliant Resources | kpatrick@reliant.com | 713-497-3396 | bar: 2004-01-20 to 2004-03-24
| Reed, Cary | AEP | careed@aep.com | 918-260-0093 | bar: 2004-01-20 to 2004-02-18
| Rehfeldt, Diana | TNMP/First Choice Power | drehfeldt@tnpe.com | 817-377-5580 | bar: 2004-01-20 to 2004-01-21
| Reily, Bill | Oncor | breily1@txu.com | 214-875-2520 | bar: 2004-01-20 to 2004-03-23
| Robertson, Johnny | TXU | jrobert1@txu.com | 214-875-1565 | bar: 2004-01-20; 2004-03-23 to 2004-03-24
| Rodriguez, Robert | Constellation New Energy | Robert.Rodriguez@constellation.com | 281-793-6339 | bar: 2004-01-20; 2004-03-23
2004 VC | Scott, Kathy | CenterPoint Energy | Kathy.d.scott@centerpointenergy.com | 713-945-6630 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24
| Steen, Lora | Entergy | lsteen@entergy.com | 936-525-2034 | bar: 2004-01-20 to 2004-01-21
| Teel, Jennifer | EC POWER | jennifer.teel@ec-power.com | 713-403-8731 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24
| Weaver, Steve | Entergy
| Wilburn, Suzette M. | ERCOT | swilburn@ercot.com | 512-248-3991 | bar: 2004-01-20 to 2004-03-24
| Davis, Mike |  | mdavis@ercot.com | 512-248-6763 | bar: 2004-02-17; 2004-03-23
| Wilson, Frank | Nueces Electric Coop | fwilson@nueceselectric.org | 361-387-2581 | bar: 2004-02-17

## 2004 Action Items
Meeting | Sponsor | CC | Issue | Action Item | Resolution | Status
January | RRI |  | Would like to investigate possibility of adding a flag to indicate whether the meter is temporary or permanent | CRs will meet to re-frame the question and provide the TDSPs with exactly what they'd like to see |  | Closed | 2004-02-17
January | RRI |  | Would like to investigate the possibility of adding a code on the 814_16 and 650 series that would provide gate access codes | Group agreed that more time was necessary to determine if there was a need for this type of information from all CRs |  | Closed | 2004-02-17
January | ERCOT |  | Review of the draft 867_01 IG for opting in entities | TDSPs to review guide with SMEs at their companies to verify guide contains all necessary segments and data elements | TX SET believes that the cost for re implementing the 867_01 is much larger than the cost for using a flat file on a on going basis. | Closed
January | ONCOR |  | Outdated scheduled transactions in ERCOTs system that cannot be completed | ERCOT to investigate if a common theme exists for the manual processes used to 'fix' these scheduled transactions to get a better idea of where TX SET needs to focus their attention |  | Open
January | ERCOT | Y | Clarification needed on how maintenance to unmetered service devices are communicated in the 814_20 | 814_20 guide needs to be updated if the 814_20 is not used when maintaining unmetered service devices. TX SET to investigate the possibility of adding this functionality to the 814_20 | TDSPs waiting for response on whether they send 814_20s. | Open
January | CNP | Y |  | 867_03 How to Use Section meeting needs to be arranged to convert the How to Use to a BPO and make the appropriate updates in the new BPO document. | This will be an agenda item at the March meeting. | Open
January | TX SET |  |  | TX SET Leads need to develop a process that would remind members of outstanding and/or open action items prior to monthly meetings (1 or 2-weeks before if possible) | Leadership will remind team members of action items when meeting notice and agenda are sent. | Open
| ERCOT |  | In the case of a MOV to CSA, when an 814_08 is submitted by the Cur CR, is the TDSP expecting the Cur CR or CSA CR Duns in the N1~SJ? I would believe it would be the CSA CRs Duns, because the TDSP would have received an 814_03 with the CSA CRs information, not and 814_24 with the Cur CR information. |  | ERCOT will be putting the CSA CR in the 814_08 | Closed
February | TX SET |  | Review BPOs for 2.0 |  |  | Open
February | ERCOT | Y | · In the event that there are multiple meters exchanged on a premise, would the profile code be listed in both NM1 loops? We have seen some instances where the profile code update (REF~LO) is included in the second NM1 loop and wanted to verify that profile codes should be accepted regardless of which NM1 loop they are communicated in o If the profile code is an attribute of the ESI-ID and not the meter, why is it in the NM1 loop? Shouldn’t it be in the LIN loop? · TX SET agrees that the profile code is at a premise level and that the profile code needs to be updated regardless of which NM1 loop it is sent in. Group also agreed that this type of update needs to be in the LIN loop, not the NM1 loop, as the change is at a premise, not meter, level | S. Wilburn to write a change control to move the REF~LO segment to the LIN loop | Change Control written. | Closed
February |  |  | · The N303 in the N3 segment of the 814_20 is alphanumeric. (AN1/55). Would like to find out from the group if they would like to see ERCOT rejecting transactions that send special characters in this field. o Encountered issues with double quotes in this field. Only about 40 ESI-Id · If ERCOT decides to cross validate this field and reject transactions that contain special characters, they need to look at other fields that they currently do not cross validate on. For instance, the PER segment in the 814_03 is not cross validated to ensure the phone number is sent without dashes. | ERCOT will communicate to the team what decision they decide to go with regarding the cross validation | ERCOT implemented a fix to reject any 814_20s that contain special characters in the NM109. This fix was implemented in the 0403 release and market notification was sent out by client services on March 23rd. | Closed
February |  |  | · Following up on the issue regarding 814_20 retires being received on de-energized ESI-Ids with a scheduled MVI. We have a proposed short term solution o If the SMRD of the MVI is greater than the date on the retire, we cancel the MVI o If the SMRD of the MVI is less than the retire, we reject the retire and allow the MVI to effectuate | ERCOT will implement a fix in a near release to reject any 814_20 retires received on a de-energized premise with a scheduled service order. TDSP will open a fastrak issue to get open service order resolved. Release date is still to be determined. ERCOT Client Services will communicate when this change will be implemented |  | Open
February | Nueces |  |  | E. Flores to gather all issues addressed to date regarding the Muni/Coop market to send out to the market |  | Open
February | TX SET Officers |  |  | TX SET officers to make phone calls to the muni/coops about the meeting |  | Open
February | ERCOT |  |  | ERCOT Client Services to pull together email to be sent out inviting all Muni/Coops to attend the day meeting on April 20th |  | Open
February | TCE/STEC | Y | We need to talk about the 650_04 disconnect/reconnect process on the muni/coop side. There was some discussion at Texas Test Plan script sub team on this regarding the current test script calling for a 650_04 cancel of the disconnect request to indicate a reconnect. | TCE to work with STEC to write change control for adding a new code to the 650_04 to communicate this information | Change control was written, but withdrawn. TX SET members are working on a revision | Open
February | ERCOT | Y | Should a REF~IX always exist when a REF~4P is present in the 814-04? · For example, if you have a REF~MT~COMBO and two REF~4Ps should you also have two REF~IXs? · If not, what circumstances exist when you wouldn't, and what type of modifications could be made to the gray box to clarify this? | o (Action Item) S.Wilburn to write a change control to update the examples in the 814_04 | Change control written for May Meeting | Closed
February | TX SET |  | "Future Implementation CCs aka Unassigned CCs" Review. (SEE WORKBOOK PAGE UNASSIGNED CHANGE CONTROLS) | TX SET members to review all future implementation change controls before the March TX SET meeting |  | Open
February |  |  | Revised Working Group Procedures | TX SET members should review the Working Group Procedures Redline |  | Open
February
March | ERCOT |  | Standardized process needs to be developed for MVO to CSA scenarios when something happens to the meter that results in the TDSP sending "NONE" on the 814_03 back to ERCOT. This is sent on the 814_22 to the CSA CR, who in turn rejects it. | Needs to be brought up again for TX SET to develop a process for scenarios like this. |  | Open

## Project Plan
Project Plan for Next Release
Activity | Time Frame | Start Date | End Date | Membership
Identify all changes required for Future Version. Submit all change controls to be applied to version Future Version. Discussion and approval/denial of all change control design documents. | As determined
Update current version 1.5 to a clean baseline with all change controls applied | 3 weeks
Review all change controls and prepare any SCRs and PRRs as needed | 1 week
Build SEF and Word docs. With all Future Version change controls applied. | 3 weeks
Publish Future Version first draft redline | 1 day
Tx SET committee will review and compare Visio's, change controls and implementation guides. All market participants will start design and technical analysis. | 6 weeks
Resolve issues | 1 week
Apply resolved issues and any change controls approved since the redline publication | 1 week
Publish final Future Version redline | 1 day
TxSET committee will review and compare Visio's, change controls and implementation guides. Any identified gaps or errors will be sent to TxSET | 2 weeks
Resolve issues | 1 week
Apply resolved issues | 1 week
Update Transaction Scenario Inventory. Clean up any identified errors. | 2 weeks
Publish official version Future Version | 1 day
Minimum time needed for TxSET to publish a new version of implementation guides after the design requirements have been given to TxSET. | 21 weeks'**
Delivered to TTPT

## 2.0 Baseline Matrix
2.0 Baseline Project
Action | Due Date
SEF and Redline Complete | 2003-08-01
Verified for Baseline Due | 2003-08-27
Create or Verify BPO's for Release Version 2.0 | TBD at Aug SET meeting
Transaction | TX SET Volunteer | Analysis Results | Changes to be applied | CC Applied? Y/N | BPO
650_01 | Charlie Bratton |  |  |  | Yes
650_02 | Charlie Bratton |  |  |  | Yes
650_04 | Charlie Bratton |  |  |  | Yes
650_05 | Charlie Bratton |  |  |  | No
814_PC | Johnny Robertson |  |  |  | No
814_PD | Johnny Robertson |  |  |  | No
814_01 | Johnny Robertson |  |  |  | No
814_02 | Johnny Robertson |  |  |  | No
814_03 | Bill Reily |  |  |  | No
814_04 | Bill Reily |  |  |  | No
814_05 | Bill Reily |  |  |  | No
814_06 | Shelly |  |  |  | No
814_07 | Shelly |  |  |  | No
814_08 | Shelly |  |  |  | No
814_09 | Rehfeldt |  |  |  | no
814_10 | Kyle Patrick/Suzette |  |  |  | Yes (Update for 2.0)
814_11 | Rehfeldt |  |  |  | No
814_12 | Kathy Scott |  |  |  | No
814_13 | Kathy Scott |  |  |  | no
814_14 | Kathy Scott |  |  |  | No
814_15 | Cary Reed |  |  |  | No
814_16 | Jennifer Teel |  |  |  | No
814_17 | Jennifer Teel |  |  |  | No
814_18 | Jason Bear, Rehfeldt |  |  |  | Yes (Update for 2.0)
814_19 | Jason Bear |  |  |  | No
814_20 | Kathy Scott |  |  |  | Yes (Update for 2.0)
814_21 | David Gonzales/Suzette Wilburn |  |  |  | no
814_22 | David Gonzales/Suzette Wilburn |  |  |  | No
814_23 | David Gonzales/Suzette Wilburn |  |  |  | no
814_24 | Kyle Patrick/Suzette |  |  |  | Yes (Update for 2.0)
814_25 | Kyle Patrick |  |  |  | No
814_26 | Kyle Patrick |  |  |  | No
814_27 | Cary Reed, Bill Reily |  |  |  | No
814_28 | Bill Reily/JR |  |  |  | Yes (Update for 2.0)
814_29 | Cary Reed, Bill Reily |  |  |  | No
810_02 | Jennifer Teel |  |  |  | Yes
810_03 | Jennifer Teel |  |  |  | Yes
820_02 | Bernie Dawson |  |  |  | Yes
820_03 | Bernie Dawson |  |  |  | Yes
867_02 | Postpone until after 867/810 WS |  |  |  | Need Convert Trans notes reviewed
867_03 | Postpone until after 867/810 WS |  |  |  | Need Convert Trans notes reviewed
867_04 | Postpone until after 867/810 WS |  |  |  | Check for trans notes
824 | Bernie Dawson |  |  |  | Yes
T-Series | Kathy Scott |  |  |  | No
2.0 Change Controls to be Applied **Please see ERCOT website for most up to date list of CCs to be applied**
Current List of "APPROVED" Change Controls by #
2002-400
2002-401
2002-446
2002-448
2003-518
2003-519
2003-520
2003-521
2003-523
2003-524
2003-525
2003-535
2003-540
2003-541
2003-542
2003-543
2003-544
2003-545
2003-546
2003-547
2003-548
2003-549
2003-550
2003-554
Note on E9: TX SET Action Item: Have all "Approved" TX SET Change Controls been applied correctly to the REDLINED document?
Note on F9: TX SET Action Item: Does the transaction have a BPO? If "Yes", volunteer needs to verify that the BPO is updated for 2.0. If "No", the volunteer needs to verify that there are no transaction notes for that transaction. If "Need for 2.0", the volunteer is to draft a BPO for the requested transaction.

## Unassigned Change Controls
Change Controls
| Approved | Transactions | Version | Scope | Size/Swag | Description | Notes
pending |  | 810 |  | System | 2 | Potential 810 - 867 billing determinants changes
pending |  | 810_02 |  | System | 3 | allow TDSP to send single corrected invoice for IDR meters
3-503 | Y | 810_02 | Future | System | 3 | allow TDSP to send single corrected invoice for non-IDR meters | Valid per TX SET review 3/24/04
2-316 | Y | 814_22 | Future | System | 2 | Add the N1~loop to the 814_22 | Nullified
2-412 | Y | 814_09 | 1.6 | Gray Box/Examples | 1 | Cleanup of Example box | Already Applied to 2.0
2-413 | Y | 814_11 | 1.6 | Gray Box/Examples | 1 | Add example | Already Applied to 2.0
2-414 | Y | 814_13 | Future | Gray Box/Examples | 1 | Add example | Already Applied to 2.0
2-415 | Y | 814_25 | Future | Gray Box/Examples | 1 | Add example | Already Applied to 2.0
2-447 | Y | 814_10 | Future | System | 1 | Remove segments from N1~8R | Nullified
2-449 | Y | 814_14 | Future | System | 1 | Remove N2 segment from the N1~8R Loop and update gray boxes | Nullified
2-466 | Y | 650_04 | Future | System | 2 | Add code to 650_04 provide means to alert CR that service has been permanently suspended for ESI ID and numerous gray box changes | Valid per TX SET review 3/24/04
2-468 | Y | 810_03 | Future | System | 1 | Multiple 810_03 changes - code gray box | Valid per TX SET review 3/24/04
3-471 | Y | 650_04 | Future | System | 1 | remove must use from the YNQ04 of the NQ~5U segment | Valid per TX SET review 3/24/04
3-490 | Y | 814_14, 814_22 | Future | Gray Box/Examples | 1 | remove QTR from valid values of Meter Type from the gray box | Valid per TX SET review 3/24/04
3_493 | Y | 814_27 | Future | System | 1 | Make the N1~8S OPTIONAL on the 814_27 to be consistent with the 814_26 N1~8S loop | Valid per TX SET review 3/24/04
3_496 | Y | 650_02 | Future | System | 2 | Provide additional detail on when 650_02 should be generated and how the process should work for disconnect and reconnect for non-pay | Re-evaluate-Jennifer Teel, Bill Reily, Kathy Scott. CC was referred to Shannon Bowling and Blake Gross of Disco Reco TF.
3_497 | Y | 814_PD | Next Release | System | 1 | Remove "Zip" from the REF02 of the REF~7G segment (Rejection Reason) | Re-evaluate for validity (497, 498, 574, 596)
3_498 | Y | 814_PC | Next Release | System | 1 | Clean up of the 814_PC | Re-evaluate for validity (497, 498, 574, 596)
3_517 | Y | 814_28 | Future | System | 1 | Adding to reasons for "Complete Unexecutable" | Valid per TX SET review 3/24/04
3_527 | Y | 650_02 | Future | System | 1 | Adding to reasons for "Complete Unexecutable" | Valid per TX SET review 3/24/04
3_530 | Y | 650_01 | Future | Gray Box/Examples | 1 | Cleanup of Gray box and Example | Valid per TX SET review 3/24/04
3_532 | Y | 814_04 and 05 | Future | System | 2 | 814_04 and 05 needs a Meter Ownership Type code to eliminate gap when customer chooses competitive meter to notify new REP when switching | Valid per TX SET review 3/24/04
3_538 | Y | 867_03 | Future | System | 2 | Changes to examples in the Implementation Guide | Valid per TX SET review 3/24/04
3_539 | Y | 814_29 | Future | Gray Box/Examples | 1 | Add the BGN07 code to the gray box example in BGN segment | Valid per TX SET review 3/24/04
3_569 | Y | Entire 814 series 01-29, PC and PD | Future | Gray Box/Examples | 1 | Provide gray box clarification to the LIN segment to indicate that the Texas Market supports only 1 LIN loop per SDI Transaction | Valid per TX SET review 3/24/04
3_571 | Y | 814_09 and 814_13 | Future | Gray Box/Examples | 1 | Move segment gray box verbiage for A78 being used only by ERCOT and TDSP to gray box on actual code | Valid per TX SET review 3/24/04
3_572 | Y | 814_13 and 814_02 | Future | Gray Box/Examples | 1 | Add short title "Earliest Available Switch Date" to the EAS Reject code (REF*7G) | Re-evaluate
3_573 | Y | 814_08 and 814_09 | Future | Gray Box/Examples | 1 | Remove references to the word "reinstate" in the 814_08 and 814_09 transactions | Valid per TX SET review 3/24/04
3_574 | Y | 814 PC | Future | Gray Box/Examples | 1 | Remove existing transaction notes form the 814 PC guide | Re-evaluate for validity (497, 498, 574, 596)
3_576 | Y | 814_20 | Future | System | 1 | Meter Exchange/Profile Information | Re-evaluate
3_577 | Y | 814_17 | Future | Gray Box/Examples | 1 | Example 1 and 3 of the 814_17 guide need to have the REF*7G segment revised to match the new reject code detail put in place by the V2.0 change controls | Valid per TX SET review 3/24/04
3_578 | Y | 814_20 | Future | System | 2 | Added a new change code to indicate the annual Load Profile changes | Valid per TX SET review 3/24/04
3_580 | Y | 820_03 | Future | System | 2 | Change for adding payment adjustment | Withdrawn
3_581 | Y | 867_04 | Future | Gray Box/Examples | 1 | Example change | Valid per TX SET review 3/24/04
3_582 | Y | 814_08 | Future | System | 1 | add B30 - MIMO change | Valid per TX SET review 3/24/04
3_583 | Y | 814_02, 11, 17, 19, 21, 25, 27 | Future | Gray Box/Examples | 1 | if same BGN02 comes from two different CRs one will be rejected | Valid per TX SET review 3/24/04
3_590 | Y | 814_21 | Future | System | 1 | Add code for ERCOT generated reject | Valid per TX SET review 3/24/04
3_594 | Y | 814_08 | Future | Gray Box/Examples | 1 | MIMO clean up | Valid per TX SET review 3/24/04
4-595 | Y | 814_12 | Future | Gray Box/Examples | 1 | MIMO clean up | Valid per TX SET review 3/24/04
4-596 | Y | 814_PC | Future |  | 1 | Clarify timming to use transaction | Re-evaluate for validity (497, 498, 574, 596)
4-597 | Y | 814_13 | Future | Gray Box/Examples | 1 | MIMO clean up | Valid per TX SET review 3/24/04
4-598 | Y | 814_08,09 | Future | Gray Box/Examples | 1 | provide examples | Valid per TX SET review 3/24/04
4-601 | Y | 814_13 | Future | System | 1 | Add new reject code "ICD" MIMO | Valid per TX SET review 3/24/04
4-602 | Y | 814_08 | Future | Gray Box/Examples | 1 | MIMO clean up | Valid per TX SET review 3/24/04