## TX SET Information
TX SET |  |  |  |  | DATE | 2004-01-20 | 2004-01-21 | 2004-02-17 | 2004-02-18 | 2004-03-23 | 2004-03-24 | 2004-04-19 | 2004-04-20 | 2004-05-18 | 2004-05-19 | 2004-06-22 | 2004-06-23 | 2004-07-20 | 2004-07-21 | 2004-08-17 | 2004-08-18 | 2004-09-21 | 2004-09-22 | 2004-10-19 | 2004-10-20 | 2004-11-16 | 2004-11-17 | 2004-12-07 | 2004-12-08
[5 empty] | CITY | 2004-01-20: Austin; 2004-02-17: Austin; 2004-03-23: Austin; 2004-04-19: Corpus Christi; 2004-05-18: Dallas; 2004-06-22: Austin; 2004-07-20: Austin; 2004-08-17: Austin; 2004-09-21: Houston; 2004-10-19: Tulsa; 2004-11-16: Austin; 2004-12-07: Austin
OFFICER | NAME | COMPANY | EMAIL@ADDRESS | PHONE | MEETING VENUE | Comfort Suites | Comfort Suites | Comfort Suites | Comfort Suites | Comfort Suites | E M 206 A | AEP | AEP | TXU | TXU | E M 206 A | E M 206 A | E M 168 | E M 168 | Comfort Suites | Comfort Suites | CNP Tower | CNP Tower | AEP | AEP | AmeriSuites | E M 206 A | E M 206 A | E M 206 A
| Baum, Thomas | ERCOT | tbaum@ercot.com | 512-248-6550 | bar: 2004-06-22 to 2004-10-20
| Bear, Jason | Direct Energy | bar: 2004-01-20 to 2004-04-20; 2004-08-17 to 2004-08-18
| Bell, William | CenterPoint Energy | william.bell@centerpointenergy.com | 281-610-0309 | bar: 2004-04-19
| Bevill, Rob | Green Mountain | rob.bevill@greenmountain.com | 512-691-6134 | bar: 2004-01-20 to 2004-03-24; 2004-05-18 to 2004-06-23; 2004-09-21 to 2004-10-20
| Blumenthal, Ellen | GDS Associates | ellen.blumenthal@gdsassociates.com | 361-949-1578 | bar: 2004-04-19
| Bratton, Charlie | TXU Energy | cbratto1@txu.com | 214-875-3703 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-05-19; 2004-07-20 to 2004-08-18; 2004-10-19 to 2004-10-20
| Burke, Allan | TNMP | aburke@tnpe.com | 817-377-5532 | bar: 2004-09-21 to 2004-09-22
| Callender, Wayne | City of Public Service SA | wdcallender@cps-satx.com | 210-353-2779 | bar: 2004-04-19; 2004-08-17 to 2004-08-18
| Campirano, Eduardo | BPUB | ecampirano@brownsville-pu.com | 956-983-6279 | bar: 2004-04-19
| Collard, Zach | CenterPoint Energy | zach.collard@centerpointenergy.com | 281-433-7050 | bar: 2004-04-19; 2004-07-21
| Conner, Mike | BTU | mconner@btutilites.com | 979-821-5830 | bar: 2004-04-19
| Dauterive, Eddie | Envision Utility Software | eddied@envworld.com | 512-266-7787 | bar: 2004-04-19
| Davis, Mike | ERCOT | mdavis@ercot.com | 512-248-6763 | bar: 2004-02-17; 2004-03-23; 2004-04-19; 2004-09-21
| Dawson, Bernie | Envision Utility Software | bernardd@envworld.com | 512-266-7787 | bar: 2004-01-20; 2004-02-17 to 2004-10-20
| Duke, Warren | Peace Software | bar: 2004-06-22; 2004-10-19 to 2004-10-20
| Farley, Karen | ERCOT | kfarley@ercot.com | 512-248-3141 | bar: 2004-04-19; 2004-06-22 to 2004-06-23
| Fisher, Sarah | NEC | sfisher@nueceselectric.org | 361-387-2581 | bar: 2004-04-19
| Flores, Eloise | Nueces Electric Coop | eflores@nueceselectric.org | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-05-18; 2004-06-22; 2004-09-21
| Flowers, BJ | TXU Energy | bj.flowers@txu.com | 214-812-4330 | bar: 2004-01-20; 2004-06-22; 2004-07-20; 2004-08-17 to 2004-09-22
| Fredericks, Jennifer | ERCOT | jfredericks@ercot.com | 512-248-6733 | bar: 2004-01-20 to 2004-03-23; 2004-06-22; 2004-08-17 to 2004-08-18
| Garcia, Jennifer | USA Interlink | bar: 2004-04-19; 2004-08-17 to 2004-09-22
| Godoy, Ernie | SPEC | egodoy@sanpatricioelectric.org | 361-364-2220 | bar: 2004-04-19; 2004-05-18
| Harper, Brett | First Choice | bharper@firstchoicepower.com | 817-437-1479 | bar: 2004-06-22 to 2004-10-20
| Hensley, Bryan | TCE | bryan.hensley@mytce.com | 214-509-2195 | bar: 2004-01-20 to 2004-04-20
| Hermes, Connie | STEC | connie@stec.org | 361-485-6173 | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-04-20; 2004-09-21
| Hernandez, Ron | ERCOT | rhernandez@ercot.com | 512-248-6523 | bar: 2004-04-19
| Jackson, Tom | Austin Energy | Tom.Jackson@austinenergy.com | 512-322-6324 | bar: 2004-03-23 to 2004-03-24
| Kalips, Leo | NISC | leo.kalips@nisc.cc | bar: 2004-04-19
| Kernick, Kristina | Envision Utility Software | kristinaak@envworld.com | 512-266-7787 | bar: 2004-04-19
| Leith, Brent | First Choice | bleith@firstchoicepower.com | 701-306-6810 | bar: 2004-04-19; 2004-05-18 to 2004-07-21
| Lowder, Dave | SPEC | dlowder@sanpatricioelectric.org | 361-364-2220 | bar: 2004-04-19
| McKain, Shelley | ADS Mutual Energy | smckain@alldata.net | 918-493-9515 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24; 2004-07-20 to 2004-07-21
| Moast, Pat | ERCOT | pmoast@ercot.com | 512-261-9925 | bar: 2004-04-19
| Moore, Chuck | Direct Energy | chuck.moore@ngwi.com | bar: 2004-01-20; 2004-03-23; 2004-04-19 to 2004-05-19; 2004-07-20 to 2004-09-22
| Morales, Rita | Direct Energy | ritamorales@ngwi.com | 972-480-8224 | bar: 2004-01-20; 2004-03-23 to 2004-03-24; 2004-04-20 to 2004-08-18; 2004-10-19 to 2004-10-20
| Ohrt, Wendy | STEC | wendyjo@stec.org | 361-485-6172 | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-04-20; 2004-09-21
| Patrick, Kyle | Reliant Energy | kpatrick@reliant.com | 713-497-3396 | bar: 2004-01-20 to 2004-10-20
| Polliard, Sharon | AEP | bar: 2004-10-19
| Reed, Cary | AEP | careed@aep.com | 918-260-0093 | bar: 2004-01-20 to 2004-02-18; 2004-04-19 to 2004-10-20
| Rehfeldt, Diana | TNMP/First Choice Power | drehfeldt@tnpe.com | 817-377-5580 | bar: 2004-01-20 to 2004-01-21; 2004-07-20 to 2004-07-21
| Reily, Bill | TXU Electric Delivery | breily1@txu.com | 214-875-2520 | bar: 2004-01-20 to 2004-03-23; 2004-04-19 to 2004-04-20; 2004-05-19 to 2004-09-22
| Riordon, Ken | LCRA | ken.riordon@lcra.org | 512-473-3215 | bar: 2004-04-19; 2004-05-18
| Robertson, Johnny | TXU | jrobert1@txu.com | 214-875-1565 | bar: 2004-01-20; 2004-03-23 to 2004-10-20
| Robinson, Laura | Starlight Electric | laura@starlightelectric.com | 817-548-0808 | bar: 2004-09-21 to 2004-09-22
| Rodriguez, Robert | Constellation New Energy | Robert.Rodriguez@constellation.com | 281-793-6339 | bar: 2004-01-20; 2004-03-23; 2004-05-18 to 2004-06-22; 2004-07-20; 2004-08-17; 2004-09-21; 2004-10-19 to 2004-10-20
| Saenez, Fernando | BPUB | fsaenez@brownsville-pu.com | 956-983-6266 | bar: 2004-04-19
| Scott, Kathy | CenterPoint Energy | Kathy.d.scott@centerpointenergy.com | 713-945-6630 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24; 2004-05-18 to 2004-07-21; 2004-10-19 to 2004-10-20
| Smith, Lori | TNMP | lsmith@tnpe.com | 817-337-5532 | bar: 2004-09-21 to 2004-10-20
| Steen, Lora | Entergy | lsteen@entergy.com | 936-525-2034 | bar: 2004-01-20 to 2004-01-21; 2004-05-19
| Teel, Jennifer | EC POWER | jennifer.teel@ec-power.com | 713-403-8731 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-04-20
| Thomas, Jeff | Direct Energy | jeff.thomas@mytce.com | 214-509-2122 | bar: 2004-04-19; 2004-05-18 to 2004-06-22; 2004-07-20 to 2004-07-21
| Weaver, Steve | Entergy Solutions | sweave1@entergy.com | 832-681-3146
| Wilburn, Suzette M. | ERCOT | swilburn@ercot.com | 512-248-3991 | bar: 2004-01-20 to 2004-04-20; 2004-05-19; 2004-07-20 to 2004-07-21; 2004-10-19 to 2004-10-20
| Wilson, Frank | Nueces Electric Coop | fwilson@nueceselectric.org | 361-387-2581 | bar: 2004-02-17; 2004-04-19
| Wingerd, Glen | ERCOT | gwingerd@ercot.com | bar: 2004-04-19

## Project Plan
Project Plan for Next Release
Activity | Time Frame | Start Date | End Date | Membership
Identify all changes required for Future Version. Submit all change controls to be applied to version Future Version. Discussion and approval/denial of all change control design documents. | As determined
Update current version 1.5 to a clean baseline with all change controls applied | 3 weeks
Review all change controls and prepare any SCRs and PRRs as needed | 1 week
Build SEF and Word docs. With all Future Version change controls applied. | 3 weeks
Publish Future Version first draft redline | 1 day
Tx SET committee will review and compare Visio's, change controls and implementation guides. All market participants will start design and technical analysis. | 6 weeks
Resolve issues | 1 week
Apply resolved issues and any change controls approved since the redline publication | 1 week
Publish final Future Version redline | 1 day
TxSET committee will review and compare Visio's, change controls and implementation guides. Any identified gaps or errors will be sent to TxSET | 2 weeks
Resolve issues | 1 week
Apply resolved issues | 1 week
Update Transaction Scenario Inventory. Clean up any identified errors. | 2 weeks
Publish official version Future Version | 1 day
Minimum time needed for TxSET to publish a new version of implementation guides after the design requirements have been given to TxSET. | 21 weeks'**
Delivered to TTPT

## 2004 Open Action Items
Meeting | Segment | Sponsor | CC | Issue | Action Item | Resolution | Status | Date
2004-04-01 |  |  |  | DNP Taskforce Recommendations | DNP Taskforce to hand off deliverables | (8/17/04) Taskforce still in working and all deliverables jest to be delivered (10/12/04) Change Control written and approved for priority disconnect procedures. There maybe additional change contro | Open
2004-04-01 |  | RRI & TXU |  | Change Control for Billing Determinants | Write Change Control 09/22/04 Update - Draft Change Control writte | (08/17/04) TX SET Sub-team scheduled to meet in Houston on September 24, 2004 to finalize Change Control Request (10/12/04) Texas SET approved change 2004_644 was approved with minor changes. | Open
2004-04-01 | MOU/EC | (Eloise Flores,Nueces Electric Coop) |  | Add a customer(member) tracking number from move-in to Move-out. Customer name tied to ESID (believe this is already a noted issue); membership issues | High Priority | (06/23/04) Think about what needs to be done and what is the best solution/resolution for this problem: § Conceptual Recommendation: Add REF Segment REF~01=1W for MOU/EC only to populate with MOU/EC Membership Number. Question has does this informatio | Open
2004-04-01 | MOU/EC | Austin En |  | Change 810_03 to separate cancel examples into a 3-step process: (1) original (2) cancel (3) re-bill. Similar to changes that were made to 810_02. |  | (6/23/04) No progress yet Update 08/25/04 -Bernie Dawson and Kathy Scott will work to creat | Open
2004-04-01 | MOU/EC |  |  | Change 814_18 to handle co-op membership requirements. Landlord billing information. | Low Priority | (6/23/04) No progress yet Update 08 | Open
2004-05-01 |  |  |  | 864 straw dog example | Johnny Robertson and Cary Reed to draft example | (6/23/04) In progress, expect report in August or September. (8/17/04) Cary and Johnny should be able to provide this information at the September meeting (10/12/04) Cary and | Open
2004-05-01 |  | Mass Transition Taskforce |  | Mass Transition Phase 1 |  | (6/23/04) To be addressed along with MT Phase II (8/17/04) Phase II Meeting has been scheduled 9/30/04 at ERCOT Met Center Room 168 | Open
2004-05-01 |  | CNP |  | 814_21 pass-through to TDSP | Kathy Scott to create draft change control for updating the 814_20 business process | (6/23/04) Kathy submitted the CC at June TX SET (8/17/04) TX SET Sub team had a meeting in Dallas on July 12, 2004. TX SET is waiting for responses back from CRs on concerning their rejects or 814_21 before the next steps are taken (10/ | Open
2004-07-01 |  | TX SET Leadership |  | Action Items List |  | (6/23/04) Leadership will provide a printed copy of the most recent list of Outstanding Action items at each TX SET meeting. | Open
2004-07-01 | TDSP | RMS |  | TDSPs look at the reasons why estimations are being created, if reason is flagged into any internal systems? What are some of the options for CRs when consecutive estimates are encountered? Discussion was to consider a new segment in the 867_03 and 867 | 09/22/04 Update: Sub-team was asked by Texas SET to add general guidelines in the event of a estimated usage for both CR and TDSP . This information will be brought back to the October TX SET meeting and possibly presented at the October/November RMS | (10/12/04) Update - Bill Reily will be placed on the November 2004 Texas SET agenda to discuss the recommendations of the subteam to Texas SET | Open
2004-07-01 | CR | RMS |  | CRs what are you doing when you receive an 867_03 transactions with the Estimation Flag indicated in the transaction, as well as, the MEA Segment flag showing EE (Meter reading-beginning estimated/ending estimated) previous and current billing estimated. | 09/22/04 Update: Sub-team was asked by Texas SET to add general guidelines in the event of a estimated usage for both CR and TDSP . This information will be brought back to the October TX SET meeting and possibly presented at the October/November RMS | (10/12/04) Update - Bill Reily will be placed on the November 2004 agenda to discuss the recommendations of the subteam to Texas SET | Open
2004-07-01 |  | DEWG |  | Linked ESI ID issue- TX SET needs to determine how the TDSPs use the address field in the 814_04, is it echoed back from the 814_03 or do they pull the actual service address from their systems. Note: Where requirements are identified for flushing ou | ERCOT will look into whether this type of information can be obtained | (8/17/2004) Update will be provided to TX SET at the September Meeting - Plan is to take a sample of July's 814_04 to determine where the problems may be initiated (10/12/04) Update - Meeting will be arranged with ERCOT and TDSPs prior to the November 200 | Open
2004-08-17 |  | RMS |  | Texas SET v2.1 to be Redline |  |  | Open
2004-08-17 |  | RMS |  | Customer Protection Rules as per discussions with PUCT Staff. Need to develop a process to support Customer Protection Rule 25.472 Section b Paragraph 3 | Bill Reily will lead a TX SET sub-team to address issues and what is needed to support Customer Protection Rule for Historical Usage for Commercial and Industrial retail customers where usage is considered competitively sensitive. | (10/12/2004) Bill Reily and Texas SET is awaiting guidance from PUCT Staff (Lauren Damen) on this Action Item | Open
2004-08-17 | TX SET Leadership |  |  | Should there be some documented procedures for Market participants to communicate non-emergency system/process and/or procedure changes? | TX SET Leadership has a question of RMS Leadership Communicating Market information - Who does what, when (how early, deadline, or timelines) and how should information be communicated. | (10/12/04) Kathy Scott will take request to Lon Conn and Karen Farley to add this process to the RMS Assignment Form | Open
2004-08-17 |  | ERCOT |  | If an 814_20 maintain is sent (ASI~7~001) is it expected that there will always be a REF~TD (reason for change) present, either at the header level (LIN Loop) or meter level (NM1 Loop)? | CR's will check to see if they expect a REF~TD when an NM1~MX exists. REF~TD validation cannot be added to the ASI segment. | (10/12/04) To be discussed at the November 2004 Texas SET Meeting | Open
2004-08-25 |  | ERCOT |  | In an effort to address 814_23 rejects ERCOT has created reports, by CR, that list the 814_23 rejects received, with the reject reason. The data pulled is from June 03 to current. ERCOT would like to take the same approach as used for the 814_21 reject | ERCOT (Suzette Wilburn and Tom Baum) will compile the results from 814_23 reject to send to the CRs for additional information as to the reasons for the rejection. This will only be analysis and fact finding to resolve the issue of receiving these type r | (10/12/04) ERCOT will bring post MIMO data to the January 05 TX SET Meeting | Open
2004-08-31 | MOU/EC |  |  | If MOU/EC has disconnected services for Non-Payment for a customer is there a possiblity that the CR would send a MVO for the customer based upon the DNP being completed. Customer may come in to pay outstanding bill to MOU/EC but the ESI ID has been fin | Nueces - will monitor this process to determine if a change control is needed | 08/25/04 - Nueces - will monitor this process to determine if a change control is needed | Open
2004-09-22 |  | ERCOT |  | There has been 867_03F showing up on the ERCOT 867 Error Report that is sent to the CRs and TDSPs that have the same date in the DTM150 and DTM151 segments | ERCOT would like to find out what type of scenario would cause this and let the market know that ERCOT is not loading this data, and it doesn't appear that corrected usage was sent |  | Open
2004-09-22 |  | Market Rules |  | Diana Zake is sending out a request for TX SET representatives to attend a meeting on October 5th to review the reamil market-operating guide | Request that Market participants including Texas SET members assist in making revisions/updates and reformatting Retail Market Guide along with it's associated documents |  | Open
2004-09-22 | MOU/EC | Eloise Flores |  | MOU/EC will need a way to identify the membership number in all EDI Transactions | Change control will need to be written to apply to all EDI transaction to add a new REF Segment (REF~1W) for all EDI transactions that will be used to pass the membership number |  | Open
2004-09-22 |  | ERCOT |  | Change Control 2004-636 Withdrawn Written to remove the Business Process Ov | Suzette Wilburn and Johnny Robertson will work together to provide a revised change control to remove the BPO from the 814_20 Implementation Guide. |  | Open
2004-09-22 |  | BJ Flowers |  | CNP's Process: for MVI and MVOs with the two day window, CRs submit the current FasTrak spreadsheet directly to CNP that would normally be sent as a FasTrak to the TDSP. CNP then submits an 814_28 Complete Unexecuteable '09' to cancel order using automa | BJ Flowers is reqeusting other TDSPs to review this change in process made by CNP for handling MVIs and MVOs with the two day wind and to consider implementing this new process. CRs are requesting consistency in this process. |  | Open
2004-09-22 | TDSP | ERCOT |  | How do TDSPs communicate a meter removal on an 867_03? Can ERCOT expect to receive a DTM150 and a DTM 151 on ev | TX SET representatives will check to see if sending a DTM150/DTM 151 with the same date is valid |  | Open
2004-09-22 | ERCOT | TX SET |  | TX SET requested and required that TX SET be involved in defining the requirements that are used to write the ERCOT SIRs. | ERCOT (Suzette Wilburn) noted that they would include TX SET when writing the requirements and text for the SIRs prior to them being implemented. TX SET also discussed the need for TX SET involvement in the Retail Market Call for those instances when an |  | Open
2004-10-12 |  | Constellation |  | Usage Smoothing- What does each TDSP do? Cancel/Rebill True-up in subsequent cycles Other? | Robert Rodriguez will lead a small group of CRs to document the questions that need answering by the TDSPs concerning cancel re-bill procedures, smoothing, and zero usage. Sub-team: Kyle Patrick, Charlie Bratton, Rob Bevill
2004-10-12 |  | Direct Energy |  | Reject for Original Tracking Number from the originating transaction be provided on the 867-03 Final to provide issuing the 824 Reject transaction | Rita Morales will work with Suzette Wilburn to examine some real instances that apply to this scenario for ERCOT investigation and for Direct to provide some information to other CRs on how they are handling this particular scenario.
2004-10-12 | ERCOT | Texas SET |  | What is the appropriate process for cancelling DROP to AREP based upon version 2.0 and Protocols. | Because the Implementation Guide for the 814_08 is out of Synch with the documented procedures for a CR to Cancel a Drop to AREP in Protocols in Chapter 19 - Suzette Willburn (ERCOT) will investigate if ERCOT and/or James Cohea's group can provide a stan
2004-10-12 | Texas SET | ERCOT |  | Request from ERCOT to investigate the FasTrak Inadvertant issue | Texas SET Sub-team will work to investigate ERCOT's recommendations: Kyle Patrick, Suzette Wilburn, Charlie Bratton, Cary Reed, Tom Baum, Rob Bevill, Johnny Robertson, Kathy Scott
2004-10-12 |  | Texas SET |  | Redline version 2.0A | All Texas SET transactions were assigned to SET Members for review and verify redline changes according to v2.0A approved and recommended for v2.0A Change Controls. Review Date Completion: Redline Date Completion:
2004-10-12 |  |  |  | Change Control 2004-644 Removed the Transformer Loss Adjustment codes TA-TE to approve Change Control | TDSPs will need to discuss that if these codes are necessary for the 810 Billing Determinants - CRs will complete and internal evaluation as well. If it is found to be of value by either side then a change control will be prepared for November 2004 Change

## 2004 Closed Action Items
Meeting | Segment | Sponsor | CC | Issue | Action Item | Resolution | Status | Date
January |  | RRI |  | Would like to investigate possibility of adding a flag to indicate whether the meter is temporary or permanent | CRs will meet to re-frame the question and provide the TDSPs with exactly what they'd like to see |  | Closed | 2004-02-17
January |  | RRI |  | Would like to investigate the possibility of adding a code on the 814_16 and 650 series that would provide gate access codes | Group agreed that more time was necessary to determine if there was a need for this type of information from all CRs |  | Closed | 2004-02-17
January |  | ERCOT |  | Review of the draft 867_01 IG for opting in entities | TDSPs to review guide with SMEs at their companies to verify guide contains all necessary segments and data elements | TX SET believes that the cost for re implementing the 867_01 is much larger than the cost for using a flat file on a on going basis. | Closed
January |  | ONCOR |  | Outdated scheduled transactions in ERCOTs system that cannot be completed | ERCOT to investigate if a common theme exists for the manual processes used to 'fix' these scheduled transactions to get a better idea of where TX SET needs to focus their attention | Comment 5/19/04: No true common theme, but the problem centers around previous versions (1.4, 1.5) trxs cannot be completed with future releases (1.6, 2.0). Kyle Patrick will refer to MCT for future discussion. | Closed
January |  | ERCOT | Y | Clarification needed on how maintenance to unmetered service devices are communicated in the 814_20 | 814_20 guide needs to be updated if the 814_20 is not used when maintaining unmetered service devices. TX SET to investigate the possibility of adding this functionality to the 814_20 | TDSPs waiting for response on whether they send 814_20s. | Closed
January |  | CNP | Y |  | 867_03 How to Use Section meeting needs to be arranged to convert the How to Use to a BPO and make the appropriate updates in the new BPO document. | Comment April TX SET: This will be an agenda item for the May meeting of TX SET in Dallas. Comment May TX SET: This will be an agenda item for the June meeting of TX SET. | Closed
January |  | TX SET |  |  | TX SET Leads need to develop a process that would remind members of outstanding and/or open action items prior to monthly meetings (1 or 2-weeks before if possible) | Leadership will remind team members of action items when meeting notice and agenda are sent. | Closed
|  | ERCOT |  | In the case of a MOV to CSA, when an 814_08 is submitted by the Cur CR, is the TDSP expecting the Cur CR or CSA CR Duns in the N1~SJ? I would believe it would be the CSA CRs Duns, because the TDSP would have received an 814_03 with the CSA CRs informatio |  | ERCOT will be putting the CSA CR in the 814_08 | Closed
February |  | TX SET |  | Review BPOs for 2.0 | Cary Reed, Kyle Patrick, Suzette Wilburn, JR, and Bill Reily will review. | Comment 5/19/04: Team to meet 5/25/04 in Austin, TX venue to be determined. | Closed
February |  | ERCOT | Y | · In the event that there are multiple meters exchanged on a premise, would the profile code be listed in both NM1 loops? We have seen some instances where the profile code update (REF~LO) is included in the second NM1 loop and wanted to verify that prof | S. Wilburn to write a change control to move the REF~LO segment to the LIN loop | Comment 5/19/04: Change control has been written but not submitted. | Closed
February |  |  |  | · The N303 in the N3 segment of the 814_20 is alphanumeric. (AN1/55). Would like to find out from the group if they would like to see ERCOT rejecting transactions that send special characters in this field. o Encountered issues with double quotes in th | ERCOT will communicate to the team what decision they decide to go with regarding the cross validation | ERCOT put validation in that reject double quotes in the address field. | Closed
February |  |  |  | · Following up on the issue regarding 814_20 retires being received on de-energized ESI-Ids with a scheduled MVI. We have a proposed short term solution o If the SMRD of the MVI is greater than the date on the retire, we cancel the MVI o If the SMRD of t | ERCOT will implement a fix in a near release to reject any 814_20 retires received on a de-energized premise with a scheduled service order. TDSP will open a fastrak issue to get open service order resolved. Release date is still to be determined. ERCO | ERCOT will follow the short term solution in the recommendation | Closed
February |  | Nueces |  |  | E. Flores to gather all issues addressed to date regarding the Muni/Coop market to send out to the market | This will be an ongoing list | Closed
February |  | TX SET Officers |  |  | TX SET officers to make phone calls to the muni/coops about the meeting | MOU/EC meeting was held on 4/19/04 in Corpus Christi | Closed
February |  | ERCOT |  |  | ERCOT Client Services to pull together email to be sent out inviting all Muni/Coops to attend the day meeting on April 20th | MOU/EC meeting was held on 4/19/04 in Corpus Christi | Closed
February |  | TCE/STEC | Y | We need to talk about the 650_04 disconnect/reconnect process on the muni/coop side. There was some discussion at Texas Test Plan script sub team on this regarding the current test script calling for a 650_04 cancel of the disconnect request to indicate | TCE to work with STEC to write change control for adding a new code to the 650_04 to communicate this information | Comment 5/19/04: Jeff Thomas to update SET on this. | Closed
February |  | ERCOT | Y | Should a REF~IX always exist when a REF~4P is present in the 814-04? · For example, if you have a REF~MT~COMBO and two REF~4Ps should you also have two REF~IXs? · If not, what circumstances exist when you wouldn't, and what type of modifications could be | o (Action Item) S.Wilburn to write a change control to update the examples in the 814_04 | Comment 5/19/04: Change control was written, and withdrawn. The text will be left in the example. TX SET again stresses that MPs should code to the guide section not the examples section. | Closed
February |  | TX SET |  | "Future Implementation CCs aka Unassigned CCs" Review. (SEE WORKBOOK PAGE UNASSIGNED CHANGE CONTROLS) | TX SET members to review all "Unassigned" Change Controls at future meetings. | TX SET will begin to work on the Future Version of the I.Gs using the Unassigned change controls in this next release. | Closed
February |  | TX SET |  | Revised Working Group Procedures | TX SET members should review the Working Group Procedures Redline | Comment 5/19/04: TX SET reviewed the WG procedures they will be posted for review. WG procedures to be an agenda item at the June meeting. (6/23/04) Approved with changes on June 22, 2004- | Closed
April |  | TX SET Chair |  | ERCOT should not be completing Safety Net MVIs without electronic trx. |  | TX SET presented this back to RMS in its RMS report at the May '04 Meeting. It was TX SETs opinion that all MPs and ERCOT who participate in the Safety Net process should follow the approved guidelines. | Closed
April |  |  |  | REF~1P removal issue | CRs will discuss and frame issue prior to this becoming a TX SET agenda item. | TX SET discussed at the April meeting, the REF~1P change control was withdrawn. | Closed
April |  | ERCOT |  | 814_07 Rejects | ERCOT to develop a proposal for handling 814_07 rejects. | (6/24/04) Suzette Wilburn brought recommendations to TX SET on this. | Closed
2004-05-01 |  | ERCOT |  | ERCOT service orders completed without transactions | ERCOT to draft proposal to TX SET for reporting back to RMS | (6/23/04) ERCOT to bring back information to next TX SET meeting regarding instances where complete w/out trx occurs. | Closed | 2004-08-17
2004-05-01 |  | TX SET |  | Flag on 814_24 for instances where the first is '09'd and a second is sent | Suzette Wilburn, Kyle Patrick, Charlie Bratton, Kathy Scott to review 824 Workshop documentation and begin drafting new codes | (6/23/04) Team has not met. (8/17/04) Change Control has been written and update for discussion and approval on 8/18/04 | Closed | 2004-08-17
2004-05-01 |  | RMS |  | TDSPs to document estimation processes |  | (6/23/04) TDSPs did so at June meeting. TX SET chair to either report or request time to report to RMS at July meeting. | Closed | 2004-08-17
2004-05-01 |  | Customer Protection |  | Customer Protection compliance | Bill Reily and Charlie Bratton to organize TDSP/CR reviews of the rule | (6/23/04) Bill and Charlie to bring back report to a next TX SET meeting. (8/17/04) Subteam assigned to discuss issues and make recommendations | Closed | 2004-08-17
2004-05-01 |  |  |  | Change Control 503 | Bill Reily to draft change control | (6/23/04) Bill will draft CC prior to CC deadline for next release. | Closed | 2004-08-17
2004-05-01 |  | TXU ED |  | 867_02 large file of data | Bill Reily to bring recommendation to June Meeting | (6/23/04) Bill will bring back suggestion at a later meeting. (8/17/04) TXU ED will send additional files similar to the same process as CNP | Closed | 2004-08-17
2004-06-01 |  | CNP |  | 867_03 BPO - additional create 867_03 scenario examples to be incorporated along with gray-box changes to create one change control for the 867_03 Implementation guide | Suzette Wilburn, Tom Baum, and Kathy Scott to draft document | (6/23/04) Due to length of this document and the number of changes included in the redline version, a review of this document will be deferred to the next Texas SET meeting for discussions. The updated document will be included in the minutes for SET Mem | Closed | 2004-08-17
2004-07-01 |  | TX SET Sub-team |  | TX SET Subteam will discuss and develop change controls for the 814_24 (TITF Taskforce), 824 and 810_02 (810/867/824 Taskforce), 650_01 (DNP/Reconnect Taskforce) and Redlines for BPOs process changes | Shannon Bowling, Suzette Wilburn, Kyle Patrick, Cary Reed, Charlie Bratton, Brett Harper, Bill Reily, Tom Baum, Robert Rodriquez, Kathy Scott | (8/17/2004) This action item includes several other action items- to eliminate redundancy this one was closed | Closed | 2004-08-17
2004-07-01 |  | RMS |  | TX SET - Discuss an Implementation Timeline for: 810 Billing Determinants for 810/867/824 Workshops Additional SAC04 Codes requested by CNP at July RM |  | (8/17/2004) This action item includes several other action items- to eliminate redundancy this one was closed | Closed | 2004-08-17
2004-07-01 |  | DNP Taskforce |  | TX SET Sub-team develop draft straw man of adding 3 new codes into the current YNQ Segment where CRs must give TDSPs the autohrization to Disconnect service for non-payment at one of the following disconnect points: | Shannon Bowling, Suzette Wilburn, Kyle Patrick, Cary Reed, Charlie Bratton, Brett Harper, Bill Reily, Tom Baum, Robert Rodriquez, Kathy Scott | (8/17/2004) Change Control already written and up for discussion and approval on 8/18/2004 | Closed | 2004-08-17
2004-07-01 |  | Jennifer Teel- EC Power |  | Change Control needed on the 814_02 Transaction LIN Segment for SW data element - Gray Box Clarification needed to remove or eliminate the statement DTM~MRR is required when requesting an off-cycle read. There is no DTM~MRR segment in the 814_02 transa | Suzette Wilburn and Tom Baum | (8/17/2004) Change Control already written and up for discussion and approval on 8/18/2004 | Closed | 2004-08-17
2004-07-01 | PUCT Staff | Customer Protection |  | Lauren Damen (PUCT Staff) reqeusted that Bill Reily (TXU ED) re-send the same email that was forwarded to Brian Lloyd to her attention for clarification concerning competitively sensitive information regarding historical usage for C&I customers | Lauren Damen and Bill Reily | (8/17/2004) PUCT Staff provided Clarification to Bill Reily on this action item | Closed | 2004-08-17
2004-07-01 | TDSP | ERCOT |  | Follow-up 814_20 move the REF~LO Load profile from Meter level to ESI ID Level, however the 814_20 guide has load profiles communited at a meter level. TDSPs will review the proposed chane controls to move the load profile segement from the NM1 loop in | TDSPs to provide an update to this question | (8/17/2004) TDSPs agreed that this is not an issue and there should not be any market reason to make this change | Closed | 2004-08-17
2004-04-01 | MOU/EC | TX SET |  | Change 814_28 to allow move-in to be pended because customer is not a member of the co-op. | High Priority | (6/23/04) Redlined document posted to May meeting documents (08/17/04) No progress yet | Closed | 2004-10-12
2004-04-01 | MOU/EC | Austin En |  | Change 820_03 to allow for a code to reference a credit pmt. | N/A | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discus | Closed | 2004-10-12
2004-04-01 | MOU/EC | Nueces |  | Change 820-payment adjustments 6000 record to allow credits and debits in the total payment field for the batch total. | High Priority | (6/23/04) No progress yet Update 08/25/04 -Change control 2004_607 already | Closed | 2004-10-12
2004-04-01 | MOU/EC | Austin En |  | Change 810_03 to include information on deferred payment agreements that CR has set up with customer. | N/A | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discuss o | Closed | 2004-10-12
2004-04-01 | MOU/EC | Austin En |  | Change 810_03 to include reasons for cancel (BIG segment): usage or monetary correction. Similar to changes that were made to 810_02. | N/A | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to disc | Closed | 2004-10-12
2004-04-01 | MOU/EC | CPS |  | Why can't a 814_01 originate from the MCTDSP since customer remains with MCTDSP? | N/A | (6/23/04) No progress yet Update 08/25/04 - This was not the decision made by the Market prior to Open Competition and was not chosen to be the Current Market model. | Closed | 2004-10-12
2004-04-01 | MOU/EC | LCRA |  | With exception of PC & PD, all other 814's go through ERCOT. Since MOU/EC don't unbundled, why do 814's still need to go thru ERCOT? Same question with 867's? Since CR and TDSP functions handled at same office? | High Priority | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to dis | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | If customer calls TDSP first, can there be an enrollment from the TDSP. Can the TDSP go ahead and set up customer? Since other city services need to be set up? -Responses - lots of discussion about scheduling power, how can you without CR, etc. | N/A | (6/23/04) No progress yet Update 08/25/04 - This was not the decision made by the Market prior to Open Competition and was not chosen to be the Current Market model. | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | Make 814_PC bi-directional. | High Priority | (6/23/04) No progress yet - Update 08/25/04 - Change control will be written to allow the 814_PC to be bi-directional only for MOU/EC Markets. Note | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | In MOU/EC T&C's - city services also paid 1st, or just electricity? -ACTION ITEM - read/interpret T&C's | N/A | (6/23/04) No progress yet Update 08/25/04 - This is not a Texas SET issue | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | More than move-in, would like to see bi-directional move-out. For forwarding of final bill, capital credits check, etc. | High Priority | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discuss or provide any information as to the problems, issues, and possible recommendations for this issue | Closed | 2004-10-12
2004-05-01 |  | 810/867/824 Taskforce |  | 824 new codes | Suzette Wilburn, Kyle Patrick, Charlie Bratton, Kathy Scott to review 824 Workshop documentation and begin drafting new codes | (6/23/04) Team has not met. (8/17/04) Sub-team planning on meeting, hopefully for 8/24/04 meeting in Houston 10/12/04 - Draft Change Control written and discussed by SET | Closed | 2004-10-12
2004-05-01 | TDSP |  |  | 650_01 1 to 1 relationship | TDSPs to verify that they are responding the 650_01s on a one to one relationship and bring back at June Meeting | (6/23/04) Cary Reed to refer this to Blake Gross and Shannon Bowling (DNP/REC TF). Also change control 2003-496 should clear this issue up. (8/17/04) Cary Reed, Suzette Wilburn and Kathy S | Closed | 2004-10-12
2004-05-01 |  |  |  | 814_28 redline document MOU/EC | TX SET to document the different scenarios that would be affected by membership codes suggested for the 814_28 | (6/23/04) The TDSPs will get together along with MOU/EC to make a list of the Reasons for Pending a Move-In or Move-Out to cover the majority or the higher percentage of reasons for pending a request. Cary Reed will send an open invitation to Eloise and | Closed | 2004-10-12
2004-07-01 |  | TX SET Leadership |  | PRS will have their Annual Budget Priorization meeting scheduled August 27, 2004 where TX SET Leadsership will ask for a spot on this meeting's agenda. Tenative Schedule for TX SET for 2005 (4th Quarter Implementation) and a list of approved change contr | Kyle Patrick, Kathy Scott and Bill Reily - TX SET Chair and Vice Chairs | Leadership attended the Annual Budget Priorization Meeting and Texas SET 2.1 has been placed as high priority for 2005 ERCOT Budget | Closed | 2004-10-12
2004-07-01 | Market |  |  | TX SET representatives will go back to their companies to review the approved gray box/example change controls and come back with any concerns for updating the guides with these approved change controls for version 2.0A release schedule |  | Change Controls for version 2.0A have been completed and agreed to by Texas SET | Closed | 2004-10-12
2004-08-17 | TDSP/MOU/EC |  |  | (6/17/2004) Initial discussion has been to change 814_28 to allow move-in to be pended because customer is not a meter of the co-op. With an interval of time expiring and 814_08s being sent for membership fees not sent to the MOU/EC - | Cary Reed will organize a second meeting with the TDSPs and MOU/EC to discuss and flush out issues with using either the 814_28 or 814_04 transactions for membership fees and assigned membership numbers for those customers that have been established as me | Sub-team meeting scheduled August 25 and 26, 2004 in Corpus Christi, Texas - Sponsored by AEP (Cary Reed) Sub-team members/participants: Bernie Dawson, Bill Reily, Eloise Flores, Cary Reed, Bre | Closed | 2004-10-12
2004-08-17 |  | RMS |  | Update on service address comparison request. Identifying how large the issue is with regard to the service address sent on the initiating transactions and what is received on the 814_04 from the TDSPs | ERCOT completed query for the month of July-found 30,000 records- Suzette Wilburn (ERCOT) will breakout these 30,000 ESI IDs into subsets by TDSP territory to be distributed by end of next week. A sample will be taken from this sub-set to determine exte |  | Closed | 2004-10-12
2004-08-17 |  |  |  | Time Table and/or schedule for v2.1 Change Controls | Suzette Wilburn and Tom Baum (ERCOT) will work on developing a time time and/or schedule for v2.1 Change Controls, Communications, Baseline of Implementation Guides, and Posting to ERCOT web-site for updated guides |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2004-597 was marked as a graybox change. This requires adding a new code to the 814_13. Should be marked as system change |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2004-610 request additional language to the 810_02. Now tha we are removing the BPOs, we need to make sure this language was captured in the guide and discuss submitting this CC to be nullified. Charlie Bratton and Jason Bear will create a change con |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2003-496 adds clarificatoin to the 650_02 for disconnects. TX SET will need to review the content of this change contol to determine if it is still valid. |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2003-538 updates examples in the 867_03 but this is marked as a system change. Need to re-classify as gray box/example change. |  | Closed | 2004-10-12
2004-08-17 | TX SET Leadership |  |  | What is the process or procedure for Market participants to take when a Market participant is not following Market Guidelines or Rules? | TX SET Leadership has a question of RMS Leadership | (10/12/04) Kathy Scott will take request to Lon Conn and Karen Farley to add this process to the RMS Assignment Form | Closed | 2004-10-12
2004-08-25 | MOU/EC |  |  | Need to re-visit 2004_609 for Reconnect after Disconnect for Non-Payment | High Priority | 08/25/04 -Bernie Dawson will rework change control 2004_609 to apply correct ANSI standards for Reconnect processing by MOU/EC (10/12/2004) Bernie Dawson provided this change control to Texas SET and some revision were made by the team. Bernie will | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: | The 810/867/824 Workshop Taskforce agreed that extending the 2 day timeframeto 5 days will fix several validations and rejcection problems created by enrollment transacations missing or delayed The agreement by the TDSPs would be the 2 day rule WILL be | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: | The 810/867/824 Workshop Taskforce agreed that extending the 2 day timeframeto 5 days will fix several validations and rejcection problems created by enrollment transacations missing or delayed The agreement by the TDSPs would be the 2 day rule WILL be | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: | The 810/867/824 Workshop Taskforce agreed that the Stacking Solution is designed to fix this with a response driven cancel process for all cancels. TX SET should re-visit this in six months to a year AFTER stacking has been implemented for evaluation th | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: | The 810/867/824 Workshop Taskforce agreed that extending the 2 day timeframeto 5 days will fix several validations and rejcection problems created by enrollment transacations missing or delayed The agreement by the TDSPs would be the 2 day rule WILL be | 10/12/2004 Draft Change Control was created to provide new rejection code to providing this information | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | Dates Don't Match or New CR COMMENTS: | For inadvertent switches, the Inadvertent switch task force will handle the resolution. Remainder should be deferred and governed by the PUC ruling around this issue Re-evaluate after MIMO implementation | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12

## 2.0A Change Controls
Change Controls
| Approved | Transactions | Version | Scope | TX SET Version | Description | Notes
3_530 | Y | 650_01 | Future | Gray Box/Examples | V2.0A | Cleanup of Gray box and Example | Valid per TX SET review 3/24/04
3_538 | Y | 867_03 | Future | Gray Box/Examples | V2.0A | Changes to examples in the Implementation Guide | Valid per TX SET review 3/24/04
3_539 | Y | 814_29 | Future | Gray Box/Examples | V2.0A | Add the BGN07 code to the gray box example in BGN segment | Valid per TX SET review 3/24/04
3_573 | Y | 814_08 and 814_09 | Future | Gray Box/Examples | V2.0A | Remove references to the word "reinstate" in the 814_08 and 814_09 transactions | Valid per TX SET review 3/24/04
3_574 | Y | 814 PC | Future | Gray Box/Examples | V2.0A | Remove existing transaction notes form the 814 PC guide | Re-evaluate for validity (497, 498, 574, 596)
3_577 | Y | 814_17 | Future | Gray Box/Examples | V2.0A | Example 1 and 3 of the 814_17 guide need to have the REF*7G segment revised to match the new reject code detail put in place by the V2.0 change controls | Valid per TX SET review 3/24/04
3_581 | Y | 867_04 | Future | Gray Box/Examples | V2.0A | Example change | Valid per TX SET review 3/24/04
3_583 | Y | 814_02, 11, 17, 19, 21, 25, 27 | Future | Gray Box/Examples | V2.0A | if same BGN02 comes from two different CRs one will be rejected | Valid per TX SET review 3/24/04
3_594 | Y | 814_08 | Future | Gray Box/Examples | V2.0A | MIMO clean up | Valid per TX SET review 3/24/04
4-595 | Y | 814_12 | Future | Gray Box/Examples | V2.0A | MIMO clean up | Valid per TX SET review 3/24/04
4-598 | Y | 814_08,09 | Future | Gray Box/Examples | V2.0A | provide examples | Valid per TX SET review 3/24/04
4-602 | Y | 814_08 | Future | Gray Box/Examples | V2.0A | MIMO clean up | Valid per TX SET review 3/24/04
2004-605 | Y | 814_25 | Future | Gray Box/Examples | V2.0A | Update the examples in the 814_25 examples to include the Move Out Date which is required in accept transactions | Recently approved by Texas SET
2004-608 | Y | 820_02 | Future | Gray Box/Examples | V2.0A | Corrected examples for the 820_02 | Recently approved by Texas SET
2004-611 | Y | 867_03 | Future | Gray Box/Examples | V2.0A | 867_03 DTM~514 Gray Box in the PTD~PM loop contains example errors. Also need to correct Example #15 & #16 to reflect this correction (examples added in CC2003-538). | Gray Box/Examples OK for Graybox and Examples changes, however Examples need to be corrected Date incorrect for changed examples -
2004-613 | Y | 814_01, 814_03, 814_16 | Future | Gray Box/Examples | V2.0A | Cleanup of graybox on N404 element. The URL does not work. | Recently approved by Texas SET
2004-614 | Y | 814_08, 814_09 | Future | Gray Box/Examples | V2.0A | There have been questions on whether the REF~1P segment can be sent multiple times on the 814_08 and therefore sent back multiple times on the 814_09 | Recently approved by Texas SET
2004-617 | Y | 814_20 | Future | Gray Box/Examples | V2.0A | Update the DTM Effective Date gray box, DTM Start Date gray box, & DTM End Date gray box to reflect validations that are in ERCOT’s Lodestar system. | Recently approved by Texas SET
2004-620 | Y | 814_08 | Future | Gray Box/Examples | V2.0A | Update the BGN06 gray box to indicate the 814_08 BGN06 will match the BGN06 of the 814_14 or 814_22 in situations where there is a Drop to AREP or Move out to CSA | Recently approved by Texas SET
2004-623 | Y | 650_01 | Future | Gray box/Examples | V2.0A | Remove Businesss Process Overviews from the Implementation Guides and incorporate that logic into the graybox or data element itself of the Implementation guideline | Approved on 8/18/04 by Texas SET
2004-625 | Y | 810_02 | Future | Gray box/Examples | V2.0A | Remove Businesss Process Overviews from the Implementation Guides and incorporate that logic into the graybox or data element itself of the Implementation guideline | Approved on 8/18/04 by Texas SET
2004-626 | Y | 814_18 | Future | Gray box/Examples | V2.0A | Remove Businesss Process Overviews from the Implementation Guides and incorporate that logic into the graybox or data element itself of the Implementation guideline | Approved on 8/18/04 by Texas SET
2004-628 | Y | 867_03 | Future | Gray box/Examples | V2.0A | Remove Businesss Process Overviews from the Implementation Guides and incorporate that logic into the graybox or data element itself of the Implementation guideline | Approved on 8/18/04 by Texas SET
2004-630 | Y | 814_02 | Future | Gray box/Examples | V2.0A | In the LIN07, remove the DTM~MRR text from the SW data element since it is not being used. | Approved on 8/18/04 by Texas SET
2004-634 | Y | 810_02, 810_03, 820_02, 820_03 824 814_01 thru 814_29 814_PC, 814_PD 867_02, 867_03, 867_04 650_01, 650_02 650_04, 650_05 | Future | Gray box/Examples | V2.0A | Additional language should be added to each Transaction SET to identify the requirements and required response to the 997 Functional acknowledgement | Approved on 8/18/04 by Texas SET
2004-637 | N | 814_04 | Future | Gray box/Examples | V2.0A | Add graybox clarification to NM1 and REF segments to better communicate what is requires when transmitting meter level information. | Approved 9/22/04 with modifications by Texas SET
2004-638 | N | 814_08 | Future | Gray box/Examples | V2.0A | Update example # 5 of 5 to correctly show “New CR” in the description of the field. | Approved 9/22/04 by Texas SET
2004-640 | N | 814_03 | Future | Gray box/Examples | V2.0A | Update the graybox text for the LIN07 codes. Correct the following text by moving it from the MVI graybox to the MVO graybox | Approved 9/22/04 by Texas SET
2004-641 | Y | 810_02 | Future | Gray box/Examples | V2.0A | Apply BPO clarification from nullified CC2004-610 to the appropriate gray box | Approved 9/22/04 by Texas SET

## 2.0A Redline Matrix
2.0A Redline Project
Action | Due Date
SEF and Redline Complete | 2004-10-08
Verified Redline Comments Due to TBAUM@ERCOT.COM | 2004-11-05
Transaction | TX SET Volunteer | Analysis Results | Changes to be applied | Redline Verified? | Additional Comments Necessary?
650_01 | Rob Bevil
650_02 | Rob Bevil
650_04 | Warren Duke
650_05 | Warren Duke
814_PC | Warren Duke
814_PD | Warren Duke
814_01 | Brett Harper
814_02 | Brett Harper
814_03 | Lori Smith
814_04 | Lori Smith
814_05 | Rita Morales
814_06 | Rita Morales
814_07 | Chuck Moore
814_08 | Cary Reed
814_09 | Cary Reed
814_10 | Chuck Moore
814_11 | Bill Reily
814_12 | Bill Reily
814_13 | Johnny Robertson
814_14 | Johnny Robertson
814_15 | Charlie Bratton
814_16 | Charlie Bratton
814_17 | Bernie Dawson
814_18 | Bernie Dawson
814_19 | Suzette Wilburn
814_20 | Suzette Wilburn
814_21 | Kathy Scott
814_22 | Kathy Scott
814_23 | Kyle Patrick
814_24 | Kyle Patrick
814_25 | Kyle Patrick
814_26 | Suzette Wilburn
814_27 | Suzette Wilburn
814_28 | Johnny Robertson
814_29 | Charlie Bratton
810_02 | Robert Rodriguez
810_03 | Bernie Dawson
820_02 | Johnny Robertson
820_03 | Bernie Dawson
867_02 | Kathy Scott
867_03 | Robert Rodriguez
867_04 | Kyle Patrick
824 | Carrie Rohrer

## Unassigned Change Controls
Change Controls
| Approved | Transactions | Version | Scope | TX SET Version | Description | Notes
pending | pending | 810 |  | System | TBD | Potential 810 - 867 billing determinants changes
pending | pending | 810_02 |  | System | TBD | allow TDSP to send single corrected invoice for non-IDR meters
2-466 | Y | 650_04 | Future | System | TBD | Add code to 650_04 provide means to alert CR that service has been permanently suspended for ESI ID and numerous gray box changes | Valid per TX SET review 3/24/04
2-468 | Y | 810_03 | Future | System | TBD | Multiple 810_03 changes - code gray box | Valid per TX SET review 3/24/04
3-471 | Y | 650_04 | Future | System | TBD | remove must use from the YNQ04 of the NQ~5U segment | Valid per TX SET review 3/24/04
3-490 | Y | 814_14, 814_22 | Future | Gray Box/Examples | TBD | remove QTR from valid values of Meter Type from the gray box | Valid per TX SET review 3/24/04
3_493 | Y | 814_27 | Future | System | TBD | Make the N1~8S OPTIONAL on the 814_27 to be consistent with the 814_26 N1~8S loop | Valid per TX SET review 3/24/04
3_496 | Y | 650_02 | Future | System | TBD | Provide additional detail on when 650_02 should be generated and how the process should work for disconnect and reconnect for non-pay | Re-evaluate-Jennifer Teel, Bill Reily, Kathy Scott. CC was referred to Shannon Bowling and Blake Gross of Disco Reco TF.
3_497 | Y | 814_PD | Next Release | System | TBD | Remove "Zip" from the REF02 of the REF~7G segment (Rejection Reason) | Re-evaluate for validity (497, 498, 574, 596)
3_498 | Y | 814_PC | Next Release | System | TBD | Clean up of the 814_PC | Re-evaluate for validity (497, 498, 574, 596)
3-503 | Y | 810_02 | Future | System | TBD | allow TDSP to send single corrected invoice for IDR meters | Valid per TX SET review 3/24/04
3_517 | Y | 814_28 | Future | System | TBD | Adding to reasons for "Complete Unexecutable" | Valid per TX SET review 3/24/04
3_527 | Y | 650_02 | Future | System | TBD | Adding to reasons for "Complete Unexecutable" | Valid per TX SET review 3/24/04
3_532 | Y | 814_04 and 05 | Future | System | TBD | 814_04 and 05 needs a Meter Ownership Type code to eliminate gap when customer chooses competitive meter to notify new REP when switching | Valid per TX SET review 3/24/04
3_569 | Y | Entire 814 series 01-29, PC and PD | Future | System | TBD | Provide gray box clarification to the LIN segment to indicate that the Texas Market supports only 1 LIN loop per SDI Transaction | Valid per TX SET review 3/24/04
3_571 | Y | 814_09 and 814_13 | Future | Gray Box/Examples | TBD | Move segment gray box verbiage for A78 being used only by ERCOT and TDSP to gray box on actual code | Valid per TX SET review 3/24/04
3_572 | Y | 814_13 and 814_02 | Future | Gray Box/Examples | TBD | Add short title "Earliest Available Switch Date" to the EAS Reject code (REF*7G) | Re-evaluate
3_576 | Y | 814_20 | Future | System | TBD | Meter Exchange/Profile Information | Re-evaluate
3_578 | Y | 814_20 | Future | System | TBD | Added a new change code to indicate the annual Load Profile changes | Valid per TX SET review 3/24/04
3_582 | Y | 814_08 | Future | System | TBD | Add B30 - MIMO change | Valid per TX SET review 3/24/04
3_590 | Y | 814_21 | Future | System | TBD | Add code for ERCOT generated reject | Valid per TX SET review 3/24/04
4-596 | Y | 814_PC | Future | TBD | TBD | Clarify timing to use transaction | Re-evaluate for validity (497, 498, 574, 596)
4-597 | Y | 814_13 | Future | System | TBD | MIMO clean up | Valid per TX SET review 3/24/04
4-601 | Y | 814_13 | Future | System | TBD | Add new reject code "ICD" MIMO | Valid per TX SET review 3/24/04
2004-604 | Y | 814_09, 814_13, 814_25 | Future | System | TBD | The gray boxes in CC2003-400 were written such that the ‘OA’ code will be sent on every response from the TDSP, reject or accept. This needs to be changed to only send the ‘OA’ code on rejects to be consistent with CC2003-401, which is the same change for the 814_11. | Recently approved by Texas SET
2004-607 | Y | 820_03 | Future | System | TBD | changes to the 820_03 transaction are needed to add data elements/segments to accommodate payment adjustments to the CR when payments are adjusted on the customer’s Muni-Co-op account due to being applied to an incorrect account, for the wrong amount, or in the case of a returned check | Recently approved by Texas SET
2004-615 | Y | 650_01 | Future | System | TBD | Need to expand the message text in the MTX segment from 80 characters to 255 characters | Recently approved by Texas SET
2004-616 | Y | 814_11 | Future | System | TBD | Add ‘SBD’ Reject code to the 814_11 | Recently approved by Texas SET
2004-624 | Y | 650_02 | Future | System | TBD | Remove Businesss Process Overviews from the Implementation Guides and incorporate that logic into the graybox or data element itself of the Implementation guideline | Approved on 8/18/04 by Texas SET
2004-627 | Y | 820_02 | Future | Gray box/Examples | TBD | Remove Businesss Process Overviews from the Implementation Guides and incorporate that logic into the graybox or data element itself of the Implementation guideline | Approved on 8/18/04 by Texas SET
2004-629 | Y | 650_01 | Future | System | TBD | Update the 650_01 YNQ (Premium Disconnect Location) YNQ09 PDL graybox and add 2 additional codes in the YNQ09 to give the TDSO clear instructions as to what charges the CR has agreed to pay for Reconnect following Disconnect for non-payment | Approved on 8/18/04 by Texas SET
2004-631 | Y | 814_04 | Future | System | TBD | Remove the A75 reject code on the 814_04 as it is no longer needed | Approved on 8/18/04 by Texas SET
2004-632 | Y | 814_24 | Future | System | TBD | Add a new code to the REF~1P status reason segment in the 814_24 that will be used by CRs when submitting a second MVO that will communicate to the TDSP second request for MVO and disconnect service. | Approved on 8/18/04 by Texas SET
2004-633 | Y | 867_03 | Future | Gray box/Examples | TBD | Update graybox in the PTD-PL, PTD-BO, and PTD-PM loops to include multiple meter exchange examples in one service period. | Approved on 8/18/04 by Texas SET
2004_635 | Y | 810_02 | Future | System | TBD | Add (6) New SAC04 codes to the 810 Invoice transaction for new tariffs- transition charges and/or charge off allowances to be appropriately identified with the invoice transaction. | Approved on 8/18/04 by Texas SET
2004-639 | N | 824 | Future | System | TBD | Add two codes to the existing approved reject codes for 824. | Approved 9/22/04 with modifications by Texas SET
2004-642 | N | 814_08, 814_09 | Future | System | TBD | Update the 814_08/814_09 IG transaction flow to indicate the 814_08 can be used to cancel a drop to AREP | Approved 10/12/04 by TX SET
2004-643 | N | 820_02 | Future | Gray Box/Examples | TBD | Update the 820_02 IG to provide clarification on how decimals are used in the BPR02 & RMR04. | Approved 10/12/04 by TX SET
2004-644 | N | 810_02 | Future | System | TBD | Update SAC09 code list for the Billing Determinants | Approved 10/12/04 by TX SET

## Trx Description Card
TEXAS SET VERSION 2.0 |  |  | 650* | Maintenance Service Order - Work Orders, Meter Config. Details, Outage Notification
814 - Request, Response, Maintenance for Enrollments, Drops, Switches, Maintenance & Request Consumption
Trx | Definition | Flow | Trx | Definition | Flow
814_PC | Maintain Customer Information Request | CR=>TDSP | 650_01 | Basic Service Order | CR=>TDSP
814_PD | Maintain Customer Information Response | TDSP=>CR
814_01 | Enrollment Request | CR=>ERCOT | 650_02 | Service Order Complete Response | TDSP=>CR
814_02 | Enrollment Reject Response | ERCOT=>CR | 650_04 | Suspension of Delivery Svc Notification or Cancellation | TDSP=>CR
814_03 | Switch CR Notification Request | ERCOT=>TDSP
814_04 | Switch CR Notification Response | TDSP=>ERCOT | 650_05 | Suspension of Delivery Service Reject Response | CR=>TDSP
814_05 | Premise Info & Enrollment Response | ERCOT=>CR
814_06 | Drop Due to Switch Request | ERCOT=>CR | *The 650_03 functionality was distributed amongst the other 650 transactions.
814_07 | Drop Due to Switch Response | CR=>ERCOT
814_08 | Cancel Switch Request | CR=>ERCOT | 810 - Statement, Settlement, Wire Charge Invoices
|  | ERCOT=>CR | 810_02 | Wires Charge/Service Order Charge Invoice | TDSP=>CR
ERCOT=>TDSP
814_09 | Cancel Switch Response | ERCOT=>CR | 810_03 | Muni/Coop Invoice | CR=>MCTDSP
CR=>ERCOT
|  | TDSP=>ERCOT | 820 - Payment and Advice through Bank
814_10 | Drop to AREP Request | CR=>ERCOT | 820_02 | CR Remittance Advice | CR=>TDSP
814_11 | Drop to AREP Response | ERCOT=>CR
814_12 | Move-In/Move-Out Dte Chg Request | CR=>ERCOT | 820_03 | Muni/Coop Remittance Advice | MC TDSP=>CR
ERCOT=>CR
|  | ERCOT=>TDSP | 824 - Reject Response to 810 or 867 Data - O
814_13 | Move-In/Move-Out Dte Chg Response | ERCOT=>CR | 824 | Application Advice | CR=>TDSP
|  | CR=>ERCOT |  |  | CR=>ERCOT
|  | TDSP=>ERCOT |  |  | ERCOT=>TDSP
814_14 | AREP Enrollment Request | ERCOT=>AREP | 867-Interval, Non Interval, Reads & Consumption Data Historical and Monthly Activity
814_15 | AREP Enrollment Response | AREP=> ERCOT
814_16 | Move-In Request | CR=>ERCOT | 867_02 | Historical Usage | TDSP=>ERCOT
814_17 | Move-In Reject Response | ERCOT=>CR |  |  | ERCOT=>CR
814_18 | Establish/Delete CSA CR Request | CR=>ERCOT | 867_03 | Monthly Usage | TDSP=>ERCOT
|  | ERCOT=>TDSP |  |  | ERCOT=>CR
814_19 | Establish/Delete CSA CR Response | ERCOT=>CR | 867_04 | Initial Meter Read Notification | TDSP=>ERCOT
|  | TDSP=>ERCOT |  |  | ERCOT=>CR
814_20 | Create/Maintain/Retire ESI ID Request | TDSP=>ERCOT
ERCOT=>CR
814_21 | Create/Maintain/Retire ESI ID Response | ERCOT=>TDSP
CR=>ERCOT
814_22 | CSA CR Move-In Request | ERCOT=>CR
814_23 | CSA CR Move-In Response | CR=>ERCOT
814_24 | Move-Out Request | CR=>ERCOT
ERCOT=>TDSP
814_25 | Move-Out Response | ERCOT=>CR
TDSP=>ERCOT
814_26 | Ad-Hoc Historical Usage Request | CR=>ERCOT
ERCOT=>TDSP
814_27 | Ad-Hoc Historical Usage Response | ERCOT=>CR
TDSP=>ERCOT
814_28 | Completed Unexecutable or Permit Required | TDSP=>ERCOT
ERCOT=>CR
814_29 | Response Completed Unexecutable or Permit Required - O | ERCOT=>TDSP
CR=>ERCOT