## Sheet1
Change Controls
# | Approved | Transactions | Version | Scope | Size/Swag | Description | Notes
pending |  | 814_20 |  | ERCOT Only | 1 | add recodes instead of 813s
pending |  | 814_20 |  | ERCOT Only | 1 | add recodes instead of 813s
pending |  | 814_20 |  | ERCOT Only | 1 | add recodes instead of 813s
pending |  | 814_20 |  | ERCOT Only | 1 | eliminate a code out of 813
pending |  | 810 |  | System | 2 | Potential 810 - 867 billing determinants changes
pending |  | 810_02 |  | System | 3 | allow TDSP to send single corrected invoice for IDR meters
3-503 | Y | 810_02 | Future | System | 3 | allow TDSP to send single corrected invoice for non-IDR meters
2-316 | Y | 814_22 | Future | System | 2 | Add the N1~loop to the 814_22
2-412 | Y | 814_09 | 1.6 | Gray Box/Examples | 1 | Cleanup of Example box | verify with Bernie
2-413 | Y | 814_11 | 1.6 | Gray Box/Examples | 1 | Add example | potential conflict with 27084
2-414 | Y | 814_13 | Future | Gray Box/Examples | 1 | Add example
2-415 | Y | 814_25 | Future | Gray Box/Examples | 1 | Add example
2-447 | Y | 814_10 | Future | System | 1 | Remove segments from N1~8R
2-449 | Y | 814_14 | Future | System | 1 | Remove N2 segment from the N1~8R Loop and update gray boxes
2-466 | Y | 650_04 | Future | System | 2 | Add code to 650_04 provide means to alert CR that service has been permanently suspended for ESI ID and numerous gray box changes
2-468 | Y | 810_03 | Future | System | 1 | Multiple 810_03 changes - code gray box
3-471 | Y | 650_04 | Future | System | 1 | remove must use from the YNQ04 of the NQ~5U segment
3-490 | Y | 814_14, 814_22 | Future | Gray Box/Examples | 1 | remove QTR from valid values of Meter Type from the gray box
3_493 | Y | 814_27 | Future | System | 1 | Make the N1~8S OPTIONAL on the 814_27 to be consistent with the 814_26 N1~8S loop
3_496 | Y | 650_02 | Future | System | 2 | Provide additional detail on when 650_02 should be generated and how the process should work for disconnect and reconnect for non-pay | Potential re-evaluation with the Blue Team
3_497 | Y | 814_PD | Next Release | System | 1 | Remove "Zip" from the REF02 of the REF~7G segment (Rejection Reason) | Re-evaluate for validity
3_498 | Y | 814_PC | Next Release | System | 1 | Clean up of the 814_PC | Re-evaluate for validity
3_517 | Y | 814_28 | Future | System | 1 | Adding to reasons for "Complete Unexecutable" | potential issue with White Team safety-net document
3_527 | Y | 650_02 | Future | System | 1 | Adding to reasons for "Complete Unexecutable"
3_530 | Y | 650_01 | Future | Gray Box/Examples | 1 | Cleanup of Gray box and Example
3_532 | Y | 814_04 and 05 | Future | System | 2 | 814_04 and 05 needs a Meter Ownership Type code to eliminate gap when customer chooses competitive meter to notify new REP when switching
3_538 | Y | 867_03 | Future | System | 2 | Changes to examples in the Implementation Guide
3_539 | Y | 814_29 | Future | Gray Box/Examples | 1 | Add the BGN07 code to the gray box example in BGN segment
3_569 | Y | Entire 814 series 01-29, PC and PD | Future | Gray Box/Examples | 1 | Provide gray box clarification to the LIN segment to indicate that the Texas Market supports only 1 LIN loop per SDI Transaction
3_571 | Y | 814_09 and 814_13 | Future | Gray Box/Examples | 1 | Move segment gray box verbiage for A78 being used only by ERCOT and TDSP to gray box on actual code
3_572 | Y | 814_13 and 814_02 | Future | Gray Box/Examples | 1 | Add short title "Earliest Available Switch Date" to the EAS Reject code (REF*7G)
3_573 | Y | 814_08 and 814_09 | Future | Gray Box/Examples | 1 | Remove references to the word "reinstate" in the 814_08 and 814_09 transactions
3_574 | Y | 814 PC | Future | Gray Box/Examples | 1 | Remove existing transaction notes form the 814 PC guide
3_576 | Y | 814_20 | Future | System | 1 | Meter Exchange/Profile Information
3_577 | Y | 814_17 | Future | Gray Box/Examples | 1 | Example 1 and 3 of the 814_17 guide need to have the REF*7G segment revised to match the new reject code detail put in place by the V2.0 change controls
3_578 | Y | 814_20 | Future | System | 2 | Added a new change code to indicate the annual Load Profile changes
3_580 | N | 820_03 | Future | System | 2 | Change for adding payment adjustment
3_581 | N | 867_04 | Future | Gray Box/Examples | 1 | Example change
3_582 | N | 814_08 | Future | System | 1 | add B30 - MIMO change
3_583 | N | 814_02, 11, 17, 19, 21, 25, 27 | Future | Gray Box/Examples | 1 | if same BGN02 comes from two different CRs one will be rejected
3_584 | N | 810_02 | Future | System | 3 | Add code to the BIG08 for invoice type of REISSUE or restatement of a cancelled invoice - add gray box information to the REF~O1

## Sheet2
|  |  |  | 814 | [29 empty] | 650
Transaction | 810 | 867 | 820 | PC | PD | 02 | 02 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 4
Gray Box |  |  |  | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 3 | 1 | 4 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 1 | 2 | 1 |  |  | 51
ERCOT only | [5 empty] | 21: 4 | 4
Small | 1 | 1 |  | 1 | 1 | [31 empty] | 10 | bar: 08; 10; 14; 20; 27 to 28
Medium | 1 | 1 | 1 | [33 empty] | 9 | bar: 04 to 05; 20; 22; 650 2 to 650 4
Large | 3 | [35 empty] | 3
Total | 5 | 2 | 1 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 3 | 1 | 4 | 3 | 1 | 1 | 3 | 1 | 2 | 3 | 6 | 3 | 1 | 1 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 1 | 77