## TX SET Information
TX SET |  |  |  |  | DATE | 2004-01-20 | 2004-01-21 | 2004-02-17 | 2004-02-18 | 2004-03-23 | 2004-03-24 | 2004-04-19 | 2004-04-20 | 2004-05-18 | 2004-05-19 | 2004-06-22 | 2004-06-23 | 2004-07-20 | 2004-07-21 | 2004-08-17 | 2004-08-18 | 2004-09-21 | 2004-09-22 | 2004-10-19 | 2004-10-20 | 2004-11-16 | 2004-11-17 | 2004-12-07 | 2004-12-08
[5 empty] | CITY | 2004-01-20: Austin; 2004-02-17: Austin; 2004-03-23: Austin; 2004-04-19: Corpus Christi; 2004-05-18: Dallas; 2004-06-22: Austin; 2004-07-20: Austin; 2004-08-17: Austin; 2004-09-21: Tulsa; 2004-10-19: Austin; 2004-11-16: Austin; 2004-12-07: Austin
OFFICER | NAME | COMPANY | EMAIL@ADDRESS | PHONE | MEETING VENUE | Comfort Suites | Comfort Suites | Comfort Suites | Comfort Suites | Comfort Suites | E M 206 A | AEP | AEP | TXU | TXU | E M 206 A | E M 206 A | E M 168 | E M 168 | AmeriSuites | AmeriSuites | AEP | AEP | AmeriSuites | E M 206 A | AmeriSuites | E M 206 A | E M 206 A | E M 206 A
| Baum, Thomas | ERCOT | tbaum@ercot.com | 512-248-6550 | bar: 2004-06-22 to 2004-06-23
| Bear, Jason | TCE | bar: 2004-01-20 to 2004-04-20
| Bell, William | CenterPoint Energy | william.bell@centerpointenergy.com | 281-610-0309 | bar: 2004-04-19
| Bergman, Karen | ERCOT | kbergman@ercot.com | 512-248-3141 | bar: 2004-04-19; 2004-06-22 to 2004-06-23
| Bevill, Rob | Green Mountain | rob.bevill@greenmountain.com | 512-691-6134 | bar: 2004-01-20 to 2004-03-24; 2004-05-18 to 2004-06-23
| Blumenthal, Ellen | GDS Associates | ellen.blumenthal@gdsassociates.com | 361-949-1578 | bar: 2004-04-19
| Bratton, Charlie | TXU Energy | cbratto1@txu.com | 214-875-3703 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-05-19
| Callender, Wayne | City of Public Service SA | wdcallender@cps-satx.com | 210-353-2779 | bar: 2004-04-19
| Campirano, Eduardo | BPUB | ecampirano@brownsville-pu.com | 956-983-6279 | bar: 2004-04-19
| Collard, Zach | CenterPoint Energy | zach.collard@centerpointenergy.com | 281-433-7050 | bar: 2004-04-19
| Conner, Mike | BTU | mconner@btutilites.com | 979-821-5830 | bar: 2004-04-19
| Dauterive, Eddie | Envision Utility Software | eddied@envworld.com | 512-266-7787 | bar: 2004-04-19
| Davis, Mike | ERCOT | mdavis@ercot.com | 512-248-6763 | bar: 2004-02-17; 2004-03-23; 2004-04-19
| Dawson, Bernie | Envision Utility Software | bernardd@envworld.com | 512-266-7787 | bar: 2004-01-20; 2004-02-17 to 2004-06-23
| Fisher, Sarah | NEC | sfisher@nueceselectric.org | 361-387-2581 | bar: 2004-04-19
| Flores, Eloise | Nueces Electric Coop | eflores@nueceselectric.org | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-05-18; 2004-06-22
| Flowers, BJ | TXU Energy | bj.flowers@txu.com | 214-812-4330 | bar: 2004-01-20; 2004-06-22
| Garcia, Jennifer | ERCOT | jgarcia@ercot.com | 512-413-0864 | bar: 2004-04-19
| Godoy, Ernie | SPEC | egodoy@sanpatricioelectric.org | 361-364-2220 | bar: 2004-04-19; 2004-05-18
| Hensley, Bryan | TCE | bryan.hensley@mytce.com | 214-509-2195 | bar: 2004-01-20 to 2004-04-20
| Hermes, Connie | STEC | connie@stec.org | 361-485-6173 | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-04-20
| Hernandez, Ron | ERCOT | rhernandez@ercot.com | 512-248-6523 | bar: 2004-04-19
| Jackson, Tom | Austin Energy | Tom.Jackson@austinenergy.com | 512-322-6324 | bar: 2004-03-23 to 2004-03-24
| Fredericks, Jennifer | ERCOT | jfredericks@ercot.com | 512-248-6733 | bar: 2004-01-20 to 2004-03-23; 2004-06-22
| Kalips, Leo | NISC | leo.kalips@nisc.cc | bar: 2004-04-19
| Kernick, Kristina | Envision Utility Software | kristinaak@envworld.com | 512-266-7787 | bar: 2004-04-19
| Leith, Brent | First Choice | bleith@firstchoicepower.com | 701-306-6810 | bar: 2004-04-19; 2004-05-18 to 2004-06-23
| Lowder, Dave | SPEC | dlowder@sanpatricioelectric.org | 361-364-2220 | bar: 2004-04-19
| McKain, Shelley | ADS Mutual Energy | smckain@alldata.net | 918-493-9515 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24
| Moast, Pat | ERCOT | pmoast@ercot.com | 512-261-9925 | bar: 2004-04-19
| Moore, Chuck | Direct Energy | chuck.moore@ngwi.com | bar: 2004-01-20; 2004-03-23; 2004-04-19 to 2004-05-19
| Morales, Rita | Direct Energy | ritamorales@ngwi.com | 972-480-8224 | bar: 2004-01-20; 2004-03-23 to 2004-03-24; 2004-04-20 to 2004-06-23
| Ohrt, Wendy | STEC | wendyjo@stec.org | 361-485-6172 | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-04-20
2004 Chair | Patrick, Kyle | Reliant Energy | kpatrick@reliant.com | 713-497-3396 | bar: 2004-01-20 to 2004-06-23
| Reed, Cary | AEP | careed@aep.com | 918-260-0093 | bar: 2004-01-20 to 2004-02-18; 2004-04-19 to 2004-06-23
| Rehfeldt, Diana | TNMP/First Choice Power | drehfeldt@tnpe.com | 817-377-5580 | bar: 2004-01-20 to 2004-01-21
2004 VC | Reily, Bill | Oncor | breily1@txu.com | 214-875-2520 | bar: 2004-01-20 to 2004-03-23; 2004-04-19 to 2004-04-20; 2004-05-19 to 2004-06-23
| Riordon, Ken | LCRA | ken.riordon@lcra.org | 512-473-3215 | bar: 2004-04-19; 2004-05-18
| Robertson, Johnny | TXU | jrobert1@txu.com | 214-875-1565 | bar: 2004-01-20; 2004-03-23 to 2004-06-23
| Rodriguez, Robert | Constellation New Energy | Robert.Rodriguez@constellation.com | 281-793-6339 | bar: 2004-01-20; 2004-03-23; 2004-05-18 to 2004-06-22
| Saenez, Fernando | BPUB | fsaenez@brownsville-pu.com | 956-983-6266 | bar: 2004-04-19
2004 VC | Scott, Kathy | CenterPoint Energy | Kathy.d.scott@centerpointenergy.com | 713-945-6630 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24; 2004-05-18 to 2004-06-23
| Steen, Lora | Entergy | lsteen@entergy.com | 936-525-2034 | bar: 2004-01-20 to 2004-01-21; 2004-05-19
| Teel, Jennifer | EC POWER | jennifer.teel@ec-power.com | 713-403-8731 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-04-20
| Thomas, Jeff | TCE | jeff.thomas@mytce.com | 214-509-2122 | bar: 2004-04-19; 2004-05-18 to 2004-06-22
| Duke, Warren | Pease Software | bar: 2004-06-22
| Wilburn, Suzette M. | ERCOT | swilburn@ercot.com | 512-248-3991 | bar: 2004-01-20 to 2004-04-20; 2004-05-19
| Wilson, Frank | Nueces Electric Coop | fwilson@nueceselectric.org | 361-387-2581 | bar: 2004-02-17; 2004-04-19
| Wingerd, Glen | ERCOT | gwingerd@ercot.com | bar: 2004-04-19

## 2004 Open Action Items
Meeting | Segment | Sponsor | CC | Issue | Action Item | Resolution | Status | Date
April |  |  |  | DNP Taskforce Recommendations | DNP Taskforce to hand off deliverables | (6/23/04) Yet to be delivered to TX SET | Open
April |  | RRI & TXU |  | Change Control for Billing Determinants | Write Change Control | (6/23/04) JR drafted a version of this CC, TX SET reviewed it at the June meeting. | Open
April | MOU/EC | (Eloise Flores,Nueces Electric Coop) |  | Add a customer(member) tracking number from move-in to Move-out. Customer name tied to ESID (believe this is already a noted issue); membership issues |  | (6/23/04) Think about what needs to be done and what is the best solution/resolution for this problem: § Conceptual Recommendation: Add REF Segment REF~01=1W for MOU/EC only to populate with MOU/EC Membership Number. Question has does this information stay updated and provided to CR’s for switch/move-in, and/or move-out? | Open
April | MOU/EC | TX SET |  | Change 814_28 to allow move-in to be pended because customer is not a member of the co-op. |  | (6/23/04) Redlined document posted to May meeting documents | Open
April | MOU/EC | Austin En |  | Change 820_03 to allow for a code to reference a credit pmt. |  | (6/23/04) No progress yet | Open
April | MOU/EC | Nueces |  | Change 820-payment adjustments 6000 record to allow credits and debits in the total payment field for the batch total. |  | (6/23/04) No progress yet | Open
April | MOU/EC | Austin En |  | Change 810_03 to include information on deferred payment agreements that CR has set up with customer. |  | (6/23/04) No progress yet | Open
April | MOU/EC | Austin En |  | Change 810_03 to separate cancel examples into a 3-step process: (1) original (2) cancel (3) re-bill. Similar to changes that were made to 810_02. |  | (6/23/04) No progress yet | Open
April | MOU/EC | Austin En |  | Change 810_03 to include reasons for cancel (BIG segment): usage or monetary correction. Similar to changes that were made to 810_02. |  | (6/23/04) No progress yet | Open
April | MOU/EC | CPS |  | Why can't a 814_01 originate from the MCTDSP since customer remains with MCTDSP? |  | (6/23/04) No progress yet | Open
April | MOU/EC | LCRA |  | With exception of PC & PD, all other 814's go through ERCOT. Since MOU/EC don't unbundle, why do 814's still need to go thru ERCOT? Same question with 867's? Since CR and TDSP functions handled at same office? |  | (6/23/04) No progress yet | Open
April | MOU/EC |  |  | If customer calls TDSP first, can there be an enrollment from the TDSP. Can the TDSP go ahead and set up customer? Since other city services need to be set up? -Responses - lots of discussion about scheduling power, how can you without CR, etc. |  | (6/23/04) No progress yet | Open
April | MOU/EC |  |  | Change 814_18 to handle co-op membership requirements. Landlord billing information. |  | (6/23/04) No progress yet | Open
April | MOU/EC |  |  | Make 814_PC bi-directional. |  | (6/23/04) No progress yet | Open
April | MOU/EC |  |  | In MOU/EC T&C's - city services also paid 1st, or just electricity? -ACTION ITEM - read/interpret T&C's |  | (6/23/04) No progress yet | Open
April | MOU/EC |  |  | More that move-in, would like to see bi-directional move-out. For forwarding of final bill, capital credits check, etc. |  | (6/23/04) No progress yet | Open
May |  | ERCOT |  | ERCOT service orders completed without transactions | ERCOT to draft proposal to TX SET for reporting back to RMS | (6/23/04) ERCOT to bring back information to next TX SET meeting regarding instances where complete w/out trx occurs. | Open
May |  | TX SET |  | Flag on 814_24 for instances where the first is '09'd and a second is sent | Suzette Wilburn, Kyle Patrick, Charlie Bratton, Kathy Scott to review 824 Workshop documentation and begin drafting new codes | (6/23/04) Team has not met. | Open
May |  |  |  | 824 new codes | Suzette Wilburn, Kyle Patrick, Charlie Bratton, Kathy Scott to review 824 Workshop documentation and begin drafting new codes | (6/23/04) Team has not met. | Open
May |  |  |  | TDSPs to document estimation processes |  | (6/23/04) TDSPs did so at June meeting. TX SET chair to either report or request time to report to RMS at July meeting. | Open
May |  |  |  | 864 strawdog example | Johnny Robertson and Cary Reed to draft example | (6/23/04) In progress, expect report in August or September. | Open
May |  |  |  | Customer Protection compliance | Bill Reily and Charlie Bratton to organize TDSP/CR reviews of the rule | (6/23/04) Bill and Charlie to bring back report to a next TX SET meeting. | Open
May |  |  |  | Mass Transition Phase 1 |  | (6/23/04) To be addressed along with MT Phase II | Open
May |  |  |  | 814_21 passthrough to TDSP | Kathy Scott to create draft change control for updating the 814_20 business process | (6/23/04) Kathy submitted the CC at June TX SET | Open
May |  |  |  | Change Control 503 | Bill Reily to draft change control | (6/23/04) Bill will draft CC prior to CC deadline for next release. | Open
May |  |  |  | 650_01 1 to 1 relationship | TDSPs to verify that they are responding the 650_01s on a one to one relationship and bring back at June Meeting | (6/23/04) Cary Reed to refer this to Blake Gross and Shannon Bowling (DNP/REC TF). Also change control 2003-496 should clear this issue up. | Open
May |  |  |  | 867_02 large file of data | Bill Reily to bring recommendation to June Meeting | (6/23/04) Bill will bring back suggestion at a later meeting. | Open
May |  |  |  | 814_28 redline document MOU/EC | TX SET to document the different scenarios that would be affected by membership codes suggested for the 814_28 | (6/23/04) The TDSPs will get together along with MOU/EC to make a list of the Reasons for Pending a Move-In or Move-Out to cover the majority or the higher percentage of reasons for pending a request. Cary Reed will send an open invitation to Eloise and any other MOU/EC to a meeting scheduled on July 15, 2004 to discuss this action item. | Open
June |  |  |  | 867_03 BPO | Suzette Wilburn and Kathy Scott to draft document | (6/23/04) Due to length of this document and the number of changes included in the redline version, a review of this document will be deferred to the next Texas SET meeting for discussions. The updated document will be included in the minutes for SET Membership to review at a later time. | Open
June |  |  |  | Action Items List |  | (6/23/04) Leadership will provide a printed copy of the most recent list of Outstanding Action items at each TX SET meeting. | Open
June | [6 empty] | Open
June | [6 empty] | Open
June | [6 empty] | Open
June | [6 empty] | Open
June | [6 empty] | Open
June | [6 empty] | Open
June | [6 empty] | Open
June | [6 empty] | Open
June | [6 empty] | Open
June | [6 empty] | Open
June | [6 empty] | Open

## 2004 Closed Action Items
Meeting | Segment | Sponsor | CC | Issue | Action Item | Resolution | Status | Date
January |  | RRI |  | Would like to investigate possibility of adding a flag to indicate whether the meter is temporary or permanent | CRs will meet to re-frame the question and provide the TDSPs with exactly what they'd like to see |  | Closed | 2004-02-17
January |  | RRI |  | Would like to investigate the possibility of adding a code on the 814_16 and 650 series that would provide gate access codes | Group agreed that more time was necessary to determine if there was a need for this type of information from all CRs |  | Closed | 2004-02-17
January |  | ERCOT |  | Review of the draft 867_01 IG for opting in entities | TDSPs to review guide with SMEs at their companies to verify guide contains all necessary segments and data elements | TX SET believes that the cost for re implementing the 867_01 is much larger than the cost for using a flat file on a on going basis. | Closed
January |  | ONCOR |  | Outdated scheduled transactions in ERCOTs system that cannot be completed | ERCOT to investigate if a common theme exists for the manual processes used to 'fix' these scheduled transactions to get a better idea of where TX SET needs to focus their attention | Comment 5/19/04: No true common theme, but the problem centers around previous versions (1.4, 1.5) trxs cannot be completed with future releases (1.6, 2.0). Kyle Patrick will refer to MCT for future discussion. | Open
January |  | ERCOT | Y | Clarification needed on how maintenance to unmetered service devices are communicated in the 814_20 | 814_20 guide needs to be updated if the 814_20 is not used when maintaining unmetered service devices. TX SET to investigate the possibility of adding this functionality to the 814_20 | TDSPs waiting for response on whether they send 814_20s. | Closed
January |  | CNP | Y |  | 867_03 How to Use Section meeting needs to be arranged to convert the How to Use to a BPO and make the appropriate updates in the new BPO document. | Comment April TX SET: This will be an agenda item for the May meeting of TX SET in Dallas. Comment May TX SET: This will be an agenda item for the June meeting of TX SET. | Open
January |  | TX SET |  |  | TX SET Leads need to develop a process that would remind members of outstanding and/or open action items prior to monthly meetings (1 or 2-weeks before if possible) | Leadership will remind team members of action items when meeting notice and agenda are sent. | Closed
|  | ERCOT |  | In the case of a MOV to CSA, when an 814_08 is submitted by the Cur CR, is the TDSP expecting the Cur CR or CSA CR Duns in the N1~SJ? I would believe it would be the CSA CRs Duns, because the TDSP would have received an 814_03 with the CSA CRs information, not and 814_24 with the Cur CR information. |  | ERCOT will be putting the CSA CR in the 814_08 | Closed
February |  | TX SET |  | Review BPOs for 2.0 | Cary Reed, Kyle Patrick, Suzette Wilburn, JR, and Bill Reily will review. | Comment 5/19/04: Team to meet 5/25/04 in Austin, TX venue to be determined. | Open
February |  | ERCOT | Y | · In the event that there are multiple meters exchanged on a premise, would the profile code be listed in both NM1 loops? We have seen some instances where the profile code update (REF~LO) is included in the second NM1 loop and wanted to verify that profile codes should be accepted regardless of which NM1 loop they are communicated in o If the profile code is an attribute of the ESI-ID and not the meter, why is it in the NM1 loop? Shouldn’t it be in the LIN loop? · TX SET agrees that the profile code is at a premise level and that the profile code needs to be updated regardless of which NM1 loop it is sent in. Group also agreed that this type of update needs to be in the LIN loop, not the NM1 loop, as the change is at a premise, not meter, level | S. Wilburn to write a change control to move the REF~LO segment to the LIN loop | Comment 5/19/04: Change control has been written but not submitted. | Open
February |  |  |  | · The N303 in the N3 segment of the 814_20 is alphanumeric. (AN1/55). Would like to find out from the group if they would like to see ERCOT rejecting transactions that send special characters in this field. o Encountered issues with double quotes in this field. Only about 40 ESI-Id · If ERCOT decides to cross validate this field and reject transactions that contain special characters, they need to look at other fields that they currently do not cross validate on. For instance, the PER segment in the 814_03 is not cross validated to ensure the phone number is sent without dashes. | ERCOT will communicate to the team what decision they decide to go with regarding the cross validation | ERCOT put validation in that reject double quotes in the address field. | Closed
February |  |  |  | · Following up on the issue regarding 814_20 retires being received on de-energized ESI-Ids with a scheduled MVI. We have a proposed short term solution o If the SMRD of the MVI is greater than the date on the retire, we cancel the MVI o If the SMRD of the MVI is less than the retire, we reject the retire and allow the MVI to effectuate | ERCOT will implement a fix in a near release to reject any 814_20 retires received on a de-energized premise with a scheduled service order. TDSP will open a fastrak issue to get open service order resolved. Release date is still to be determined. ERCOT Client Services will communicate when this change will be implemented | ERCOT will follow the short term solution in the recommendation | Closed
February |  | Nueces |  |  | E. Flores to gather all issues addressed to date regarding the Muni/Coop market to send out to the market | This will be an ongoing list | Closed
February |  | TX SET Officers |  |  | TX SET officers to make phone calls to the muni/coops about the meeting | MOU/EC meeting was held on 4/19/04 in Corpus Christi | Closed
February |  | ERCOT |  |  | ERCOT Client Services to pull together email to be sent out inviting all Muni/Coops to attend the day meeting on April 20th | MOU/EC meeting was held on 4/19/04 in Corpus Christi | Closed
February |  | TCE/STEC | Y | We need to talk about the 650_04 disconnect/reconnect process on the muni/coop side. There was some discussion at Texas Test Plan script sub team on this regarding the current test script calling for a 650_04 cancel of the disconnect request to indicate a reconnect. | TCE to work with STEC to write change control for adding a new code to the 650_04 to communicate this information | Comment 5/19/04: Jeff Thomas to update SET on this. | Open
February |  | ERCOT | Y | Should a REF~IX always exist when a REF~4P is present in the 814-04? · For example, if you have a REF~MT~COMBO and two REF~4Ps should you also have two REF~IXs? · If not, what circumstances exist when you wouldn't, and what type of modifications could be made to the gray box to clarify this? | o (Action Item) S.Wilburn to write a change control to update the examples in the 814_04 | Comment 5/19/04: Change control was written, and withdrawn. The text will be left in the example. TX SET again stresses that MPs should code to the guide section not the examples section. | Closed
February |  | TX SET |  | "Future Implementation CCs aka Unassigned CCs" Review. (SEE WORKBOOK PAGE UNASSIGNED CHANGE CONTROLS) | TX SET members to review all "Unassigned" Change Controls at future meetings. | TX SET will begin to work on the Future Version of the I.Gs using the Unassigned change controls in this next release. | Closed
February |  | TX SET |  | Revised Working Group Procedures | TX SET members should review the Working Group Procedures Redline | Comment 5/19/04: TX SET reviewed the WG procedures they will be posted for review. WG procedures to be an agenda item at the June meeting. (6/23/04) Approved with changes on June 22, 2004- | Open
April |  | TX SET Chair |  | ERCOT should not be completing Safety Net MVIs without electronic trx. |  | TX SET presented this back to RMS in its RMS report at the May '04 Meeting. It was TX SETs opinion that all MPs and ERCOT who participate in the Safety Net process should follow the approved guidelines. | Closed
April |  |  |  | REF~1P removal issue | CRs will discuss and frame issue prior to this becoming a TX SET agenda item. | TX SET discussed at the April meeting, the REF~1P change control was withdrawn. | Closed
April |  | ERCOT |  | 814_07 Rejects | ERCOT to develop a proposal for handling 814_07 rejects. | (6/24/04) Suzette Wilburn brought recommendations to TX SET on this. | Closed

## Project Plan
Project Plan for Next Release
Activity | Time Frame | Start Date | End Date | Membership
Identify all changes required for Future Version. Submit all change controls to be applied to version Future Version. Discussion and approval/denial of all change control design documents. | As determined
Update current version 1.5 to a clean baseline with all change controls applied | 3 weeks
Review all change controls and prepare any SCRs and PRRs as needed | 1 week
Build SEF and Word docs. With all Future Version change controls applied. | 3 weeks
Publish Future Version first draft redline | 1 day
Tx SET committee will review and compare Visio's, change controls and implementation guides. All market participants will start design and technical analysis. | 6 weeks
Resolve issues | 1 week
Apply resolved issues and any change controls approved since the redline publication | 1 week
Publish final Future Version redline | 1 day
TxSET committee will review and compare Visio's, change controls and implementation guides. Any identified gaps or errors will be sent to TxSET | 2 weeks
Resolve issues | 1 week
Apply resolved issues | 1 week
Update Transaction Scenario Inventory. Clean up any identified errors. | 2 weeks
Publish official version Future Version | 1 day
Minimum time needed for TxSET to publish a new version of implementation guides after the design requirements have been given to TxSET. | 21 weeks'**
Delivered to TTPT

## Unassigned Change Controls
Change Controls
| Approved | Transactions | Version | Scope | Size/Swag | Description | Notes
pending |  | 810 |  | System | 2 | Potential 810 - 867 billing determinants changes
pending |  | 810_02 |  | System | 3 | allow TDSP to send single corrected invoice for IDR meters
3-503 | Y | 810_02 | Future | System | 3 | allow TDSP to send single corrected invoice for non-IDR meters | Valid per TX SET review 3/24/04
2-316 | Y | 814_22 | Future | System | 2 | Add the N1~loop to the 814_22 | Nullified
2-412 | Y | 814_09 | 1.6 | Gray Box/Examples | 1 | Cleanup of Example box | Already Applied to 2.0
2-413 | Y | 814_11 | 1.6 | Gray Box/Examples | 1 | Add example | Already Applied to 2.0
2-414 | Y | 814_13 | Future | Gray Box/Examples | 1 | Add example | Already Applied to 2.0
2-415 | Y | 814_25 | Future | Gray Box/Examples | 1 | Add example | Already Applied to 2.0
2-447 | Y | 814_10 | Future | System | 1 | Remove segments from N1~8R | Nullified
2-449 | Y | 814_14 | Future | System | 1 | Remove N2 segment from the N1~8R Loop and update gray boxes | Nullified
2-466 | Y | 650_04 | Future | System | 2 | Add code to 650_04 provide means to alert CR that service has been permanently suspended for ESI ID and numerous gray box changes | Valid per TX SET review 3/24/04
2-468 | Y | 810_03 | Future | System | 1 | Multiple 810_03 changes - code gray box | Valid per TX SET review 3/24/04
3-471 | Y | 650_04 | Future | System | 1 | remove must use from the YNQ04 of the NQ~5U segment | Valid per TX SET review 3/24/04
3-490 | Y | 814_14, 814_22 | Future | Gray Box/Examples | 1 | remove QTR from valid values of Meter Type from the gray box | Valid per TX SET review 3/24/04
3_493 | Y | 814_27 | Future | System | 1 | Make the N1~8S OPTIONAL on the 814_27 to be consistent with the 814_26 N1~8S loop | Valid per TX SET review 3/24/04
3_496 | Y | 650_02 | Future | System | 2 | Provide additional detail on when 650_02 should be generated and how the process should work for disconnect and reconnect for non-pay | Re-evaluate-Jennifer Teel, Bill Reily, Kathy Scott. CC was referred to Shannon Bowling and Blake Gross of Disco Reco TF.
3_497 | Y | 814_PD | Next Release | System | 1 | Remove "Zip" from the REF02 of the REF~7G segment (Rejection Reason) | Re-evaluate for validity (497, 498, 574, 596)
3_498 | Y | 814_PC | Next Release | System | 1 | Clean up of the 814_PC | Re-evaluate for validity (497, 498, 574, 596)
3_517 | Y | 814_28 | Future | System | 1 | Adding to reasons for "Complete Unexecutable" | Valid per TX SET review 3/24/04
3_527 | Y | 650_02 | Future | System | 1 | Adding to reasons for "Complete Unexecutable" | Valid per TX SET review 3/24/04
3_530 | Y | 650_01 | Future | Gray Box/Examples | 1 | Cleanup of Gray box and Example | Valid per TX SET review 3/24/04
3_532 | Y | 814_04 and 05 | Future | System | 2 | 814_04 and 05 needs a Meter Ownership Type code to eliminate gap when customer chooses competitive meter to notify new REP when switching | Valid per TX SET review 3/24/04
3_538 | Y | 867_03 | Future | System | 2 | Changes to examples in the Implementation Guide | Valid per TX SET review 3/24/04
3_539 | Y | 814_29 | Future | Gray Box/Examples | 1 | Add the BGN07 code to the gray box example in BGN segment | Valid per TX SET review 3/24/04
3_569 | Y | Entire 814 series 01-29, PC and PD | Future | Gray Box/Examples | 1 | Provide gray box clarification to the LIN segment to indicate that the Texas Market supports only 1 LIN loop per SDI Transaction | Valid per TX SET review 3/24/04
3_571 | Y | 814_09 and 814_13 | Future | Gray Box/Examples | 1 | Move segment gray box verbiage for A78 being used only by ERCOT and TDSP to gray box on actual code | Valid per TX SET review 3/24/04
3_572 | Y | 814_13 and 814_02 | Future | Gray Box/Examples | 1 | Add short title "Earliest Available Switch Date" to the EAS Reject code (REF*7G) | Re-evaluate
3_573 | Y | 814_08 and 814_09 | Future | Gray Box/Examples | 1 | Remove references to the word "reinstate" in the 814_08 and 814_09 transactions | Valid per TX SET review 3/24/04
3_574 | Y | 814 PC | Future | Gray Box/Examples | 1 | Remove existing transaction notes form the 814 PC guide | Re-evaluate for validity (497, 498, 574, 596)
3_576 | Y | 814_20 | Future | System | 1 | Meter Exchange/Profile Information | Re-evaluate
3_577 | Y | 814_17 | Future | Gray Box/Examples | 1 | Example 1 and 3 of the 814_17 guide need to have the REF*7G segment revised to match the new reject code detail put in place by the V2.0 change controls | Valid per TX SET review 3/24/04
3_578 | Y | 814_20 | Future | System | 2 | Added a new change code to indicate the annual Load Profile changes | Valid per TX SET review 3/24/04
3_580 | Y | 820_03 | Future | System | 2 | Change for adding payment adjustment | Withdrawn
3_581 | Y | 867_04 | Future | Gray Box/Examples | 1 | Example change | Valid per TX SET review 3/24/04
3_582 | Y | 814_08 | Future | System | 1 | add B30 - MIMO change | Valid per TX SET review 3/24/04
3_583 | Y | 814_02, 11, 17, 19, 21, 25, 27 | Future | Gray Box/Examples | 1 | if same BGN02 comes from two different CRs one will be rejected | Valid per TX SET review 3/24/04
3_590 | Y | 814_21 | Future | System | 1 | Add code for ERCOT generated reject | Valid per TX SET review 3/24/04
3_594 | Y | 814_08 | Future | Gray Box/Examples | 1 | MIMO clean up | Valid per TX SET review 3/24/04
4-595 | Y | 814_12 | Future | Gray Box/Examples | 1 | MIMO clean up | Valid per TX SET review 3/24/04
4-596 | Y | 814_PC | Future |  | 1 | Clarify timming to use transaction | Re-evaluate for validity (497, 498, 574, 596)
4-597 | Y | 814_13 | Future | Gray Box/Examples | 1 | MIMO clean up | Valid per TX SET review 3/24/04
4-598 | Y | 814_08,09 | Future | Gray Box/Examples | 1 | provide examples | Valid per TX SET review 3/24/04
4-601 | Y | 814_13 | Future | System | 1 | Add new reject code "ICD" MIMO | Valid per TX SET review 3/24/04
4-602 | Y | 814_08 | Future | Gray Box/Examples | 1 | MIMO clean up | Valid per TX SET review 3/24/04
2004-604 |  | 814_09, 814_13, 814_25 | Future | Gray Box/Examples |  | The gray boxes in CC2003-400 were written such that the ‘OA’ code will be sent on every response from the TDSP, reject or accept. This needs to be changed to only send the ‘OA’ code on rejects to be consistent with CC2003-401, which is the same change for the 814_11.
2004-605 |  | 814_25 | Future | Gray Box/Examples |  | Update the examples in the 814_25 examples to include the Move Out Date which is required in accept transactions
2004-607 |  | 820_03 | Future | System |  | changes to the 820_03 transaction are needed to add data elements/segments to accommodate payment adjustments to the CR when payments are adjusted on the customer’s Muni-Co-op account due to being applied to an incorrect account, for the wrong amount, or in the case of a returned check
2004-608 |  | 820_02 | Future | Gray Box/Examples |  | Corrected examples for the 820_02
2004-610 |  | 810_02 | Future | System |  | The purpose of this request is to allow clarity in the use of the invoice due dates when an original invoice has been cancelled and the new invoice is sent
2004-611 |  | 867_03 | Future | Gray Box/Examples |  | 867_03 DTM~514 Gray Box in the PTD~PM loop contains example errors. Also need to correct Example #15 & #16 to reflect this correction (examples added in CC2003-538).
2004-613 |  | 814_01, 814_03, 814_16 | Future | Gray Box/Examples |  | Cleanup of graybox on N404 element. The URL does not work.
2004-614 |  | 814_08, 814_09 | Future | System |  | There have been questions on whether the REF~1P segment can be sent multiple times on the 814_08 and therefore sent back multiple times on the 814_09
2004-615 |  | 650_01 | Future | System |  | Need to expand the message text in the MTX segment from 80 characters to 255 characters
2004-616 |  | 814_11 | Future | System |  | Add ‘SBD’ Reject code to the 814_11
2004-617 |  | 814_20 | Future | Gray Box/Examples |  | Update the DTM Effective Date gray box, DTM Start Date gray box, & DTM End Date gray box to reflect validations that are in ERCOT’s Lodestar system.
2004-620 |  | 814_08 | Future | Gray Box/Examples |  | Update the BGN06 gray box to indicate the 814_08 BGN06 will match the BGN06 of the 814_14 or 814_22 in situations where there is a Drop to AREP or Move out to CSA

## Trx Description Card
TEXAS SET VERSION 1.6 |  |  | 650* | Maintenance Service Order - Work Orders, Meter Config. Details, Outage Notification
814 - Request, Response, Maintenance for Enrollments, Drops, Switches, Maintenance & Request Consumption
Trx | Definition | Flow | Trx | Definition | Flow
814_PC | Maintain Customer Information Request | CR=>TDSP | 650_01 | Basic Service Order | CR=>TDSP
814_PD | Maintain Customer Information Response | TDSP=>CR
814_01 | Enrollment Request | CR=>ERCOT | 650_02 | Service Order Complete Response | TDSP=>CR
814_02 | Enrollment Reject Response | ERCOT=>CR | 650_04 | Suspension of Delivery Svc Notification or Cancellation | TDSP=>CR
814_03 | Switch CR Notification Request | ERCOT=>TDSP
814_04 | Switch CR Notification Response | TDSP=>ERCOT | 650_05 | Suspension of Delivery Service Reject Response | CR=>TDSP
814_05 | Premise Info & Enrollment Response | ERCOT=>CR
814_06 | Drop Due to Switch Request | ERCOT=>CR | *The 650_03 functionality was distributed amongst the other 650 transactions.
814_07 | Drop Due to Switch Response | CR=>ERCOT
814_08 | Cancel Switch Request | CR=>ERCOT | 810 - Statement, Settlement, Wire Charge Invoices
|  | ERCOT=>CR | 810_02 | Wires Charge/Service Order Charge Invoice | TDSP=>CR
ERCOT=>TDSP
814_09 | Cancel Switch Response | ERCOT=>CR | 810_03 | Muni/Coop Invoice | CR=>MCTDSP
CR=>ERCOT
|  | TDSP=>ERCOT | 820 - Payment and Advice through Bank
814_10 | Drop to AREP Request | CR=>ERCOT | 820_02 | CR Remittance Advice | CR=>TDSP
814_11 | Drop to AREP Response | ERCOT=>CR
814_12 | Move-In/Move-Out Dte Chg Request | CR=>ERCOT | 820_03 | Muni/Coop Remittance Advice | MC TDSP=>CR
ERCOT=>CR
|  | ERCOT=>TDSP | 824 - Reject Response to 810 or 867 Data - O
814_13 | Move-In/Move-Out Dte Chg Response | ERCOT=>CR | 824 | Application Advice | CR=>TDSP
|  | CR=>ERCOT |  |  | CR=>ERCOT
|  | TDSP=>ERCOT |  |  | ERCOT=>TDSP
814_14 | AREP Enrollment Request | ERCOT=>AREP | 867-Interval, Non Interval, Reads & Consumption Data Historical and Monthly Activity
814_15 | AREP Enrollment Response | AREP=> ERCOT
814_16 | Move-In Request | CR=>ERCOT | 867_02 | Historical Usage | TDSP=>ERCOT
814_17 | Move-In Reject Response | ERCOT=>CR |  |  | ERCOT=>CR
814_18 | Establish/Delete CSA CR Request | CR=>ERCOT | 867_03 | Monthly Usage | TDSP=>ERCOT
|  | ERCOT=>TDSP |  |  | ERCOT=>CR
814_19 | Establish/Delete CSA CR Response | ERCOT=>CR | 867_04 | Initial Meter Read Notification | TDSP=>ERCOT
|  | TDSP=>ERCOT |  |  | ERCOT=>CR
814_20 | Create/Maintain/Retire ESI ID Request | TDSP=>ERCOT
ERCOT=>CR
814_21 | Create/Maintain/Retire ESI ID Response | ERCOT=>TDSP
CR=>ERCOT
814_22 | CSA CR Move-In Request | ERCOT=>CR
814_23 | CSA CR Move-In Response | CR=>ERCOT
814_24 | Move-Out Request | CR=>ERCOT
ERCOT=>TDSP
814_25 | Move-Out Response | ERCOT=>CR
TDSP=>ERCOT
814_26 | Ad-Hoc Historical Usage Request | CR=>ERCOT
ERCOT=>TDSP
814_27 | Ad-Hoc Historical Usage Response | ERCOT=>CR
TDSP=>ERCOT
814_28 | Completed Unexecutable or Permit Required | TDSP=>ERCOT
ERCOT=>CR
814_29 | Response Completed Unexecutable or Permit Required - O | ERCOT=>TDSP
CR=>ERCOT