## TX SET Information
TX SET |  |  |  |  | DATE | 2004-01-20 | 2004-01-21 | 2004-02-17 | 2004-02-18 | 2004-03-23 | 2004-03-24 | 2004-04-19 | 2004-04-20 | 2004-05-18 | 2004-05-19 | 2004-06-22 | 2004-06-23 | 2004-07-20 | 2004-07-21 | 2004-08-17 | 2004-08-18 | 2004-09-21 | 2004-09-22 | 2004-10-19 | 2004-10-20 | 2004-11-16 | 2004-11-17 | 2004-12-07 | 2004-12-08
[5 empty] | CITY | 2004-01-20: Austin; 2004-02-17: Austin; 2004-03-23: Austin; 2004-04-19: Corpus Christi; 2004-05-18: Dallas; 2004-06-22: Austin; 2004-07-20: Austin; 2004-08-17: Austin; 2004-09-21: Houston; 2004-10-19: Tulsa; 2004-11-16: Austin; 2004-12-07: Austin
OFFICER | NAME | COMPANY | EMAIL@ADDRESS | PHONE | MEETING VENUE | Comfort Suites | Comfort Suites | Comfort Suites | Comfort Suites | Comfort Suites | E M 206 A | AEP | AEP | TXU | TXU | E M 206 A | E M 206 A | E M 168 | E M 168 | Comfort Suites | Comfort Suites | CNP Tower | CNP Tower | AEP | AEP | E M 168 | E M 206 A | E M 206 A | E M 206 A
| Baum, Thomas | ERCOT | tbaum@ercot.com | 512-248-6550 | bar: 2004-06-22 to 2004-11-17
| Bear, Jason | Direct Energy | bar: 2004-01-20 to 2004-04-20; 2004-08-17 to 2004-08-18
| Bell, William | CenterPoint Energy | william.bell@centerpointenergy.com | 281-610-0309 | bar: 2004-04-19
| Bevill, Rob | Green Mountain | rob.bevill@greenmountain.com | 512-691-6134 | bar: 2004-01-20 to 2004-03-24; 2004-05-18 to 2004-06-23; 2004-09-21 to 2004-11-17
| Blumenthal, Ellen | GDS Associates | ellen.blumenthal@gdsassociates.com | 361-949-1578 | bar: 2004-04-19
| Bratton, Charlie | TXU Energy | cbratto1@txu.com | 214-875-3703 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-05-19; 2004-07-20 to 2004-08-18; 2004-10-19 to 2004-11-17
| Burke, Allan | TNMP | aburke@tnpe.com | 817-377-5532 | bar: 2004-09-21 to 2004-09-22; 2004-11-16 to 2004-11-17
| Callender, Wayne | City of Public Service SA | wdcallender@cps-satx.com | 210-353-2779 | bar: 2004-04-19; 2004-08-17 to 2004-08-18
| Campirano, Eduardo | BPUB | ecampirano@brownsville-pu.com | 956-983-6279 | bar: 2004-04-19
| Collard, Zach | CenterPoint Energy | zach.collard@centerpointenergy.com | 281-433-7050 | bar: 2004-04-19; 2004-07-21; 2004-11-16
| Conner, Mike | BTU | mconner@btutilites.com | 979-821-5830 | bar: 2004-04-19
| Dauterive, Eddie | Envision Utility Software | eddied@envworld.com | 512-266-7787 | bar: 2004-04-19
| Davis, Mike | ERCOT | mdavis@ercot.com | 512-248-6763 | bar: 2004-02-17; 2004-03-23; 2004-04-19; 2004-09-21
| Dawson, Bernie | Envision Utility Software | bernardd@envworld.com | 512-266-7787 | bar: 2004-01-20; 2004-02-17 to 2004-11-17
| Duke, Warren | Peace Software | bar: 2004-06-22; 2004-10-19 to 2004-11-17
| Farley, Karen | ERCOT | kfarley@ercot.com | 512-248-3141 | bar: 2004-04-19; 2004-06-22 to 2004-06-23
| Fisher, Sarah | NEC | sfisher@nueceselectric.org | 361-387-2581 | bar: 2004-04-19
| Flores, Eloise | Nueces Electric Coop | eflores@nueceselectric.org | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-05-18; 2004-06-22; 2004-09-21; 2004-11-16 to 2004-11-17
| Flowers, BJ | TXU Energy | bj.flowers@txu.com | 214-812-4330 | bar: 2004-01-20; 2004-06-22; 2004-07-20; 2004-08-17 to 2004-09-22
| Fredericks, Jennifer | ERCOT | jfredericks@ercot.com | 512-248-6733 | bar: 2004-01-20 to 2004-03-23; 2004-06-22; 2004-08-17 to 2004-08-18; 2004-11-16 to 2004-11-17
| Garcia, Jennifer | USA Interlink | bar: 2004-04-19; 2004-08-17 to 2004-09-22
| Godoy, Ernie | SPEC | egodoy@sanpatricioelectric.org | 361-364-2220 | bar: 2004-04-19; 2004-05-18
| Harper, Brett | First Choice | bharper@firstchoicepower.com | 817-437-1479 | bar: 2004-06-22 to 2004-11-17
| Hensley, Bryan | TCE | bryan.hensley@mytce.com | 214-509-2195 | bar: 2004-01-20 to 2004-04-20
| Hermes, Connie | STEC | connie@stec.org | 361-485-6173 | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-04-20; 2004-09-21
| Hernandez, Ron | ERCOT | rhernandez@ercot.com | 512-248-6523 | bar: 2004-04-19
| Jackson, Tom | Austin Energy | Tom.Jackson@austinenergy.com | 512-322-6324 | bar: 2004-03-23 to 2004-03-24
| Kalips, Leo | NISC | leo.kalips@nisc.cc | bar: 2004-04-19
| Kernick, Kristina | Envision Utility Software | kristinaak@envworld.com | 512-266-7787 | bar: 2004-04-19
| Leith, Brent | First Choice | bleith@firstchoicepower.com | 701-306-6810 | bar: 2004-04-19; 2004-05-18 to 2004-07-21
| Lowder, Dave | SPEC | dlowder@sanpatricioelectric.org | 361-364-2220 | bar: 2004-04-19
| McKain, Shelley | ADS Mutual Energy | smckain@alldata.net | 918-493-9515 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24; 2004-07-20 to 2004-07-21
| Moast, Pat | ERCOT | pmoast@ercot.com | 512-261-9925 | bar: 2004-04-19
| Moore, Chuck | Direct Energy | chuck.moore@ngwi.com | bar: 2004-01-20; 2004-03-23; 2004-04-19 to 2004-05-19; 2004-07-20 to 2004-09-22; 2004-11-17
| Morales, Rita | Direct Energy | ritamorales@ngwi.com | 972-480-8224 | bar: 2004-01-20; 2004-03-23 to 2004-03-24; 2004-04-20 to 2004-08-18; 2004-10-19 to 2004-11-17
| Ohrt, Wendy | STEC | wendyjo@stec.org | 361-485-6172 | bar: 2004-01-20; 2004-02-17; 2004-03-23 to 2004-04-20; 2004-09-21
| Patrick, Kyle | Reliant Energy | kpatrick@reliant.com | 713-497-3396 | bar: 2004-01-20 to 2004-11-17
| Polliard, Sharon | AEP | bar: 2004-10-19
| Reed, Cary | AEP | careed@aep.com | 918-260-0093 | bar: 2004-01-20 to 2004-02-18; 2004-04-19 to 2004-11-17
| Rehfeldt, Diana | TNMP/First Choice Power | drehfeldt@tnpe.com | 817-377-5580 | bar: 2004-01-20 to 2004-01-21; 2004-07-20 to 2004-07-21
| Reily, Bill | TXU Electric Delivery | breily1@txu.com | 214-875-2520 | bar: 2004-01-20 to 2004-03-23; 2004-04-19 to 2004-04-20; 2004-05-19 to 2004-09-22; 2004-11-16 to 2004-11-17
| Riordon, Ken | LCRA | ken.riordon@lcra.org | 512-473-3215 | bar: 2004-04-19; 2004-05-18
| Robertson, Johnny | TXU | jrobert1@txu.com | 214-875-1565 | bar: 2004-01-20; 2004-03-23 to 2004-11-17
| Robinson, Laura | Starlight Electric | laura@starlightelectric.com | 817-548-0808 | bar: 2004-09-21 to 2004-09-22
| Rodriguez, Robert | Constellation New Energy | Robert.Rodriguez@constellation.com | 281-793-6339 | bar: 2004-01-20; 2004-03-23; 2004-05-18 to 2004-06-22; 2004-07-20; 2004-08-17; 2004-09-21; 2004-10-19 to 2004-11-16
| Saenez, Fernando | BPUB | fsaenez@brownsville-pu.com | 956-983-6266 | bar: 2004-04-19
| Scott, Kathy | CenterPoint Energy | Kathy.d.scott@centerpointenergy.com | 713-945-6630 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-03-24; 2004-05-18 to 2004-07-21; 2004-10-19 to 2004-11-17
| Smith, Lori | TNMP | lsmith@tnpe.com | 817-337-5532 | bar: 2004-09-21 to 2004-10-20
| Steen, Lora | Entergy | lsteen@entergy.com | 936-525-2034 | bar: 2004-01-20 to 2004-01-21; 2004-05-19
| Teel, Jennifer | EC POWER | jennifer.teel@ec-power.com | 713-403-8731 | bar: 2004-01-20 to 2004-01-21; 2004-03-23 to 2004-04-20; 2004-11-16
| Thomas, Jeff | Direct Energy | jeff.thomas@mytce.com | 214-509-2122 | bar: 2004-04-19; 2004-05-18 to 2004-06-22; 2004-07-20 to 2004-07-21
| Weaver, Steve | Entergy Solutions | sweave1@entergy.com | 832-681-3146
| Wilburn, Suzette M. | ERCOT | swilburn@ercot.com | 512-248-3991 | bar: 2004-01-20 to 2004-04-20; 2004-05-19; 2004-07-20 to 2004-07-21; 2004-10-19 to 2004-11-17
| Wilson, Frank | Nueces Electric Coop | fwilson@nueceselectric.org | 361-387-2581 | bar: 2004-02-17; 2004-04-19
| Wingerd, Glen | ERCOT | gwingerd@ercot.com | bar: 2004-04-19; 2004-11-16
| Shillington, Shawn | TNMP | sshillington@tnpe.com | bar: 2004-11-16 to 2004-11-17

## Project Plan
Project Plan for Next Release
Activity | Time Frame | Start Date | End Date | Membership
Identify all changes required for Future Version. Submit all change controls to be applied to version Future Version. Discussion and approval/denial of all change control design documents. | As determined
Update current version 1.5 to a clean baseline with all change controls applied | 3 weeks
Review all change controls and prepare any SCRs and PRRs as needed | 1 week
Build SEF and Word docs. With all Future Version change controls applied. | 3 weeks
Publish Future Version first draft redline | 1 day
Tx SET committee will review and compare Visio's, change controls and implementation guides. All market participants will start design and technical analysis. | 6 weeks
Resolve issues | 1 week
Apply resolved issues and any change controls approved since the redline publication | 1 week
Publish final Future Version redline | 1 day
TxSET committee will review and compare Visio's, change controls and implementation guides. Any identified gaps or errors will be sent to TxSET | 2 weeks
Resolve issues | 1 week
Apply resolved issues | 1 week
Update Transaction Scenario Inventory. Clean up any identified errors. | 2 weeks
Publish official version Future Version | 1 day
Minimum time needed for TxSET to publish a new version of implementation guides after the design requirements have been given to TxSET. | 21 weeks'**
Delivered to TTPT

## 2004 Open Action Items
Meeting | Segment | Sponsor | CC | Issue | Action Item | Resolution | Status | Date
2004-04-01 |  |  |  | DNP Taskforce Recommendations | DNP Taskforce to hand off deliverables | (8/17/04) Taskforce still in working and all deliverables jest to be delivered (10/12/04) Change Control written and approved for priority disconnect procedures. There maybe additional change control required from this Taskforce (11/17/04) - Charlie Bratton will write a change control to include rejection code for Life Support/Critical Care | Open
2004-04-01 | MOU/EC | Austin En |  | Change 810_03 to separate cancel examples into a 3-step process: (1) original (2) cancel (3) re-bill. Similar to changes that were made to 810_02. |  | (6/23/04) No progress yet Update 08/25/04 -Bernie Dawson and Kathy Scott will work to create new examples for the 810_03 to look similar to the 810_02 transaction (11/17/04) Still Open for example modification and BPO Removed from 810_03 and 820_03 (11/17/2004) Still open for Change Control | Open
2004-04-01 | MOU/EC |  |  | Change 814_18 to handle co-op membership requirements. Landlord billing information. | Low Priority | (6/23/04) No progress yet Update 08/25/04 - Bernie Dawson will write a change control for the 814_18 to add new segment (N1~BT loop) for landlord information and provide a process where ERCOT would send this transaction to MOU/EC as well as the CSA CR for membership information. For an 814_03 (CSA Customer) Nueces will complete unexecuteable with 814_28 until CSA Name Match Membership can be verified. (10/12/04) Update: Texas SET will need to look at the overall process in detail to determine all the issues and fallout of this process (11/17/2004) Still open at this point | Open
2004-05-01 |  |  |  | 864 straw dog example | Johnny Robertson and Cary Reed to draft example | (6/23/04) In progress, expect report in August or September. (8/17/04) Cary and Johnny should be able to provide this information at the September meeting (10/12/04) Cary and Johnny will need to submitt to Texas SET for discussion at the January 2005 meeting (11/17/2004) Still open for discussion | Open
2004-05-01 |  | Mass Transition Taskforce |  | Mass Transition Phase 1 |  | (6/23/04) To be addressed along with MT Phase II (8/17/04) Phase II Meeting has been scheduled 9/30/04 at ERCOT Met Center Room 168 (11/17/2004) Still open for discussion and Phase II recommendations | Open
2004-05-01 |  | CNP |  | 814_21 pass-through to TDSP | Kathy Scott to create draft change control for updating the 814_20 business process | (6/23/04) Kathy submitted the CC at June TX SET (8/17/04) TX SET Sub team had a meeting in Dallas on July 12, 2004. TX SET is waiting for responses back from CRs on concerning their rejects or 814_21 before the next steps are taken (10/12/04) Suzette and Tom will bring updated information back to Texas SET in January 2005 to determine if there is a problem or issue. (11/17/2004) Still open for further investigation and analysis | Open
2004-07-01 |  | TX SET Leadership |  | Action Items List |  | (6/23/04) Leadership will provide a printed copy of the most recent list of Outstanding Action items at each TX SET meeting. (8/17/2004) Open as a reminder to Leadership only | Open
2004-07-01 | TDSP | RMS |  | TDSPs look at the reasons why estimations are being created, if reason is flagged into any internal systems? What are some of the options for CRs when consecutive estimates are encountered? Discussion was to consider a new segment in the 867_03 and 867_04 transactions to indicate reasons for estimation. | 09/22/04 Update: Sub-team was asked by Texas SET to add general guidelines in the event of a estimated usage for both CR and TDSP . This information will be brought back to the October TX SET meeting and possibly presented at the October/November RMS | (10/12/04) Update - Bill Reily will be placed on the November 2004 Texas SET agenda to discuss the recommendations of the subteam to Texas SET (11/17/04) - Closed, TX SET will discuss further adding a reason code for estimations | Closed | 38308
2004-07-01 | CR | RMS |  | CRs what are you doing when you receive an 867_03 transactions with the Estimation Flag indicated in the transaction, as well as, the MEA Segment flag showing EE (Meter reading-beginning estimated/ending estimated) previous and current billing estimated. EE - Meter reading-beginning estimated/ending estimated | 09/22/04 Update: Sub-team was asked by Texas SET to add general guidelines in the event of a estimated usage for both CR and TDSP . This information will be brought back to the October TX SET meeting and possibly presented at the October/November RMS | (11/17/2004) Still open for further discussion and CR responses | Open
2004-07-01 |  | DEWG |  | Linked ESI ID issue- TX SET needs to determine how the TDSPs use the address field in the 814_04, is it echoed back from the 814_03 or do they pull the actual service address from their systems. Note: Where requirements are identified for flushing out and developing should go back to RMS for update. TDSPs have the most accurate informatoin regarding the ESI ID so if they have an address tat is different from what was sent on the initiating transaction and/or exists on the portal, this should be the address that is followed, however before TX SET agrees to amkde a change to the 814_04 transaction they would like to know if any statistics can be gathered on how many discrepancies exist | ERCOT will look into whether this type of information can be obtained | (8/17/2004) Update will be provided to TX SET at the September Meeting - Plan is to take a sample of July's 814_04 to determine where the problems may be initiated (10/12/04) Update - Meeting will be arranged with ERCOT and TDSPs prior to the November 2004 Texas SET meeting to create recommendations to bring back to Texas SET for discussion (11/17/2004) Closed | Closed | 38308
2004-08-17 |  | RMS |  | Texas SET v2.1 to be Redline |  | (11/17/2004) initial discussion of v2.1 change controls scheduled for December 2004 TX SET Meeting | Open
2004-08-17 |  | RMS |  | Customer Protection Rules as per discussions with PUCT Staff. Need to develop a process to support Customer Protection Rule 25.472 Section b Paragraph 3 | Bill Reily will lead a TX SET sub-team to address issues and what is needed to support Customer Protection Rule for Historical Usage for Commercial and Industrial retail customers where usage is considered competitively sensitive. The sub-team will come back to the larger Working group with issues and potential recommendation, members will be: Lauren Damen (PUCT Staff), Kyle Patrick, Chuck Moore, Charlie Bratton, Cary Reed, Kathy Scott, Suzette Wilburn 09/22/04 Update: Subteam met to discuss impacts from the customer protection ruling on passing historical usage imformation deemed competitively sensitive. Lauren Damen will review high level process changes with the PUC | (10/12/2004) Bill Reily and Texas SET is awaiting guidance from PUCT Staff (Lauren Damen) on this Action Item (11/17/2004) Still pending PUCT answers back to TX SET - This will be moved to an agenda item for December 2004's meeting | Open
2004-08-17 | TX SET Leadership |  |  | Should there be some documented procedures for Market participants to communicate non-emergency system/process and/or procedure changes? | TX SET Leadership has a question of RMS Leadership Communicating Market information - Who does what, when (how early, deadline, or timelines) and how should information be communicated. | (10/12/04) Kathy Scott will take request to Lon Conn and Karen Farley to add this process to the RMS Assignment Form (11/17/2004) Still open to be discussed with the Communications Taskforce of COPS to outline the details of communicating information | Open
2004-08-17 |  | ERCOT |  | If an 814_20 maintain is sent (ASI~7~001) is it expected that there will always be a REF~TD (reason for change) present, either at the header level (LIN Loop) or meter level (NM1 Loop)? | CR's will check to see if they expect a REF~TD when an NM1~MX exists. REF~TD validation cannot be added to the ASI segment. | (10/12/04) To be discussed at the November 2004 Texas SET Meeting (11/17/2004) ERCOT and CRs will need to get together to determine what should be accepted on the 814_20- REF~TD Reason for Change | Open
2004-08-25 |  | ERCOT |  | In an effort to address 814_23 rejects ERCOT has created reports, by CR, that list the 814_23 rejects received, with the reject reason. The data pulled is from June 03 to current. ERCOT would like to take the same approach as used for the 814_21 rejects and send these lists out to the affected CRs for information on what the reject means and what they are expecting to happend by sending the rejects | ERCOT (Suzette Wilburn and Tom Baum) will compile the results from 814_23 reject to send to the CRs for additional information as to the reasons for the rejection. This will only be analysis and fact finding to resolve the issue of receiving these type rejections. 09/22/04 Update: Deferred to the October 2004 Texas SET meeting | (10/12/04) ERCOT will bring post MIMO data to the January 05 TX SET Meeting (11/17/2004) Still open time for January discussion | Open
2004-08-31 | MOU/EC |  |  | If MOU/EC has disconnected services for Non-Payment for a customer is there a possiblity that the CR would send a MVO for the customer based upon the DNP being completed. Customer may come in to pay outstanding bill to MOU/EC but the ESI ID has been final billed because of the MVO. | Nueces - will monitor this process to determine if a change control is needed | 08/25/04 - Nueces - will monitor this process to determine if a change control is needed (11/17/2004) Continued Discussion | Open
2004-09-22 |  | Market Rules |  | Diana Zake is sending out a request for TX SET representatives to attend a meeting on October 5th to review the reamil market-operating guide | Request that Market participants including Texas SET members assist in making revisions/updates and reformatting Retail Market Guide along with it's associated documents | 11/17/2004 - Kyle has sent scope and procedures document need to send change control documentation | Open
2004-09-22 |  | BJ Flowers |  | CNP's Process: for MVI and MVOs with the two day window, CRs submit the current FasTrak spreadsheet directly to CNP that would normally be sent as a FasTrak to the TDSP. CNP then submits an 814_28 Complete Unexecuteable '09' to cancel order using automated transactions. Notification automatically to ERCOT and CR closing BPI. | BJ Flowers is requesting other TDSPs to review this change in process made by CNP for handling MVIs and MVOs with the two day wind and to consider implementing this new process. CRs are requesting consistency in this process. Cary Reed requested that CRs need to agree on whether they all want this process to change to be consistent with CNP. TDSPs will review this process to determine if it is something they can all implement. | 11/17/2004- Discussion at this time was that AEP, TNMP, and TXU ED have evaluated what could be done internally, however each could not make a definite commentment as to when this process could be done. | Open
2004-10-12 |  | Constellation |  | Usage Smoothing- What does each TDSP do? Cancel/Rebill True-up in subsequent cycles Other? | Robert Rodriguez will lead a small group of CRs to document the questions that need answering by the TDSPs concerning cancel re-bill procedures, smoothing, and zero usage. Sub-team: Kyle Patrick, Charlie Bratton, Rob Bevill, Brett Harper | (11/17/2004) Continued Discussion | Open
2004-10-12 | ERCOT | Texas SET |  | What is the appropriate process for cancelling DROP to AREP based upon version 2.0 and Protocols. | Because the Implementation Guide for the 814_08 is out of Synch with the documented procedures for a CR to Cancel a Drop to AREP in Protocols in Chapter 19 - Suzette Willburn (ERCOT) will investigate if ERCOT and/or James Cohea's group can provide a standard procedure that allows a CR to send the FasTrak request to ERCOT, without the TDSP being involved in the FasTrack, and ERCOT will create an 814_08 transaction to the all TDSPs - creating a standardize process for the Market. | (11/17/2004) TX SET has a question to PUCT Staff on this process: Question: Is PUCT Staff OK if we use existing market design and rules for transactions processing during the evaluation period rather than creating manual processes to work these type issues in the Market? | Open
2004-11-17 |  | Texas SET |  | Multiple ESI IDs assigned to a single address- Is there any way an address and/or ESI can be uniquely identified to know what is being servicec? Example Guard Light, Barn, Residence, Garage/Tool House. |  |  | Open
2004-11-17 |  | Robert Rodriguez |  | Robert Rodriguez will hold another conference call to discuss examples and develop a white paper of specific questions on what CRs would like to know with regard to the smoothing process at each TDSP. Smoothing: Actual – Estimate – Actual. The two actuals are inconsistent so the TDSP cancel/rebills the timeframe back to the first actual to adjust the usage for the months between the two actuals. | Robert Rodriguez will host another conference call to discuss CR examples. Cycles affected by the smoothing/pro-rating/cancel-rebilling. These examples will be forwarded to both ERCOT and the TDSPs. CRs will then review the TDSP estimation procedures and develop a white paper with specific questions. |  | Open
2004-11-17 |  | ERCOT |  | Currently ERCOT checks the dates on the initiating transactions (16, 24) to make sure they are within the appropriate windows (no more than 90 calendar days in the future or 270 calendar days in the past). Want to find out if TX SET is in agreement to add this validation to the 814_12s as well as they act in the same manner as the initiating transactions | TX SET agrees with adding the date reasonableness validation to the 814_12. ERCOT will write the SIR that will be presented on the Retail Market Call. |  | Open
2004-11-17 |  | Texas SET |  | 814_28 unexecutables come through for a MVI service order with a MVO in the LIN07 and a MVO action code (ASI02=002). | TX SET recommends that the ERCOT hold off on adding the validation through an internal SIR. ERCOT will write a change control to update the 814_28 guide to remove the LIN07 and make the Action Code ASI segment generic to prevent 814_28s from being rejected. |  | Open
2004-11-17 |  | ERCOT |  | In the DTM~649 segment of the 867_03, the IG says that this segment is required when the Bill Type is LDC, but later in the gray box it states ‘not provided on cancel transactions’. Should this segment be included on a MOU/EC 867_03 cancel transaction? Currently the IG is contradicting itself | TX SET agrees that the language needs to be updated. ERCOT will write a change control to remove the requirement that the DTM~649 is not required when sending 867_03 cancels, when the BPT=01 |  | Open
2004-11-17 |  | ERCOT |  | In the DTM~649 segment of the 867_03, the IG says that this segment is required when the Bill Type is LDC, but later in the gray box it states ‘not provided on cancel transactions’. Should this segment be included on a MOU/EC 867_03 cancel transaction? Currently the IG is contradicting itself | TX SET agrees that the language needs to be updated. ERCOT will write a change control to remove the requirement that the DTM~649 is not required when sending 867_03 cancels, when the BPT=01 |  | Open
2004-11-17 |  | ERCOT |  | Modify the existing reject code A78 (“Item or Service Already Established”) to include CRs as well as TDSPs and ERCOT. This would allow CRs to reject 814_08 transactions where the BPI has already been completed. | TX SET agreed this needed to be added as an agenda item for discussion and to develop a process, if necessary for this scenario |  | Open
2004-11-17 |  | FCP |  | · Discuss pending change control for 814_09, ERCOT will query all 814_09 rejects received since V2.0 was implemented to get an idea of the reasons the TDSPs and CRs are rejecting 814_08s. ERCOT will work with FCP in getting some examples of what they are seeing and will provide analysis at the November TX SET meeting | Change Control was withdrawn by FCP for TX SET to discuss as an agenda item for the December meeting. Need to determine what the problem is and identify solution along with process to prevent. |  | Open

## 2004 Closed Action Items
Meeting | Segment | Sponsor | CC | Issue | Action Item | Resolution | Status | Date
January |  | RRI |  | Would like to investigate possibility of adding a flag to indicate whether the meter is temporary or permanent | CRs will meet to re-frame the question and provide the TDSPs with exactly what they'd like to see |  | Closed | 2004-02-17
January |  | RRI |  | Would like to investigate the possibility of adding a code on the 814_16 and 650 series that would provide gate access codes | Group agreed that more time was necessary to determine if there was a need for this type of information from all CRs |  | Closed | 2004-02-17
January |  | ERCOT |  | Review of the draft 867_01 IG for opting in entities | TDSPs to review guide with SMEs at their companies to verify guide contains all necessary segments and data elements | TX SET believes that the cost for re implementing the 867_01 is much larger than the cost for using a flat file on a on going basis. | Closed | 2004-05-13
January |  | ONCOR |  | Outdated scheduled transactions in ERCOTs system that cannot be completed | ERCOT to investigate if a common theme exists for the manual processes used to 'fix' these scheduled transactions to get a better idea of where TX SET needs to focus their attention | Comment 5/19/04: No true common theme, but the problem centers around previous versions (1.4, 1.5) trxs cannot be completed with future releases (1.6, 2.0). Kyle Patrick will refer to MCT for future discussion. | Closed | 2004-05-13
January |  | ERCOT | Y | Clarification needed on how maintenance to unmetered service devices are communicated in the 814_20 | 814_20 guide needs to be updated if the 814_20 is not used when maintaining unmetered service devices. TX SET to investigate the possibility of adding this functionality to the 814_20 | TDSPs waiting for response on whether they send 814_20s. | Closed | 2004-05-13
January |  | CNP | Y |  | 867_03 How to Use Section meeting needs to be arranged to convert the How to Use to a BPO and make the appropriate updates in the new BPO document. | Comment April TX SET: This will be an agenda item for the May meeting of TX SET in Dallas. Comment May TX SET: This will be an agenda item for the June meeting of TX SET. | Closed | 2004-05-13
January |  | TX SET |  |  | TX SET Leads need to develop a process that would remind members of outstanding and/or open action items prior to monthly meetings (1 or 2-weeks before if possible) | Leadership will remind team members of action items when meeting notice and agenda are sent. | Closed | 2004-05-13
|  | ERCOT |  | In the case of a MOV to CSA, when an 814_08 is submitted by the Cur CR, is the TDSP expecting the Cur CR or CSA CR Duns in the N1~SJ? I would believe it would be the CSA CRs Duns, because the TDSP would have received an 814_03 with the CSA CRs information, not and 814_24 with the Cur CR information. |  | ERCOT will be putting the CSA CR in the 814_08 | Closed | 2004-05-13
February |  | TX SET |  | Review BPOs for 2.0 | Cary Reed, Kyle Patrick, Suzette Wilburn, JR, and Bill Reily will review. | Comment 5/19/04: Team to meet 5/25/04 in Austin, TX venue to be determined. | Closed | 2004-05-13
February |  | ERCOT | Y | · In the event that there are multiple meters exchanged on a premise, would the profile code be listed in both NM1 loops? We have seen some instances where the profile code update (REF~LO) is included in the second NM1 loop and wanted to verify that profile codes should be accepted regardless of which NM1 loop they are communicated in o If the profile code is an attribute of the ESI-ID and not the meter, why is it in the NM1 loop? Shouldn’t it be in the LIN loop? · TX SET agrees that the profile code is at a premise level and that the profile code needs to be updated regardless of which NM1 loop it is sent in. Group also agreed that this type of update needs to be in the LIN loop, not the NM1 loop, as the change is at a premise, not meter, level | S. Wilburn to write a change control to move the REF~LO segment to the LIN loop | Comment 5/19/04: Change control has been written but not submitted. | Closed | 2004-05-13
February |  |  |  | · The N303 in the N3 segment of the 814_20 is alphanumeric. (AN1/55). Would like to find out from the group if they would like to see ERCOT rejecting transactions that send special characters in this field. o Encountered issues with double quotes in this field. Only about 40 ESI-Id · If ERCOT decides to cross validate this field and reject transactions that contain special characters, they need to look at other fields that they currently do not cross validate on. For instance, the PER segment in the 814_03 is not cross validated to ensure the phone number is sent without dashes. | ERCOT will communicate to the team what decision they decide to go with regarding the cross validation | ERCOT put validation in that reject double quotes in the address field. | Closed | 2004-05-13
February |  |  |  | · Following up on the issue regarding 814_20 retires being received on de-energized ESI-Ids with a scheduled MVI. We have a proposed short term solution o If the SMRD of the MVI is greater than the date on the retire, we cancel the MVI o If the SMRD of the MVI is less than the retire, we reject the retire and allow the MVI to effectuate | ERCOT will implement a fix in a near release to reject any 814_20 retires received on a de-energized premise with a scheduled service order. TDSP will open a fastrak issue to get open service order resolved. Release date is still to be determined. ERCOT Client Services will communicate when this change will be implemented | ERCOT will follow the short term solution in the recommendation | Closed | 2004-05-13
February |  | Nueces |  |  | E. Flores to gather all issues addressed to date regarding the Muni/Coop market to send out to the market | This will be an ongoing list | Closed | 2004-05-13
February |  | TX SET Officers |  |  | TX SET officers to make phone calls to the muni/coops about the meeting | MOU/EC meeting was held on 4/19/04 in Corpus Christi | Closed | 2004-05-13
February |  | ERCOT |  |  | ERCOT Client Services to pull together email to be sent out inviting all Muni/Coops to attend the day meeting on April 20th | MOU/EC meeting was held on 4/19/04 in Corpus Christi | Closed | 2004-05-13
February |  | TCE/STEC | Y | We need to talk about the 650_04 disconnect/reconnect process on the muni/coop side. There was some discussion at Texas Test Plan script sub team on this regarding the current test script calling for a 650_04 cancel of the disconnect request to indicate a reconnect. | TCE to work with STEC to write change control for adding a new code to the 650_04 to communicate this information | Comment 5/19/04: Jeff Thomas to update SET on this. | Closed | 2004-05-13
February |  | ERCOT | Y | Should a REF~IX always exist when a REF~4P is present in the 814-04? · For example, if you have a REF~MT~COMBO and two REF~4Ps should you also have two REF~IXs? · If not, what circumstances exist when you wouldn't, and what type of modifications could be made to the gray box to clarify this? | o (Action Item) S.Wilburn to write a change control to update the examples in the 814_04 | Comment 5/19/04: Change control was written, and withdrawn. The text will be left in the example. TX SET again stresses that MPs should code to the guide section not the examples section. | Closed | 2004-05-13
February |  | TX SET |  | "Future Implementation CCs aka Unassigned CCs" Review. (SEE WORKBOOK PAGE UNASSIGNED CHANGE CONTROLS) | TX SET members to review all "Unassigned" Change Controls at future meetings. | TX SET will begin to work on the Future Version of the I.Gs using the Unassigned change controls in this next release. | Closed | 2004-06-23
February |  | TX SET |  | Revised Working Group Procedures | TX SET members should review the Working Group Procedures Redline | Comment 5/19/04: TX SET reviewed the WG procedures they will be posted for review. WG procedures to be an agenda item at the June meeting. (6/23/04) Approved with changes on June 22, 2004- | Closed | 2004-06-23
April |  | TX SET Chair |  | ERCOT should not be completing Safety Net MVIs without electronic trx. |  | TX SET presented this back to RMS in its RMS report at the May '04 Meeting. It was TX SETs opinion that all MPs and ERCOT who participate in the Safety Net process should follow the approved guidelines. | Closed | 2004-06-23
April |  |  |  | REF~1P removal issue | CRs will discuss and frame issue prior to this becoming a TX SET agenda item. | TX SET discussed at the April meeting, the REF~1P change control was withdrawn. | Closed | 2004-06-23
April |  | ERCOT |  | 814_07 Rejects | ERCOT to develop a proposal for handling 814_07 rejects. | (6/24/04) Suzette Wilburn brought recommendations to TX SET on this. | Closed | 2004-06-23
2004-05-01 |  | ERCOT |  | ERCOT service orders completed without transactions | ERCOT to draft proposal to TX SET for reporting back to RMS | (6/23/04) ERCOT to bring back information to next TX SET meeting regarding instances where complete w/out trx occurs. | Closed | 2004-08-17
2004-05-01 |  | TX SET |  | Flag on 814_24 for instances where the first is '09'd and a second is sent | Suzette Wilburn, Kyle Patrick, Charlie Bratton, Kathy Scott to review 824 Workshop documentation and begin drafting new codes | (6/23/04) Team has not met. (8/17/04) Change Control has been written and update for discussion and approval on 8/18/04 | Closed | 2004-08-17
2004-05-01 |  | RMS |  | TDSPs to document estimation processes |  | (6/23/04) TDSPs did so at June meeting. TX SET chair to either report or request time to report to RMS at July meeting. | Closed | 2004-08-17
2004-05-01 |  | Customer Protection |  | Customer Protection compliance | Bill Reily and Charlie Bratton to organize TDSP/CR reviews of the rule | (6/23/04) Bill and Charlie to bring back report to a next TX SET meeting. (8/17/04) Subteam assigned to discuss issues and make recommendations | Closed | 2004-08-17
2004-05-01 |  |  |  | Change Control 503 | Bill Reily to draft change control | (6/23/04) Bill will draft CC prior to CC deadline for next release. | Closed | 2004-08-17
2004-05-01 |  | TXU ED |  | 867_02 large file of data | Bill Reily to bring recommendation to June Meeting | (6/23/04) Bill will bring back suggestion at a later meeting. (8/17/04) TXU ED will send additional files similar to the same process as CNP | Closed | 2004-08-17
2004-06-01 |  | CNP |  | 867_03 BPO - additional create 867_03 scenario examples to be incorporated along with gray-box changes to create one change control for the 867_03 Implementation guide | Suzette Wilburn, Tom Baum, and Kathy Scott to draft document | (6/23/04) Due to length of this document and the number of changes included in the redline version, a review of this document will be deferred to the next Texas SET meeting for discussions. The updated document will be included in the minutes for SET Membership to review at a later time. (8/17/2004) Change Control written and up for discussion and approval on 8/18/2004 | Closed | 2004-08-17
2004-07-01 |  | TX SET Sub-team |  | TX SET Subteam will discuss and develop change controls for the 814_24 (TITF Taskforce), 824 and 810_02 (810/867/824 Taskforce), 650_01 (DNP/Reconnect Taskforce) and Redlines for BPOs process changes | Shannon Bowling, Suzette Wilburn, Kyle Patrick, Cary Reed, Charlie Bratton, Brett Harper, Bill Reily, Tom Baum, Robert Rodriquez, Kathy Scott | (8/17/2004) This action item includes several other action items- to eliminate redundancy this one was closed | Closed | 2004-08-17
2004-07-01 |  | RMS |  | TX SET - Discuss an Implementation Timeline for: 810 Billing Determinants for 810/867/824 Workshops Additional SAC04 Codes requested by CNP at July RMS |  | (8/17/2004) This action item includes several other action items- to eliminate redundancy this one was closed | Closed | 2004-08-17
2004-07-01 |  | DNP Taskforce |  | TX SET Sub-team develop draft straw man of adding 3 new codes into the current YNQ Segment where CRs must give TDSPs the autohrization to Disconnect service for non-payment at one of the following disconnect points: PDL - Premium Disconnect Location ROL - Authorization to Roll to next crew, including Premium Disconnect Location MTR - Meter Only | Shannon Bowling, Suzette Wilburn, Kyle Patrick, Cary Reed, Charlie Bratton, Brett Harper, Bill Reily, Tom Baum, Robert Rodriquez, Kathy Scott | (8/17/2004) Change Control already written and up for discussion and approval on 8/18/2004 | Closed | 2004-08-17
2004-07-01 |  | Jennifer Teel- EC Power |  | Change Control needed on the 814_02 Transaction LIN Segment for SW data element - Gray Box Clarification needed to remove or eliminate the statement DTM~MRR is required when requesting an off-cycle read. There is no DTM~MRR segment in the 814_02 transactions, must have been a copy paste error. | Suzette Wilburn and Tom Baum | (8/17/2004) Change Control already written and up for discussion and approval on 8/18/2004 | Closed | 2004-08-17
2004-07-01 | PUCT Staff | Customer Protection |  | Lauren Damen (PUCT Staff) reqeusted that Bill Reily (TXU ED) re-send the same email that was forwarded to Brian Lloyd to her attention for clarification concerning competitively sensitive information regarding historical usage for C&I customers | Lauren Damen and Bill Reily | (8/17/2004) PUCT Staff provided Clarification to Bill Reily on this action item | Closed | 2004-08-17
2004-07-01 | TDSP | ERCOT |  | Follow-up 814_20 move the REF~LO Load profile from Meter level to ESI ID Level, however the 814_20 guide has load profiles communited at a meter level. TDSPs will review the proposed chane controls to move the load profile segement from the NM1 loop in the 814_20 to the LIN Loop of the 814_20. as it is an attribute of the ESI ID , not the meter. ERCOT would appreciate if the TDSPs could proivde an estimate of whether a change control would require a large system change on each company. | TDSPs to provide an update to this question | (8/17/2004) TDSPs agreed that this is not an issue and there should not be any market reason to make this change | Closed | 2004-08-17
2004-04-01 | MOU/EC | TX SET |  | Change 814_28 to allow move-in to be pended because customer is not a member of the co-op. | High Priority | (6/23/04) Redlined document posted to May meeting documents (08/17/04) No progress yet (Update 08/25/04) - MOU/EC has a temporary solution to reject switch and/or move-in without where names do not match with an A13 Rejection Code - Remarks name do not Match. Long Term Change: Add - New Rejection Code to the 814_28, 814_25, and 814_04 for the Name Do Not Match. Add In the BGN07 and ASI segments for the 814_28 to add Membership pending for 20 days with new code on the 814_28 also new code for both Membership and Permit Required. Add Membership code to the 814_08 transaction. Clarification needed for Bill to Name Segment of the 814_24 to provide Membership Name for MOU/EC verification of name for Move-Out customer (10/12/04) Update the approach has changed so the group felt this item was CLOSED | Closed | 2004-10-12
2004-04-01 | MOU/EC | Austin En |  | Change 820_03 to allow for a code to reference a credit pmt. | N/A | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discuss or provide any information as to the issues and possible recommendations for this item | Closed | 2004-10-12
2004-04-01 | MOU/EC | Nueces |  | Change 820-payment adjustments 6000 record to allow credits and debits in the total payment field for the batch total. | High Priority | (6/23/04) No progress yet Update 08/25/04 -Change control 2004_607 already written and approved. | Closed | 2004-10-12
2004-04-01 | MOU/EC | Austin En |  | Change 810_03 to include information on deferred payment agreements that CR has set up with customer. | N/A | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discuss or provide any information as to the issues and possible recommendations for this item (10/12/04) Update this item as Closed for discussion due to lack of information and expertise needed to provide an adequate and appropriate recommendation | Closed | 2004-10-12
2004-04-01 | MOU/EC | Austin En |  | Change 810_03 to include reasons for cancel (BIG segment): usage or monetary correction. Similar to changes that were made to 810_02. | N/A | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discuss or provide any information as to the issues and possible recommendations for this item (10/12/04) Update this item as Closed for discussion due to lack of information and expertise needed to provide an adequate and appropriate recommendation | Closed | 2004-10-12
2004-04-01 | MOU/EC | CPS |  | Why can't a 814_01 originate from the MCTDSP since customer remains with MCTDSP? | N/A | (6/23/04) No progress yet Update 08/25/04 - This was not the decision made by the Market prior to Open Competition and was not chosen to be the Current Market model. | Closed | 2004-10-12
2004-04-01 | MOU/EC | LCRA |  | With exception of PC & PD, all other 814's go through ERCOT. Since MOU/EC don't unbundled, why do 814's still need to go thru ERCOT? Same question with 867's? Since CR and TDSP functions handled at same office? | High Priority | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discuss or provide any information as to the problems, issues, and possible recommendations for this issue . This was not the decision made by the Market prior to Open Competition and was not chosen to be the Current Market model. Modifications will be made to the 650_04 transaction to allow the MOU/EC to disconnect service at customer request and/or safety issues. (10/12/04) Update Draft Change-Control written to provide 650_04 Disconnect and Reconnect along with a bi-directional 814_PC and PD transaction for the MOU/EC only - Texas SET feels this item is closed with the approval of these change controls. | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | If customer calls TDSP first, can there be an enrollment from the TDSP. Can the TDSP go ahead and set up customer? Since other city services need to be set up? -Responses - lots of discussion about scheduling power, how can you without CR, etc. | N/A | (6/23/04) No progress yet Update 08/25/04 - This was not the decision made by the Market prior to Open Competition and was not chosen to be the Current Market model. | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | Make 814_PC bi-directional. | High Priority | (6/23/04) No progress yet - Update 08/25/04 - Change control will be written to allow the 814_PC to be bi-directional only for MOU/EC Markets. Note: Need to refer to item to Mass Transition Taskforce for possible CR to CR notification of customer information for transitioning customer from one CR to another (10/12/04) Update - Draft Change Control written and discussed today - | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | In MOU/EC T&C's - city services also paid 1st, or just electricity? -ACTION ITEM - read/interpret T&C's | N/A | (6/23/04) No progress yet Update 08/25/04 - This is not a Texas SET issue | Closed | 2004-10-12
2004-04-01 | MOU/EC |  |  | More than move-in, would like to see bi-directional move-out. For forwarding of final bill, capital credits check, etc. | High Priority | (6/23/04) No progress yet Update 08/25/04 - Sponsor was not available to discuss or provide any information as to the problems, issues, and possible recommendations for this issue . (Update 08/25/04) This was not the decision made by the Market prior to Open Competition and was not chosen to be the Current Market model. Modifications will be made to the 650_04 transaction to allow the MOU/EC to disconnect service at customer request and/or safety issues. (10/12/04) Update - Draft Change Control written and discussed today for the 650_04 Requesting a MOVE-OUT transaction from the CR used by MOU/EC only | Closed | 2004-10-12
2004-05-01 |  | 810/867/824 Taskforce |  | 824 new codes | Suzette Wilburn, Kyle Patrick, Charlie Bratton, Kathy Scott to review 824 Workshop documentation and begin drafting new codes | (6/23/04) Team has not met. (8/17/04) Sub-team planning on meeting, hopefully for 8/24/04 meeting in Houston 10/12/04 - Draft Change Control written and discussed by SET | Closed | 2004-10-12
2004-05-01 | TDSP |  |  | 650_01 1 to 1 relationship | TDSPs to verify that they are responding the 650_01s on a one to one relationship and bring back at June Meeting | (6/23/04) Cary Reed to refer this to Blake Gross and Shannon Bowling (DNP/REC TF). Also change control 2003-496 should clear this issue up. (8/17/04) Cary Reed, Suzette Wilburn and Kathy Scott will work with the DNP/REC TF (10/12/04) Recommendation from DNP/RC Taskforce is to continue the change control and process one-to-one | Closed | 2004-10-12
2004-05-01 |  |  |  | 814_28 redline document MOU/EC | TX SET to document the different scenarios that would be affected by membership codes suggested for the 814_28 | (6/23/04) The TDSPs will get together along with MOU/EC to make a list of the Reasons for Pending a Move-In or Move-Out to cover the majority or the higher percentage of reasons for pending a request. Cary Reed will send an open invitation to Eloise and any other MOU/EC to a meeting scheduled on July 15, 2004 to discuss this action item. (Same as Line Item #4- need to be put together) Update 08/25/04 - Meeting held in Corpus Christi - sponsored by AEP - closed out various issues | Closed | 2004-10-12
2004-07-01 |  | TX SET Leadership |  | PRS will have their Annual Budget Priorization meeting scheduled August 27, 2004 where TX SET Leadsership will ask for a spot on this meeting's agenda. Tenative Schedule for TX SET for 2005 (4th Quarter Implementation) and a list of approved change controls that could be affect with v2.1 implementation. | Kyle Patrick, Kathy Scott and Bill Reily - TX SET Chair and Vice Chairs | Leadership attended the Annual Budget Priorization Meeting and Texas SET 2.1 has been placed as high priority for 2005 ERCOT Budget | Closed | 2004-10-12
2004-07-01 | Market |  |  | TX SET representatives will go back to their companies to review the approved gray box/example change controls and come back with any concerns for updating the guides with these approved change controls for version 2.0A release schedule |  | Change Controls for version 2.0A have been completed and agreed to by Texas SET | Closed | 2004-10-12
2004-08-17 | TDSP/MOU/EC |  |  | (6/17/2004) Initial discussion has been to change 814_28 to allow move-in to be pended because customer is not a meter of the co-op. With an interval of time expiring and 814_08s being sent for membership fees not sent to the MOU/EC - (8/17/2004) Question would MOU/EC match names for Membership fee payments? How would a MOU/EC match names on the 814_16 because these names will not always be the same as the name found in the MOU/EC database? | Cary Reed will organize a second meeting with the TDSPs and MOU/EC to discuss and flush out issues with using either the 814_28 or 814_04 transactions for membership fees and assigned membership numbers for those customers that have been established as members under the membership policies of MOU/EC. TDSPs will attempt to incorporate some of their procedures for wanting to pend transactions into the same process. The meeting minutes, discussions, and recommendations from this TX SET sub-team will be brought back to the larger TX SET membership for a decision. Meeting has been scheduled for August 25 and 26, 2004 in Corpus Christi, Texas sponsored by AEP (Cary Reed) | Sub-team meeting scheduled August 25 and 26, 2004 in Corpus Christi, Texas - Sponsored by AEP (Cary Reed) Sub-team members/participants: Bernie Dawson, Bill Reily, Eloise Flores, Cary Reed, Brett Harper, Suzette Wilburn, Kathy Scott | Closed | 2004-10-12
2004-08-17 |  | RMS |  | Update on service address comparison request. Identifying how large the issue is with regard to the service address sent on the initiating transactions and what is received on the 814_04 from the TDSPs | ERCOT completed query for the month of July-found 30,000 records- Suzette Wilburn (ERCOT) will breakout these 30,000 ESI IDs into subsets by TDSP territory to be distributed by end of next week. A sample will be taken from this sub-set to determine extent of problem and possiblitu of recommendations of the best resolution going forward. ERCOT (Suzette Wilburn) will verify street addresses for apartments/suite numbers as they are shown on the ERCOT Portal. Charlie Bratton will verify if all of Texas street addresses will utilize same assignment and criteria that is provided by 911 listings |  | Closed | 2004-10-12
2004-08-17 |  |  |  | Time Table and/or schedule for v2.1 Change Controls | Suzette Wilburn and Tom Baum (ERCOT) will work on developing a time time and/or schedule for v2.1 Change Controls, Communications, Baseline of Implementation Guides, and Posting to ERCOT web-site for updated guides |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2004-597 was marked as a graybox change. This requires adding a new code to the 814_13. Should be marked as system change |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2004-610 request additional language to the 810_02. Now tha we are removing the BPOs, we need to make sure this language was captured in the guide and discuss submitting this CC to be nullified. Charlie Bratton and Jason Bear will create a change control to add language currently found in this change control 2004-610 to the actual transaction flow page and/or graybox of appropriate data elements. |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2003-496 adds clarificatoin to the 650_02 for disconnects. TX SET will need to review the content of this change contol to determine if it is still valid. Cary Reed, Suzette Wilburn, and Kathy Scott will work with the DNP Taskforce leads to ensure that this change control is still accurate and valid to Disconnect for Non-payment processing |  | Closed | 2004-10-12
2004-08-17 |  | TX SET |  | Update Unassigned Change Control Log - Version Planning spreadsheet | CC2003-538 updates examples in the 867_03 but this is marked as a system change. Need to re-classify as gray box/example change. |  | Closed | 2004-10-12
2004-08-17 | TX SET Leadership |  |  | What is the process or procedure for Market participants to take when a Market participant is not following Market Guidelines or Rules? | TX SET Leadership has a question of RMS Leadership | (10/12/04) Kathy Scott will take request to Lon Conn and Karen Farley to add this process to the RMS Assignment Form | Closed | 2004-10-12
2004-08-25 | MOU/EC |  |  | Need to re-visit 2004_609 for Reconnect after Disconnect for Non-Payment | High Priority | 08/25/04 -Bernie Dawson will rework change control 2004_609 to apply correct ANSI standards for Reconnect processing by MOU/EC (10/12/2004) Bernie Dawson provided this change control to Texas SET and some revision were made by the team. Bernie will submit the revision change control for the Texas SET Change Control call for v2.1 Implementation | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: CR received a final read or invoice and have not received an 814_06 or sent an 814_24 TDSP COMMENTS: Valid rejection if the order (response to initiating transation) is not in scheduled status at ERCOT indicating that the TDSP has not generated the 814_04, 814_25, 814_13, to ERCOT for the gaining CR and ERCOT generated the 815_05, 814_06, 814_28 or 814_22 to the losing CR | The 810/867/824 Workshop Taskforce agreed that extending the 2 day timeframeto 5 days will fix several validations and rejcection problems created by enrollment transacations missing or delayed The agreement by the TDSPs would be the 2 day rule WILL be extended to 5 days. The 5 day rule should be officially in place by all Market participants by 10/1/2004 TX SET should re-visit the 824 rejections and reasons in six months to a year AFTER the rule has been implemented for evaluation that the problem has in fact been resolved or is minimal enough to work manually. | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: CR received a 814_08 cancel, 814_09 accept or 814_28 unexecuteable TDSP COMMENTS: Valid if the Order is in "Cancelled by Customer Objection" status at ERCOT or TDSP responds to 814_08 with an 814_09 valid rejection. Not a valid reject If the order is in scheduled status at ERCOT indicating that the TDSP has generated the 814_04, 814_25, 814_13, to the gaining CR and ERCOT has created an 815_05, 814_06, 814_28 or 814_22 to the losing CR | The 810/867/824 Workshop Taskforce agreed that extending the 2 day timeframeto 5 days will fix several validations and rejcection problems created by enrollment transacations missing or delayed The agreement by the TDSPs would be the 2 day rule WILL be extended to 5 days. The 5 day rule should be officially in place by all Market participants by 10/1/2004 TX SET should re-visit the 824 rejections and reasons in six months to a year AFTER the rule has been implemented for evaluation that the problem has in fact been resolved or is minimal enough to work manually. 09/22/04 Update: TX SET reviewed changes requested to the 824 based upon the 810/867/824 workshop spreadsheet. ERCOT will go forward to add new codes for the new gray boxes and submit the appropriate change control for the October Change Control Conference Call. | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: CR received a 814_08 cancel, 814_09 accept or 814_28 unexecuteable TDSP COMMENTS: Valid if the Order is in "Cancelled by Customer Objection" status at ERCOT or TDSP responds to 814_08 with an 814_09 valid rejection. Not a valid reject If the order is in scheduled status at ERCOT indicating that the TDSP has generated the 814_04, 814_25, 814_13, to the gaining CR and ERCOT has created an 815_05, 814_06, 814_28 or 814_22 to the losing CR | The 810/867/824 Workshop Taskforce agreed that the Stacking Solution is designed to fix this with a response driven cancel process for all cancels. TX SET should re-visit this in six months to a year AFTER stacking has been implemented for evaluation that the problem has in fact been resolved or is minimal enough to work manually. 09/22/04 Update: TX SET reviewed changes requested to the 824 based upon the 810/867/824 workshop spreadsheet. ERCOT will go forward to add new codes for the new gray boxes and submit the appropriate change control for the October Change Control Conference Call. | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | ESI ID invalid or new CR COMMENTS: Does not exist in CR database - CR has not sent or received a current enrollment transaction (814_05, 814_14, 814_22) TDSP COMMENTS: Valid Rejection if the order (response to initiating transation) is not in scheduled status at ERCOT indicating that the TDSP has generated the 814_04, 814_25, 814_13, to ERCOT for the gaining CR and ERCOT generated the 815_05, 814_06, 814_28 or 814_22 to the losing CR | The 810/867/824 Workshop Taskforce agreed that extending the 2 day timeframeto 5 days will fix several validations and rejcection problems created by enrollment transacations missing or delayed The agreement by the TDSPs would be the 2 day rule WILL be extended to 5 days. The 5 day rule should be officially in place by all Market participants by 10/1/2004 TX SET should re-visit the 824 rejections and reasons in six months to a year AFTER the rule has been implemented for evaluation that the problem has in fact been resolved or is minimal enough to work manually. 09/22/04 Update: TX SET reviewed changes requested to the 824 based upon the 810/867/824 workshop spreadsheet. ERCOT will go forward to add new codes for the new gray boxes and submit the appropriate change control for the October Change Control Conference Call. | 10/12/2004 Draft Change Control was created to provide new rejection code to providing this information | Closed | 2004-10-12
2004-08-31 |  | 810/867/824 Taskforce |  | Dates Don't Match or New CR COMMENTS: Start Read Date cannot be greater than 180 days prior to date of receipt on an invoice or meter read. Pending PUC Rule TDSP COMMENTS: Defer pending Customer Protection adoption: Exceptions identified: 1). inadvertent switches,(2) back office clean-up and (3), tampering situations may allow dates inexcess of 180 days | For inadvertent switches, the Inadvertent switch task force will handle the resolution. Remainder should be deferred and governed by the PUC ruling around this issue Re-evaluate after MIMO implementation 09/22/04 Update: TX SET reviewed changes requested to the 824 based upon the 810/867/824 workshop spreadsheet. ERCOT will go forward to add new codes for the new gray boxes and submit the appropriate change control for the October Change Control Conference Call. | 10/12/2004 Draft Change Control was created to provide new rejection code completing this action item | Closed | 2004-10-12
2004-07-01 | TDSP | RMS |  | TDSPs look at the reasons why estimations are being created, if reason is flagged into any internal systems? What are some of the options for CRs when consecutive estimates are encountered? Discussion was to consider a new segment in the 867_03 and 867_04 transactions to indicate reasons for estimation. | 09/22/04 Update: Sub-team was asked by Texas SET to add general guidelines in the event of a estimated usage for both CR and TDSP . This information will be brought back to the October TX SET meeting and possibly presented at the October/November RMS | (10/12/04) Update - Bill Reily will be placed on the November 2004 Texas SET agenda to discuss the recommendations of the subteam to Texas SET (11/17/04) - Closed, TX SET will discuss further adding a reason code for estimations | Closed | 2004-11-17
2004-07-01 |  | DEWG |  | Linked ESI ID issue- TX SET needs to determine how the TDSPs use the address field in the 814_04, is it echoed back from the 814_03 or do they pull the actual service address from their systems. Note: Where requirements are identified for flushing out and developing should go back to RMS for update. TDSPs have the most accurate informatoin regarding the ESI ID so if they have an address tat is different from what was sent on the initiating transaction and/or exists on the portal, this should be the address that is followed, however before TX SET agrees to amkde a change to the 814_04 transaction they would like to know if any statistics can be gathered on how many discrepancies exist | ERCOT will look into whether this type of information can be obtained | (8/17/2004) Update will be provided to TX SET at the September Meeting - Plan is to take a sample of July's 814_04 to determine where the problems may be initiated (10/12/04) Update - Meeting will be arranged with ERCOT and TDSPs prior to the November 2004 Texas SET meeting to create recommendations to bring back to Texas SET for discussion (11/17/2004) Closed | Closed | 2004-11-17
2004-09-22 |  | ERCOT |  | There has been 867_03F showing up on the ERCOT 867 Error Report that is sent to the CRs and TDSPs that have the same date in the DTM150 and DTM151 segments | ERCOT would like to find out what type of scenario would cause this and let the market know that ERCOT is not loading this data, and it doesn't appear that corrected usage was sent | 11/17/2004 Tom Baum reviewed with the group that the TDSPs who were identified as sending the same date in the start and stop time segments. All TDSPs had identified that 867s sent were sent in error and were corrected. TX SET agrees that Start and Stop dates cannot be the same. | Closed | 2004-11-17
2004-09-22 | MOU/EC | Eloise Flores |  | MOU/EC will need a way to identify the membership number in all EDI Transactions | Change control will need to be written to apply to all EDI transaction to add a new REF Segment (REF~1W) for all EDI transactions that will be used to pass the membership number | (11/17/2004) Closed | Closed | 2004-11-17
2004-09-22 |  | ERCOT |  | Change Control 2004-636 Withdrawn Written to remove the Business Process Overview (BPO) from the 814_20 Implementation Guide and add necessary contents from the BPO to the segments it pertains to. Also, update the REF~TD name for "Reason for Change" to "Description of Change" | Suzette Wilburn and Johnny Robertson will work together to provide a revised change control to remove the BPO from the 814_20 Implementation Guide. | (11/17/2004) Closed- Suzette and Johnny will submit Change Control for approval | Closed | 2004-11-17
2004-09-22 | TDSP | ERCOT |  | How do TDSPs communicate a meter removal on an 867_03? Can ERCOT expect to receive a DTM150 and a DTM 151 on every 867? If not, in what instance would an 867 be sent where either the DTM150 or DTM151 was not present | TX SET representatives will check to see if sending a DTM150/DTM 151 with the same date is valid | 11/17/2004 - Change control already written to clarify this process, also currently ERCOT has removed validation process or SIR that rejected these scenarios until this change control is implemented | Closed | 2004-11-17
2004-09-22 | ERCOT | TX SET |  | TX SET requested and required that TX SET be involved in defining the requirements that are used to write the ERCOT SIRs. | ERCOT (Suzette Wilburn) noted that they would include TX SET when writing the requirements and text for the SIRs prior to them being implemented. TX SET also discussed the need for TX SET involvement in the Retail Market Call for those instances when an SIR has been written that requires discussion by TX SET on the change being requested. ERCOT agreed to monitor the changes being written internally for potential business process changes to the market and will bring those requests to TX SET for agreement on the requirements | 11/17/2004 Closed action item and this information will be added to our Working Group Procedures documentation | Closed | 2004-11-17
2004-10-12 |  | Direct Energy |  | Reject for Original Tracking Number from the originating transaction be provided on the 867-03 Final to provide issuing the 824 Reject transaction | Rita Morales will work with Suzette Wilburn to examine some real instances that apply to this scenario for ERCOT investigation and for Direct to provide some information to other CRs on how they are handling this particular scenario. | (11/17/2004) Closed by Rita Morales | Closed | 2004-11-17
2004-10-12 | Texas SET | ERCOT |  | Request from ERCOT to investigate the FasTrak Inadvertant issue | Texas SET Sub-team will work to investigate ERCOT's recommendations: Kyle Patrick, Suzette Wilburn, Charlie Bratton, Cary Reed, Tom Baum, Rob Bevill, Johnny Robertson, Kathy Scott | (11/17/2004) Closed | Closed | 2004-11-17
2004-10-12 |  |  |  | Change Control 2004-644 Removed the Transformer Loss Adjustment codes TA-TE to approve Change Control | TDSPs will need to discuss that if these codes are necessary for the 810 Billing Determinants - CRs will complete and internal evaluation as well. If it is found to be of value by either side then a change control will be prepared for November 2004 Change Control Conference Call | (11/17/2004) Closed and if needed a new change control will be written to submit to Texas SET adding the Transformer Loss Adjustment codes | Closed | 2004-11-17

## Unassigned Change Controls
Change Controls
| Approved | Transactions | Version | Scope | TX SET Version | Description | Notes
pending | pending | 810 |  | System | TBD | Potential 810 - 867 billing determinants changes
pending | pending | 810_02 |  | System | TBD | allow TDSP to send single corrected invoice for non-IDR meters
2-466 | Y | 650_04 | Future | System | TBD | Add code to 650_04 provide means to alert CR that service has been permanently suspended for ESI ID and numerous gray box changes | Valid per TX SET review 3/24/04
2-468 | Y | 810_03 | Future | System | TBD | Multiple 810_03 changes - code gray box | Valid per TX SET review 3/24/04
3-471 | Y | 650_04 | Future | System | TBD | remove must use from the YNQ04 of the NQ~5U segment | Valid per TX SET review 3/24/04
3-490 | Y | 814_14, 814_22 | Future | Gray Box/Examples | TBD | remove QTR from valid values of Meter Type from the gray box | Valid per TX SET review 3/24/04
3_493 | Y | 814_27 | Future | System | TBD | Make the N1~8S OPTIONAL on the 814_27 to be consistent with the 814_26 N1~8S loop | Valid per TX SET review 3/24/04
3_496 | Y | 650_02 | Future | System | TBD | Provide additional detail on when 650_02 should be generated and how the process should work for disconnect and reconnect for non-pay | Re-evaluate-Jennifer Teel, Bill Reily, Kathy Scott. CC was referred to Shannon Bowling and Blake Gross of Disco Reco TF.
3_497 | Y | 814_PD | Next Release | System | TBD | Remove "Zip" from the REF02 of the REF~7G segment (Rejection Reason) | Re-evaluate for validity (497, 498, 574, 596)
3_498 | Y | 814_PC | Next Release | System | TBD | Clean up of the 814_PC | Re-evaluate for validity (497, 498, 574, 596)
3-503 | Y | 810_02 | Future | System | TBD | allow TDSP to send single corrected invoice for IDR meters | Valid per TX SET review 3/24/04
3_517 | Y | 814_28 | Future | System | TBD | Adding to reasons for "Complete Unexecutable" | Valid per TX SET review 3/24/04
3_527 | Y | 650_02 | Future | System | TBD | Adding to reasons for "Complete Unexecutable" | Valid per TX SET review 3/24/04
3_532 | Y | 814_04 and 05 | Future | System | TBD | 814_04 and 05 needs a Meter Ownership Type code to eliminate gap when customer chooses competitive meter to notify new REP when switching | Valid per TX SET review 3/24/04
3_569 | Y | Entire 814 series 01-29, PC and PD | Future | System | TBD | Provide gray box clarification to the LIN segment to indicate that the Texas Market supports only 1 LIN loop per SDI Transaction | Valid per TX SET review 3/24/04
3_571 | Y | 814_09 and 814_13 | Future | Gray Box/Examples | TBD | Move segment gray box verbiage for A78 being used only by ERCOT and TDSP to gray box on actual code | Valid per TX SET review 3/24/04
3_572 | Y | 814_13 and 814_02 | Future | Gray Box/Examples | TBD | Add short title "Earliest Available Switch Date" to the EAS Reject code (REF*7G) | Re-evaluate
3_576 | Y | 814_20 | Future | System | TBD | Meter Exchange/Profile Information | Re-evaluate
3_578 | Y | 814_20 | Future | System | TBD | Added a new change code to indicate the annual Load Profile changes | Valid per TX SET review 3/24/04
3_582 | Y | 814_08 | Future | System | TBD | Add B30 - MIMO change | Valid per TX SET review 3/24/04
3_590 | Y | 814_21 | Future | System | TBD | Add code for ERCOT generated reject | Valid per TX SET review 3/24/04
4-596 | Y | 814_PC | Future | TBD | TBD | Clarify timing to use transaction | Re-evaluate for validity (497, 498, 574, 596)
4-597 | Y | 814_13 | Future | System | TBD | MIMO clean up | Valid per TX SET review 3/24/04
4-601 | Y | 814_13 | Future | System | TBD | Add new reject code "ICD" MIMO | Valid per TX SET review 3/24/04
2004-604 | Y | 814_09, 814_13, 814_25 | Future | System | TBD | The gray boxes in CC2003-400 were written such that the ‘OA’ code will be sent on every response from the TDSP, reject or accept. This needs to be changed to only send the ‘OA’ code on rejects to be consistent with CC2003-401, which is the same change for the 814_11. | Recently approved by Texas SET
2004-607 | Y | 820_03 | Future | System | TBD | changes to the 820_03 transaction are needed to add data elements/segments to accommodate payment adjustments to the CR when payments are adjusted on the customer’s Muni-Co-op account due to being applied to an incorrect account, for the wrong amount, or in the case of a returned check | Recently approved by Texas SET
2004-615 | Y | 650_01 | Future | System | TBD | Need to expand the message text in the MTX segment from 80 characters to 255 characters | Recently approved by Texas SET
2004-616 | Y | 814_11 | Future | System | TBD | Add ‘SBD’ Reject code to the 814_11 | Recently approved by Texas SET
2004-624 | Y | 650_02 | Future | System | TBD | Remove Businesss Process Overviews from the Implementation Guides and incorporate that logic into the graybox or data element itself of the Implementation guideline | Approved on 8/18/04 by Texas SET
2004-627 | Y | 820_02 | Future | Gray box/Examples | TBD | Remove Businesss Process Overviews from the Implementation Guides and incorporate that logic into the graybox or data element itself of the Implementation guideline | Approved on 8/18/04 by Texas SET
2004-629 | Y | 650_01 | Future | System | TBD | Update the 650_01 YNQ (Premium Disconnect Location) YNQ09 PDL graybox and add 2 additional codes in the YNQ09 to give the TDSO clear instructions as to what charges the CR has agreed to pay for Reconnect following Disconnect for non-payment | Approved on 8/18/04 by Texas SET
2004-631 | Y | 814_04 | Future | System | TBD | Remove the A75 reject code on the 814_04 as it is no longer needed | Approved on 8/18/04 by Texas SET
2004-632 | Y | 814_24 | Future | System | TBD | Add a new code to the REF~1P status reason segment in the 814_24 that will be used by CRs when submitting a second MVO that will communicate to the TDSP second request for MVO and disconnect service. | Approved on 8/18/04 by Texas SET
2004-633 | Y | 867_03 | Future | Gray box/Examples | TBD | Update graybox in the PTD-PL, PTD-BO, and PTD-PM loops to include multiple meter exchange examples in one service period. | Approved on 8/18/04 by Texas SET
2004_635 | Y | 810_02 | Future | System | TBD | Add (6) New SAC04 codes to the 810 Invoice transaction for new tariffs- transition charges and/or charge off allowances to be appropriately identified with the invoice transaction. | Approved on 8/18/04 by Texas SET
2004-639 | N | 824 | Future | System | TBD | Add two codes to the existing approved reject codes for 824. | Approved 9/22/04 with modifications by Texas SET
2004-642 | N | 814_08, 814_09 | Future | System | TBD | Update the 814_08/814_09 IG transaction flow to indicate the 814_08 can be used to cancel a drop to AREP | Approved 10/12/04 by TX SET
2004-643 | N | 820_02 | Future | Gray Box/Examples | TBD | Update the 820_02 IG to provide clarification on how decimals are used in the BPR02 & RMR04. | Approved 10/12/04 by TX SET
2004-644 | N | 810_02 | Future | System | TBD | Update SAC09 code list for the Billing Determinants | Approved 10/12/04 by TX SET
2004-645 | N | 824 | Future |  |  | Additional Codes added to the TED Segment and grayboxes updated in the 824 per the 810/867 Workshop | Approved 11/17/04
2004-646 | N | 814_18 | Future |  |  | Add the REF~BLT (Billing Type) segment to the 814_18 in order to support multiple billing types in MOU/EC territory. Also update examples to include this required segment. | Approved 11/17/04
2004-647 | N | ALL | Future |  |  | Add clarity on the ANSI definition of Alpha numeric is the 52 upper and lower case letters in the English alphabet. TX SET requires that all alphas be Upper case which limits this to 26 characters, which does not include the use of the special characters above letters such as ~, or `, etc | Approved with Modifications 11/17/04
2004-649 | N | 814_01, 814_03, 814_04, 814_05, 814_08, 814_10, 814_14, 814_16, 814_24, 814_PC, 650_01 | Future |  |  | Add membership ID to numerous TX SET transactions to support Muni/Co-op business requirement to positively match all move-in, move-out, and switch requests to an existing MCTDSP membership/account. | Approved 11/17/04
2004-650 | N | 814_PC, 814_PD | Future |  |  | Make 814_PC and 814_PD transactions bi-directional to allow MCTDSP to send updated customer information to the CR and to allow CR to respond to MCTDSP. In the MOU/EC market, the MCTDSP will be doing consolidated billing unless the customer requests dual billing. The MCTDSP is more likely to have current billing information for the customer and needs to be able to send updated customer information to the CR. | Approved 11/17/04
2004-651 | N | 814_02, 814_04, 814_05, 814_09, 814_11, 814_15, 814_17, 814_25, 814_PD, 650_02 | Future |  |  | Membership ID is required in the MOU/EC market to positively match all move-in, move-out, and switch requests to an existing MCTDSP membership/account. MCTDSP must be able to reject an initiating request if there is no membership ID or there is no ID match with current MOU/EC accounts. | Approved 11/17/04
2004-652 | N | 650_04 | Future |  |  | Add a new suspension code for use in the MOU/EC market to provide the MCTDSP a way to notify the CR that the retail customer has requested a permanent disconnect and final bill. The new code in the 650_04 should prompt the CR to send an 814_24 for the ESI ID. This code will only be used for ESI IDs within a MOU/EC service territory. | Approved 11/17/04
2004-653 | N | 650_04 | Future |  |  | Add new Action codes (BGN08) for use in the MOU/EC market to provide the MCTDSP a way to notify the CR that a customer disconnected by MCTDSP for non-payment has been reconnected. This code will only be used for ESI IDs within a MOU/EC service territory. | Approved 11/17/04

## Trx Description Card
TEXAS SET VERSION 2.0 |  |  | 650* | Maintenance Service Order - Work Orders, Meter Config. Details, Outage Notification
814 - Request, Response, Maintenance for Enrollments, Drops, Switches, Maintenance & Request Consumption
Trx | Definition | Flow | Trx | Definition | Flow
814_PC | Maintain Customer Information Request | CR=>TDSP | 650_01 | Basic Service Order | CR=>TDSP
814_PD | Maintain Customer Information Response | TDSP=>CR
814_01 | Enrollment Request | CR=>ERCOT | 650_02 | Service Order Complete Response | TDSP=>CR
814_02 | Enrollment Reject Response | ERCOT=>CR | 650_04 | Suspension of Delivery Svc Notification or Cancellation | TDSP=>CR
814_03 | Switch CR Notification Request | ERCOT=>TDSP
814_04 | Switch CR Notification Response | TDSP=>ERCOT | 650_05 | Suspension of Delivery Service Reject Response | CR=>TDSP
814_05 | Premise Info & Enrollment Response | ERCOT=>CR
814_06 | Drop Due to Switch Request | ERCOT=>CR | *The 650_03 functionality was distributed amongst the other 650 transactions.
814_07 | Drop Due to Switch Response | CR=>ERCOT
814_08 | Cancel Switch Request | CR=>ERCOT | 810 - Statement, Settlement, Wire Charge Invoices
|  | ERCOT=>CR | 810_02 | Wires Charge/Service Order Charge Invoice | TDSP=>CR
ERCOT=>TDSP
814_09 | Cancel Switch Response | ERCOT=>CR | 810_03 | Muni/Coop Invoice | CR=>MCTDSP
CR=>ERCOT
|  | TDSP=>ERCOT | 820 - Payment and Advice through Bank
814_10 | Drop to AREP Request | CR=>ERCOT | 820_02 | CR Remittance Advice | CR=>TDSP
814_11 | Drop to AREP Response | ERCOT=>CR
814_12 | Move-In/Move-Out Dte Chg Request | CR=>ERCOT | 820_03 | Muni/Coop Remittance Advice | MC TDSP=>CR
ERCOT=>CR
|  | ERCOT=>TDSP | 824 - Reject Response to 810 or 867 Data - O
814_13 | Move-In/Move-Out Dte Chg Response | ERCOT=>CR | 824 | Application Advice | CR=>TDSP
|  | CR=>ERCOT |  |  | CR=>ERCOT
|  | TDSP=>ERCOT |  |  | ERCOT=>TDSP
814_14 | AREP Enrollment Request | ERCOT=>AREP | 867-Interval, Non Interval, Reads & Consumption Data Historical and Monthly Activity
814_15 | AREP Enrollment Response | AREP=> ERCOT
814_16 | Move-In Request | CR=>ERCOT | 867_02 | Historical Usage | TDSP=>ERCOT
814_17 | Move-In Reject Response | ERCOT=>CR |  |  | ERCOT=>CR
814_18 | Establish/Delete CSA CR Request | CR=>ERCOT | 867_03 | Monthly Usage | TDSP=>ERCOT
|  | ERCOT=>TDSP |  |  | ERCOT=>CR
814_19 | Establish/Delete CSA CR Response | ERCOT=>CR | 867_04 | Initial Meter Read Notification | TDSP=>ERCOT
|  | TDSP=>ERCOT |  |  | ERCOT=>CR
814_20 | Create/Maintain/Retire ESI ID Request | TDSP=>ERCOT
ERCOT=>CR
814_21 | Create/Maintain/Retire ESI ID Response | ERCOT=>TDSP
CR=>ERCOT
814_22 | CSA CR Move-In Request | ERCOT=>CR
814_23 | CSA CR Move-In Response | CR=>ERCOT
814_24 | Move-Out Request | CR=>ERCOT
ERCOT=>TDSP
814_25 | Move-Out Response | ERCOT=>CR
TDSP=>ERCOT
814_26 | Ad-Hoc Historical Usage Request | CR=>ERCOT
ERCOT=>TDSP
814_27 | Ad-Hoc Historical Usage Response | ERCOT=>CR
TDSP=>ERCOT
814_28 | Completed Unexecutable or Permit Required | TDSP=>ERCOT
ERCOT=>CR
814_29 | Response Completed Unexecutable or Permit Required - O | ERCOT=>TDSP
CR=>ERCOT