## Slide 1: Project Updates to DEWG
Jackie Ashbaugh
ERCOT
March 10, 2005

## Slide 2
Project Priority List (PPL) Information
ERCOT PPL posted at:
  http://www.ercot.com/ProtocolRevisions/SCRRevfilesystem.cfm?action=viewfolder&path=../ercotpublicweb/market/ftp/SystemChangeRequests/Project_Priority_List
    … or …
  www.ercot.com / Protocols / System Change Requests / Project Priority List

## Slide 3
Objectives:
Define and implement a website layout that enables users to find key information efficiently
Develop a process to ensure the sustainability of the investment in the enhancements
Scope:
Search engine functionality (including metadata strategy)
Improve navigation - create a new information architecture for the site (task driven focus)
Content owners can post updates easily – content manager
Process for maximizing the use of key real estate for critical and timely information
All information and processes are maintained after the redesign
Project Objectives / Scope
Summary of Project Status
PR-40106 ERCOT.com
Phase:
Initiation – completed in Sept ‘04
Planning – in progress
Execution – goal mid March ’05
Closing – goal July ‘05
Recent:
Vendor delivered ‘Solution Definition’ recommendations
Next steps:
Project plan w/resource allocation
Prepare to update Directors on Planning phase activities
Prepare to enter next phase (Execution)
** All target dates – will have firm dates after project plan is completed
Requirements (pens down) – early March ’05
Design (published document) – mid March ’05
Testing – late April ’05
Training – May ’05
Production (Go live) – June - July ‘05
High level timeline
Bus Lead: Scott Egger ph. 512-248-3162
PPL: Source: ERCOT Priority: 1.1 Rank: 24 Program Area: RO
What prompted the project:
  Market Survey
  TML Phase II Mid-Term Requirements
  Strategic Fit
Supporting business drivers:
  Data from the Market Survey strongly encouraged the implementation of a search engine
  Peer website comparisons between the other ISOs
  Practical usage feedback
Additional Information
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4
Objectives:
Main 1: Transition of full functionality of SCR727 extracts from the Data Archive to the ODS/EDW
Main 2: Addition of the capability for new market participants to request and receive an “initial” SCR727 ESIID extract for dimensional tables
Main 3: Addition of the capability for a separate data extract for the dimensional tables that are reused throughout all Lodestar extracts
Main 4: Inclusion of a unique file load order number in the extract file names which will identify the order in which SCR727 files should be loaded by the market participant
Project Objectives / Scope
Summary of Project Status
Phase:
Initiation – Completed in Feb ‘05
Planning – Scheduled to complete by Apr ‘05
Execution – Starting Apr ’05
Implementation – TBD
Closing – TBD
Recent:
Developing Planning Documentation
Next steps:
Prepare to enter next phase (Execution)
Start developing detailed design
All target dates will become firm after design is complete and project plan finalized
Requirements – Feb/Mar ’05
Design– Apr/May ’05
Internal Testing – TBD in Planning
External Testing – N/A
Internal Training – TBD in Planning
External Training – TBD in Planning
Production – TBD in Planning
High level timeline
Bus Lead: Jackie Ashbaugh
PPL: Source: Market Priority: 1.1 Rank: 13 Program Area: MO
What prompted the project:
  SCR 727
Supporting business drivers:
Transition all Lodestar extracts to be created in the ODS/EDW environment
Dependencies:
Lodestar ODS Stabilization
Data Delivery Module
Additional Information
PR-40007 SCR 727 Phase II
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
Day Number | Day Extract is Produced and Published | Point in Time Extract is produced for | Range of time from which net changes will be determined
1 | Monday | Saturday, 5:30 PM | Friday 5:30:01 PM – Saturday 5:30:00 PM
2 | Tuesday | Sunday, 5:30 PM | Saturday 5:30:01 PM – Sunday 5:30:00 PM
3 | Wednesday | Monday, 5:30 PM | Sunday 5:30:01 PM – Monday 5:30:00 PM
4 | Thursday | Tuesday, 5:30 PM | Monday 5:30:01 PM – Tuesday 5:30:00 PM
5 | Friday | Wednesday, 5:30 PM | Tuesday 5:30:01 PM – Wednesday 5:30:00 PM
6 | Saturday | Thursday, 5:30 PM | Wednesday 5:30:01 PM – Thursday 5:30:00 PM
7 | Sunday | Friday, 5:30 PM | Thursday 5:30:01 PM – Friday 5:30:00 PM
PR-40007 SCR 727 Phase II
Extract Timing Change Recommendation:
To allow for outages and system issues
To produce ESIID Extract in line with Load, Generation and Settlements & Billing Extracts

## Slide 6
Objectives:
Usage for Backdated LSE Relationship Changes will be provided to the appropriate CR.
A file name or number in order to identify the order in which SCR727 files should be loaded by the MP.
Auditing capability to allow MPs the function to confirm the accuracy of their extracts, including creation of initial extracts for MPs.
Ability to link a database change back to the source of the change (i.e. FasTrak issue, batch processing). (not implementing with this project)
Web Service. (Final Solution for project requirements)
Project Objectives / Scope
Summary of Project Status
Phase:
Initiation – Completed in Feb ‘05
Planning – Mar/Apr ‘05
Execution – TBD
Implementation – TBD
Closing – TBD
Recent:
Preliminary meetings
Gather market technical requirements information
Next steps:
Start developing business requirements and conceptual design
All target dates will become firm after design is complete and project plan finalized
Requirements – Mar/Apr ’05
Design– TBD in Planning
Internal Testing – TBD in Planning
External Testing – N/A
Internal Training – TBD in Planning
External Training – TBD in Planning
Production – TBD in Planning
High level timeline
Bus Lead: Jackie Ashbaugh
PPL: Source: Market Priority: 1.2 Rank:33 Program Area: MO
What prompted the project:
  SCR 727
Supporting business drivers:
Promote market participant research on ESIID level data used in data aggregation/settlements
Additional Information
PR-50024 Enhancements to SCR 727
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Project Objectives / Scope
Summary of Project Status
Phase:
Initiation – Completed in Feb ‘05
Planning – March 14, 2005
Execution – Starting August ’05
Implementation – Goal December ‘05
Closing – Starting December ‘05
Recent:
Meeting with Market Participants on Thursday, February 24th to discuss project timeline and requirement prioritization
Next steps:
Prepare to enter next phase (Planning)
Start developing detailed business requirements
Select enhancement method (upgrade current tool, Siebel or AIM)
All target dates will become firm after design is complete and project plan finalized
Requirements (pens down) – May/June ’05
Design (published document) – June/July ’05
Internal Testing – August/November ’05
External Testing – August/November ‘05
Internal Training – November/December ’05
External Training – November/December ‘05
Production (Go live) – December ‘05
High level timeline
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: sdegger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8
Project Priority List (PPL)
Questions?