## Slide 1: Project Updates to DEWG
Jackie Ashbaugh
ERCOT
April 14, 2005

## Slide 2
Project Priority List (PPL) Information
ERCOT PPL posted at:
  http://www.ercot.com/ProtocolRevisions/SCRRevfilesystem.cfm?action=viewfolder&path=../ercotpublicweb/market/ftp/SystemChangeRequests/Project_Priority_List
    … or …
  www.ercot.com / Protocols / System Change Requests / Project Priority List

## Slide 3
Project Updates
PR 50007 - FasTrak
PR 40106 - ERCOT.com
PR 30026 - EPS Meter Data Extract/Resource ID Extract – no updates
PR 50024 - SCR 740 Web Service for ESIID data
PR 40007 - SCR727 move from Data Archive to ODS
2005 Upcoming Projects
TBD
Necessary Project Updates?
PR 40042_04 - Lodestar ODS – brief update included
PR 40042_06 - Lodestar Batch Extracts
PR 50005 - EMMS Reports/Extracts
Projects
ERCOT Project Updates
As of April 4, 2005
Page 1
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
Siebel upgrade – only if Siebel is chosen as the replacement tool for FasTrak
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of April 4, 2005
Page 1
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
Phase:
Initiation – Completed in Feb ‘05
Planning – March 14, 2005
Execution – Starting August ’05
Implementation – Goal December ‘05
Closing – Starting December ‘05
Recent:
Developing process diagrams & an “as is” document with internal users
Next steps:
Meet with MPs in April to verify process flows
Start finalizing detailed requirements, after process diagrams completed
Meet with MPs in May to finalize detailed business requirements
Select enhancement method (upgrade current tool, Siebel or AIM)
Summary of Project Status
As of April 4, 2005
Page 2
PR-50007 Enhancements to FasTrak
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
** All target dates will become firm after design is complete and project plan finalized
Requirements – June ’05
Design (published document) – July ’05
Internal Testing – August/November ’05
External Testing – August/November ‘05
Internal Training – November/December ’05
External Training – November/December ‘05
Production (Go live) – December ‘05
High level timeline
As of April 4, 2005
Page 3
PR-50007 Enhancements to FasTrak
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
As of April 4, 2005
Page 4
PR-50007 Enhancements to FasTrak
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8
Objectives:
Define and implement a website layout that enables users to find key information efficiently
Develop a process to ensure the sustainability of the investment in the enhancements
Scope / Why is this important?:
Search engine functionality (including metadata strategy)
Improve navigation - create a new information architecture for the site (task driven focus)
Content owners can post updates easily – content manager
Process for maximizing the use of key real estate for critical and timely information
All information and processes are maintained after the redesign
Dependencies:
None at this time
Project Objectives / Scope / Dependencies
PR-40106 ERCOT.com
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9
Phase:
Initiation – completed in Sept ‘04
Planning – in progress
Execution – goal April/May ’05
Closing – goal October/November ‘05
Recent:
Final stages of vendor selection
Next steps:
Prepare to update Directors on Planning phase activities
Prepare to enter next phase (Execution)
Summary of Project Status
PR-40106 ERCOT.com
Notes: <number>
<footer>
<header>
<date/time>

## Slide 10
** All target dates – will have firm dates after project plan is completed
Requirements (pens down) – April/May ’05
Design (published document) – May/June ’05
ERCOT Testing – October ’05
Market Testing – October ‘05
Training – October/November ’05
Production (Go live) – October/November ‘05
High level timeline
PR-40106 ERCOT.com
Notes: <number>
<footer>
<header>
<date/time>

## Slide 11
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: ERCOT Priority: 1.1 Rank: 24 Program Area: RO
What prompted the project:
  Market Survey
  TML Phase II Mid-Term Requirements
  Strategic Fit
Supporting business drivers:
  Data from the Market Survey strongly encouraged the implementation of a search engine
  Peer website comparisons between the other ISOs
  Practical usage feedback
Additional Information
PR-40106 ERCOT.com
Notes: <number>
<footer>
<header>
<date/time>

## Slide 12
Objectives/Scope:
Main 1: Transition of full functionality of SCR727 extracts from the Data Archive to the ODS/EDW
Main 2: Addition of the capability for new market participants to request and receive an “initial” SCR727 ESIID extract for dimensional tables
Main 3: Addition of the capability for a separate data extract for the dimensional tables that are reused throughout all Lodestar extracts
Main 4: Inclusion of a unique file load order number in the extract file names which will identify the order in which SCR727 files should be loaded by the market participant
Dependencies:
Lodestar ODS Stabilization - minimal issues found and corrected during stabilization. 60 days end on Monday 4/18/2005.
Data Delivery Module - went live in December, loss of resources required replanning activities.
Project Objectives / Scope / Dependencies
PR-40007 SCR 727 Phase 2
Notes: <number>
<footer>
<header>
<date/time>

## Slide 13
Phase:
Initiation – Completed in Feb ‘05
Planning – Completed Apr ‘05
Execution – Started Apr ’05
Implementation – TBD
Closing – TBD
Recent:
Entered Execution Phase
Next steps:
Start developing detailed design and analytical design
Summary of Project Status
PR-40007 SCR 727 Phase 2
Notes: <number>
<footer>
<header>
<date/time>

## Slide 14
** All target dates will become firm after design is complete and project plan finalized
Requirements – Feb/Mar ’05
Design– Apr/May ’05
Internal Testing – June ’05 through Implementation
External Testing – N/A
Internal Training – Prior to Implementation
External Training – Prior to Implementation
Production – Late Q3 ’05/Early Q4 ‘05
High level timeline
PR-40007 SCR 727 Phase 2
Notes: <number>
<footer>
<header>
<date/time>

## Slide 15
Bus Lead: Jackie Ashbaugh
EAA Data Management
PPL: Source: Market Priority: 1.1 Rank: 13 Program Area: MO
What prompted the project:
  Implementation of ERCOT ODS/EDW environment
  Future decommission of the Lodestar Data Archive
Supporting business drivers:
Transition all Lodestar extracts to be created in the ODS/EDW environment
Additional Information
PR-40007 SCR 727 Phase 2
Notes: <number>
<footer>
<header>
<date/time>

## Slide 16
Day Number | Day Extract is Produced and Published | Point in Time Extract is produced for | Range of time from which net changes will be determined
1 | Monday | Saturday, 5:30 PM | Friday 5:30:01 PM – Saturday 5:30:00 PM
2 | Tuesday | Sunday, 5:30 PM | Saturday 5:30:01 PM – Sunday 5:30:00 PM
3 | Wednesday | Monday, 5:30 PM | Sunday 5:30:01 PM – Monday 5:30:00 PM
4 | Thursday | Tuesday, 5:30 PM | Monday 5:30:01 PM – Tuesday 5:30:00 PM
5 | Friday | Wednesday, 5:30 PM | Tuesday 5:30:01 PM – Wednesday 5:30:00 PM
6 | Saturday | Thursday, 5:30 PM | Wednesday 5:30:01 PM – Thursday 5:30:00 PM
7 | Sunday | Friday, 5:30 PM | Thursday 5:30:01 PM – Friday 5:30:00 PM
Extract Timing Change for SCR 727:
To allow for outages and system issues
To produce ESIID Extract in line with Load, Generation and Settlements & Billing Extracts
PR-40007 SCR 727 Phase 2

## Slide 17
Objectives/Scope:
Usage for Backdated LSE Relationship Changes will be provided to the appropriate CR.
A file name or number in order to identify the order in which SCR727 files should be loaded by the MP.
Auditing capability to allow MPs the function to confirm the accuracy of their extracts, including creation of initial extracts for MPs.
Ability to link a database change back to the source of the change (i.e. FasTrak issue, batch processing). (not implementing with this project)
Web Service (Final Solution for project requirements)
Dependencies:
Lodestar ODS Stabilization
Data Delivery Module
Project Objectives / Scope / Dependencies
PR-50024 Enhancements to SCR 727
Notes: <number>
<footer>
<header>
<date/time>

## Slide 18
Phase:
Initiation – Completed in Feb ‘05
Planning – May ‘05
Execution – June ‘05
Implementation – TBD
Closing – TBD
Recent:
Extended Planning to obtain BOD approval for project budget (May ’05)
Continue to gather market requirements
Business requirements complete
Next steps:
Complete development of conceptual design
Start development of analytical and detailed design
Summary of Project Status
PR-50024 Enhancements to SCR 727
Notes: <number>
<footer>
<header>
<date/time>

## Slide 19
** All target dates will become firm after design is complete and project plan finalized
Requirements – Apr ‘05
Design– July ‘05
Internal Testing – July ’05 through Implementation
External Testing – N/A
Internal Training – Prior to Implementation
External Training – Prior to Implementation
Production – Q1 ‘06
High level timeline
PR-50024 Enhancements to SCR 727
Notes: <number>
<footer>
<header>
<date/time>

## Slide 20
Bus Lead: Jackie Ashbaugh
EAA Data Management
PPL: Source: Market Priority: 1.2 Rank: 33 Program Area: MO
What prompted the project:
  SCR 727
Supporting business drivers:
Promote market participant research on ESIID level data used in data aggregation/settlements
Additional Information
PR-50024 Enhancements to SCR 727
Notes: <number>
<footer>
<header>
<date/time>

## Slide 21
Recent:
230 + million data transactions have successfully flowed between Production Lodestar, Lodestar Replicated Source System and Lodestar ODS
Few Issues encountered throughout the stabilization period (Feb ’05 – Apr ’05); All issues resolved through appropriate vendors
Zero data loss encountered throughout the stabilization period
Next steps:
Transition Lodestar extracts to the Lodestar ODS environment
Summary of Project Status
PR-40042_04 Lodestar ODS
Notes: <number>
<footer>
<header>
<date/time>

## Slide 22
ERCOT Project Updates
Questions?