2006 Capital Budget Timeline

| April 14th | Distribute 2005 unfunded market project list to PRS |
| --- | --- |
| April 22nd | Project Prioritization Overview at WMS |
| April 26th | Project Prioritization Overview at COPS |
| April 29th | Updated templates (including Cost / Benefit Analysis) provided to subcommittee leads and ERCOT CARTs by PMO |
| May 2nd | Special PRS meeting to discuss unfunded projects on 2005 project list; make recommendation to subcommittees; assess project necessity under current and future market structure |
| May 2nd – 12th | Initial review and ranking of ERCOT requests |
| May 5th | Project Prioritization Overview at TAC |
| May 10th | Project Prioritization Overview at RMS |
| May 11th | Distribute market project lists to subcommittees (WMS, COPS, RMS, ROS) |
| May 12th | Project Prioritization Overview at ROS |
| May 13th – 25th | ERCOT to complete descriptions and Cost Benefit Analysis by Requestors and CARTs for ERCOT projects |
| May 18th | WMS prioritization of SO/MO market projects assigned to WMS |
| May 19th | Prioritization process update at PRS |
| May 24th | COPS prioritization of RO/MO market projects assigned to COPS |
| May 26th – June 14th | ERCOT to complete Cost Estimate worksheets, ranking and high level resource estimates for ERCOT projects |
| June 9th | Prioritization Process Update at TAC |
| June 14th | Final combination of all ERCOT requests in priority order/rank |
| June 15th | RMS prioritization of RO/MO market projects assigned to RMS |
| June 16th | ROS prioritization of SO market projects assigned to ROS |
| June 20th | Distribute prioritized market project lists from WMS, COPS, RMS and ROS to PRS |
| June 23rd | Prioritization process update at PRS |
| June 27th | Special PRS meeting to prioritize market projects |
| June 28th – 29th | ERCOT merges prioritized lists |
| June 30th | Distribution of TAC materials (including prioritized list) |
| June 30th – July 8th | Executive Committee review |
| July 7th | TAC approval of prioritized list |
| July 10th – 18th | Build draft of 2006 Portfolio – Arrow Diagrams |
| July 19th | Budget Presentation to Finance and Audit Committee at monthly meeting |
| August 2nd | Public Meeting on Proposed Budget |
| August 4th | Finance and Audit Committee meeting to review budget (Special meeting) |
| August 11th | Finance and Audit Committee meeting to review budget (Special meeting) |
| August 16th | Finance and Audit Committee Recommendation to Board at monthly meeting |
| September 20th | Board Approval of 2006 Budget |
| September 23rd | Preliminary PUCT Filing Review |
| September 30th | PUCT Filing |